## Outages
TDTWG - ERCOT Instance Log
July 26, 2006 - March 31, 2007 Outages
Issue Date | Notification Date | Start Time | End Time | Duration (mins) | Application | Issue Description | Identification Method | Impact | Root Cause | Resolution | Date (to be) Implemented | Notes | TDTWG Meeting Comments
2007-03-23 | 2007-03-23 | 8:42AM 11:01AM | 9:32AM 11:29AM | 78 | TML | Find ESSID and Find Transaction were not available | Monitoring | Unplanned Outage | This issue was caused by backed up transactions. Monitors will be created to alert upon the recurrence of this issue. | Backlog was cleared | 2007-03-23 | A SIR was created for this issue. To Be implemented in April | In implementation - Completion date to be determined - Yellow status/monitoring in progress
2007-03-19 | 2007-03-19 | 9:00AM | 10:36AM | 96 | MarkeTrak | GUI and API not available | Monitoring / Market Notification | Unplanned Outage | Application services locked-up. | Server and services restarted | 2007-03-19 |  | Complete - Green status
2007-03-04 | 3/2/07, 3/4/07 | 8:00AM | 5:30PM | 570 | Retail | Planned Maintenance Outage | Planned Maintenance | Planned Outage | n/a | n/a | 2007-03-04 |  | Complete - Green status
2007-03-02 | 2007-03-02 | 8:30AM | 9:45AM | 75 | TML | Find ESSID and Find Transaction were not available | Monitoring | Unplanned Outage | This issue was caused by backed up transactions. Monitors will be created to alert upon the recurrence of this issue. | Backlog was cleared | 2007-03-02 | We thought this was a one time occurrence | Complete - Green status
2007-02-25 | 2/14/07, 2/25/07 | 8:00AM | 6:00PM | 600 | Retail | Planned Maintenance Outage | Planned Maintenance | Planned Outage | n/a | n/a | 2007-02-25 |  | Complete - Green status
2007-02-23 | 2007-02-23 | 11:05AM | 12:15PM | 70 | TIBCO Database | Inbound and outbound transaction processing halted | Monitoring | Unplanned Outage | Table space issue with the database | Additional storage was allocated to the database | 2007-02-23 | Stabilization from RBP implementation | Complete - Green status
2007-02-18 | 2/8/07, 2/16/07, 2/18/07 |  | 8:00PM | 720 | Retail | Planned Maintenance Outage | Planned Maintenance | Planned Outage | n/a | n/a | 2007-02-18 |  | Complete - Green status
2/10/07 - 2/11/07 | 1/16/07, 1/30/07, 2/9/07, 2/11/07 | 2/10 12:00PM | 2/11 5:00PM | 1740 | Retail | Planned Maintenance Retail Release | Planned Maintenance | Planned Outage | n/a | n/a | 2007-02-11 |  | Complete - Green status
2007-02-07 | 2007-02-08 | 9:15PM | 10:40PM | 85 | Paperfree | Connectivity issue between application and SAN | Monitoring | Unplanned Outage | Issue has been escalated to SAN vendor for root cause analysis | ERCOT effort underway | TBD | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
2007-02-07 | 2007-02-07 | 11:05AM | 11:55AM | 50 | TML (Report Explorer) | TML - Report Explorer unavailable during normal business hours | Market Notification | Unplanned Outage | Connectivity issue across applications | Server and services were restarted | 2007-02-07 | Proactive monitoring and automated recovery is being implemented to correct this issue. | Complete - Green status
2007-02-02 | 2/2/07, 2/5/07 | 6:00AM | 9:30AM | 210 | Siebel | Inbound transaction processing was interrupted following Siebel Batch. | Monitoring | Unplanned Outage | Siebel workflow locked due to incomplete data entering Siebel. | Database maintenance to resolve performance issues | 2007-02-11 | The overlying issue was a performance issue in Siebel causing transactions to take longer to process than normal at certain times of the day. This was resolved with database maintenance during a planned maintenance window. | Complete - Green status
2007-01-24 | 2007-01-24 | 12:00PM | 3:00PM | 180 | NAESB | NAESB was unable to send transactions to Paperfree for processing | Monitoring | Unplanned Outage | Application frozen | Already included in another project | 2007-01-24 | System rebooted. | Complete - SCR745 Phase 1 would have handled this issue - Implementation 11-27-06 Scheduled completion Feb 16, 2007 - Green status
2007-01-22 | 2007-01-22 | 10:06AM | 11:59AM | 112 | NAESB | The NAESB application locked up and required a reboot. All processing suspended. | Monitoring | Unplanned Outage | Application frozen | Already included in another project | 2007-01-22 | System rebooted. | Complete - SCR745 Phase 1 would have handled this issue - Implementation 11-27-06 Scheduled completion Feb 16, 2007 - Green status
2007-01-21 | 1/10/07, 1/19/07, 1/21/07 | 8:00AM | 1:30PM | 330 | Retail | Planned Maintenance Outage | Planned Maintenance | Planned Outage | n/a | n/a | 2007-01-21 |  | Complete - Green status
2007-01-18 | 2007-01-18 | 8:00AM | 8:45AM | 45 | TML | Find ESIID and Find Transaction components of TML unavailable | Monitoring | Unplanned Outage | Server crash caused the disruption of service | Server was restarted | 2007-01-18 |  | Complete - Green status
2007-01-14 | 1/12/07, 1/14/07 | 8:00AM | 11:30AM | 210 | Retail | Planned Maintenance Outage | Planned Maintenance | Planned Outage | n/a | n/a | 2007-01-14 | This outage was used to implement a portion of the Paperfree solution | Complete - Green status
2007-01-09 | 2007-01-09 | 2:00PM | 2:17PM | 17 | TML | Failed memory module | Monitoring | Unplanned Outage | Memory failure | Replaced server memory | 2007-01-09 |  | Complete - Green status
2007-01-08 | 2007-01-08 | 5:00PM | 8:15PM | 195 | Paperfree | Attempted to replace the Paperfree architecture as identified by the on-going Paperfree issues analysis | Monitoring | Unplanned Outage | Server would not come online | Server backed out and implementation rescheduled | TBD | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
2007-01-05 | 2007-01-05 | 3:00AM | 7:30AM | 270 | Paperfree | Problem pulling data from NAESB | Monitoring | Unplanned Outage | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | TBD | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
2007-01-03 | 2007-01-04 | 5:21PM | 7:31PM | 130 | Paperfree | Memory failure in the clustered environment | Monitoring | Unplanned Outage | Memory issue caused a portion of the clustered environment to be replaced. The clustered hardware had specific identification required by the cluster software which cause the clustered solution to fail. | The new hardware was correctly setup and transaction processing was able to resume | 2007-01-03 | Veritas clustering software is a new solution being used to implement SCR745. This issue was a result of learning how to work with this software. | Complete - Green status
2007-01-02 | 1/2/07, 1/3/07, 1/4/07 | 1/2 3:20PM | 1/3 9:50AM | 750 | TIBCO Database | TIBCO database indexing issue | Monitoring | Unplanned Outage | Indexing failed on the TIBCO database | Index rebuilds were required to resolve the issue | 2007-01-03 | Siebel Batch transactions were delayed on 1/2/07 due to this issue | Complete - Green status
2006-12-21 | 2006-12-22 | 12/21 5:45PM | 12/22 8:45AM | 540 | TIBCO | Following an emergency migration to correct the Customer Care process, not all components were reinstated | Monitoring | Unplanned Outage | An inbound processing component was not turned on | Pulse monitoring has been implemented to alert Operations if transactions are not processing | 2006-12-22 |  | Complete - Green status
2006-12-14 | 2006-12-14 | 12:00AM | 8:22AM | 502 | TIBCO Database | TIBCO database partitioning error | Monitoring | Unplanned Outage | Table space on the TIBCO database was consumed | Partitioning rules changed to ensure table space is available | 2006-12-14 | Stabilization from RBP implementation | Complete - Green status
2006-12-08 | 11/14/06, 11/28/06, 11/29/06, 12/7/06, 12/10/06 | 12/8 7:00AM | 12/9 10:10PM | 2350 | Retail | Planned Maintenance Retail Release | Planned Maintenance | Planned Outage | n/a | n/a | 2006-12-08 | Implementation of Retail Business Processes - PR50121, PR50025, PR40007, PR50030, PR50059, PR50060 | Complete - Implementation of RBP - Green status
2006-12-05 | 2006-12-05 | 1:10PM | 1:47PM | 37 | NAESB | The NAESB application locked up and required a reboot. All processing suspended. | Monitoring | Unplanned Outage | Application frozen | Already included in another project | 2006-12-05 | System rebooted. | Complete - SCR745 Phase 1 would have handled this issue - Implementation 11-27-06 Scheduled completion Feb 16, 2007 - Green status
2006-12-04 | 2006-12-04 | 7:00PM | 9:00PM | 120 | TML (Report Explorer) | ERCOT TML Report Explorer unavailable and Lodestar Batch Extracts delivered late | Planned Maintenance | Planned Outage | n/a | n/a | 2006-12-04 | Pre-migration activities to prepare for the RBP release on 12/8/06 | Complete - Green status
2006-11-18 | 2006-11-20 | 8:44AM | 12:45PM | 241 | TML/FasTrak | FasTrak and Texas Market Link Retail Components outage due to server maintenance | Planned Maintenance | Planned Outage | n/a | n/a | 2006-11-18 | Server maintenance lasted longer than expected. | Complete - Green status
2006-11-11 | 10/30/06, 11/11/06 | 12:00PM | 10:49PM | 649 | Retail | Planned Maintenance Retail Release | Planned Maintenance | Planned Outage | n/a | n/a | n/a | SCR745 Phase 2 - Paperfree implementation - PR60006 | Complete - Green status
2006-10-18 | 2006-10-18 | 3:21PM | 4:46PM | 85 | Paperfree | Paperfree application lost connectivity to the Paperfree File Sever. | Monitoring | Unplanned Outage | Configuration issue | Already included in another project | 2006-10-18 | During this time ERCOT was receiving transactions into NAESB and holding in Paperfree. | Complete - SCR745 Phase 2 - implementation 11-11-06 - Green status
2006-10-17 | 2006-10-17 | 10:39AM | 10:57AM | 18 | Paperfree | The NAESB application locked up and required a reboot. All processing suspended. | Monitoring | Unplanned Outage | Application frozen | Already included in another project | 2006-10-17 | System rebooted. | Complete - SCR745 Phase 1 would have handled this issue - Implementation 11-27-06 Scheduled completion Feb 16, 2007 - Green status
2006-10-15 | 10/4/06, 10/9/06, 10/13/06 | 8:00AM | 8:00PM | 720 | Retail | Planned Maintenance Outage | Planned Maintenance | Planned Outage | n/a | n/a | n/a |  | Complete - Green status
2006-10-11 | 2006-10-11 | 5:08PM | 6:10PM | 62 | Retail | Critical memory issue on a Retail Database Server | Monitoring | Unplanned Outage | Hardware failure | Already included in another project | 2006-10-11 | Conversion to the IBM P series server will allow for hot swap capabilities for this type of issue. | Complete - Green status
2006-10-02 | 2006-10-03 | 7:46PM | 7:56PM | 18 | Paperfree | Paperfree File Server network outage | Monitoring | Unplanned Outage | Hardware failure | ERCOT effort underway | 2006-10-03 | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
2006-09-26 | 2006-09-26 | 12:02PM | 4:04PM | 242 | Paperfree | Paperfree File Server not responding | Monitoring | Unplanned Outage | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | 2006-09-26 | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
2006-09-25 | 2006-09-25 | 1:58AM | 3:47PM | 829 | Paperfree | Paperfree File Server not responding | Market Notification / Monitoring | Unplanned Outage | NIC driver error | ERCOT effort underway | 2006-09-25 | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress

## Degradations
TDTWG - ERCOT Instance Log
July 26, 2006 - March 31, 2007 Degradations
Issue Date | Notification Date | Start Time | End Time | Application | Issue Description | Identification Method | Impact | Root Cause | Resolution | Date (to be) Implemented | Notes | TDTWG Meeting Comments
2007-03-21 | 2007-03-22 | n/a | n/a | Siebel | ERCOT experienced high exception counts which caused duplicates due to reprocessing | Monitoring | As a result of the reprocessing effort, some Market Participant’s may receive a second 814_05 or 814_25 with a unique transaction id. | The failure occurred while processing to Siebel for Service Order updates. ERCOT is continuing to research and identify the root cause. | TBD | TBD |  | In investigation - Completion date to be determined - Yellow status/monitoring in progress
12/10/06 - 3/6/07 | 2007-03-08 | n/a | n/a | Paperfree | 814_18 Delete transactions failing Texas Set Validation in Market Participant systems | Market Notification | Rejects from MPs | ERCOT failed to eliminate the TDSP information segment of the 814_18 Delete | ERCOT implemented a code fix for this issue | 2007-03-06 |  | Complete - Green status
2007-03-06 | 2007-03-07 | n/a | n/a | Paperfree | 814_20 transactions being forwarded with errors in the REF segment | Market Notification | Rejects from MPs | ERCOT implemented an internal SIR which resulted in a small number of 814_20 transactions being forwarded with errors in the REF segment causing Market Participant’s to respond with a 997 Reject | SIR was backed out | 2007-03-06 |  | Complete - Green status
2007-03-04 | 2007-03-05 | 7:30PM | 10:30PM | TML | ERCOT experienced service degradation of the Find ESIID, PI API and ContentProxy / Report Explorer applications on Texas Market Link (TML) | Market Notification | Intermittent accessibility issues | Security port issue due to server replacement | Port was opened and applications began to function | 2007-03-04 |  | Complete - Green status
2007-02-26 | 2007-02-26 | 9:45AM | 12:15PM | TML | Intermittent TML and MarkeTrak connectivity issues | Monitoring / Market Notification | Intermittent accessibility issues | Domain controller and DNS issues due to planned maintenance | Server replaced | 2007-02-26 |  | Complete - Green status
2/10/07 - 2/11/07 | 2/12/07, 2/13/07, 2/16/07 | n/a | n/a | TML (Report Explorer) | Delay in extract posting | Monitoring | Extract delay | A subset of extracts were not generated due to the planned outage unexpectedly affecting ERCOT’s ability to catch up on the data lag issues (1/23/07 market notice) | Extract runs were executed following the completion of the planned outage | 2007-02-12 | ERCOT has implemented processes to minimize this type of impact on the market. | Complete - Green status
2007-02-06 | 2007-02-07 | n/a | n/a | Paperfree | Duplicate transactions (29) | Monitoring | Transaction Duplication | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
2/5/07, 2/7/07 | 2/7/07, 2/9/07 | n/a | n/a | Siebel | 'DUP' reject transactions (790) sent due to multiple processing of the same transactions | Monitoring | Reject transactions sent in error | Siebel processed the same transactions multiple times | Database maintenance to resolve performance issues | 2007-02-11 | The overlying issue was a performance issue in Siebel causing transactions to take longer to process than normal at certain times of the day. This was resolved with database maintenance during a planned maintenance window. | Complete - Green status
2007-01-31 | 2007-02-01 | n/a | n/a | Paperfree | Duplicate transactions (32) | Monitoring | Transaction Duplication | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
1/28/07, 1/29/07 | 2007-01-30 | n/a | n/a | Paperfree | Duplicate transactions (60) | Monitoring | Transaction Duplication | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
2007-01-25 | 2007-01-25 | n/a | n/a | TIBCO/Siebel | ERCOT has been experiencing periodic failures of some transactions as they process to Siebel in some cases resulting in “OtherPermissionDenied” reject responses | Monitoring | Delay in processing until reprocessing is complete (generally same day) | Siebel database performance issues | Database maintenance to resolve performance issues | 2007-02-11 | The overlying issue was a performance issue in Siebel causing transactions to take longer to process than normal at certain times of the day. This was resolved with database maintenance during a planned maintenance window. | Complete - Green status
2007-01-23 | 2007-01-23 | n/a | n/a | TML (Report Explorer) | Siebel Service Order Extracts delay | Monitoring | Extract delay | Slow system performance | TBD | n/a |  | More information to be presented the next TDTWG - Yellow status
1/16/07 - 1/17/07 | 1/18/07, 1/19/07, 1/22/07 | n/a | n/a | TML (Report Explorer) | Naming error on Siebel Service Orders Extracts and missing data on Load Extracts | Market Notification | Confusion and delay in information availability | ERCOT determined a data synchronization issue existed between the Lodestar source system and the Lodestar Operational Data Store (ODS) | ERCOT isolated the times for the missing data and repaired the data set in the Lodestar ODS | 2007-01-22 | Operating processes are being updated to include additional monitoring | Complete - Green status
1/17/07 - 1/19/07 | 1/19/07, 1/23/07 | n/a | n/a | Paperfree | Outbound 814 transaction processing issue impacting subset of transactions | Monitoring | Delayed processing of a subset of transactions | Processing issue within Paperfree where certain file types within a directory were not correctly transferred | All of these transactions have been reprocessed by ERCOT | 2007-01-23 | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
2007-01-10 | 1/10/07, 2/15/07 | n/a | n/a | TML | Some transactions are not displaying on the Texas Market Link (TML) Find Transactions function. | Market Notification | Information not available | When the data conversion was done to support the implementation of RBP, a change was made that is causing transactions that were submitted and rejected prior to RBP to not display on TML | A SIR has been written | 2007-02-11 | All accepted pre-RBP orders and all accepted or rejected post-RBP orders are displaying correctly. All service order transactions should be visible. | Complete - Green status
2007-01-05 | 2007-01-05 | n/a | n/a | TML | Intermittent TML and API connectivity issues | Market Notification | Intermittent accessibility issues | Emergency Lodestar database partitioning maintenance | Partitioning completed | 2007-01-05 |  | Complete - Green status
2007-01-03 | 2007-01-04 | n/a | n/a | TIBCO/Siebel | High exception counts | Monitoring | Delayed processing of a subset of transactions | The way in which the TIBCO Siebel Adapter and Siebel Services were restarted caused processing issues | Once the services were restarted transaction processing returned to normal | 2007-01-26 | RBP stabilization | Complete - Green status
2006-12-20 | 12/20/06, 12/29/06, 2/16/07 | n/a | n/a | TML | Entering a phone number while creating customer enrollments/move ins/drops is causing transaction failures | Monitoring | TML only 814_03 outbound transaction failure | The phone number entry is causing the TE segment of the 814_03 to be created but blank causing mapping status rejects | Market Participants have been asked to leave the phone entry field blank until a Priority 1 SIR can be implemented | 2007-02-11 |  | Complete - Green status
12/15/06, 12/16/06, 12/21/06, 12/22/06, 12/23/06, 12/27/06 | 12/18/06, 12/28/06, 12/29/06, 1/2/07, 1/19/07 | n/a | n/a | Paperfree | TX Set validations not occurring on a subset of 867 transactions | Monitoring | 867s not forwarded, delay in Siebel Service Order completion, delay in reprocessing | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | TBD | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
12/14/06 - 12/18/06 | 12/14/06, 12/15/06, 12/18/06 | n/a | n/a | MarkeTrak | API timeout issues | Market Notification | Market Participants utilizing the API are receiving a timeout response | Processing time for submissions exceeded due to bad data handling | Additional exception handling added to the API functionality | 2006-12-18 |  | Complete - Green status
2006-12-11 | 12/11/06, 12/12/06, 12/13/06 | n/a | n/a | TML/API | Intermittent TML and API connectivity issues | Market Notification | Intermittent accessibility issues | Memory allocation issue due to a process not closing connections properly | Process was modified and monitored | 2006-12-13 |  | Complete - Green status
2006-12-05 | 2006-12-05 | n/a | n/a | TML (Report Explorer) | Extract posting delays | Monitoring | Report Delay | Planned reboots from 12/4 notification | Report processing caught up | n/a | Siebel Service Order Extract Load Extract Generation Extract Settlement & Billing Extract | Complete - Green status
2006-11-13 | 11/13/06, 11/14/06 | n/a | n/a | MarkeTrak | The MarkeTrak system was successfully implemented yesterday, November 13th. Throughout the day, ERCOT Identified four recurring issues Market Participants experienced with MarkeTrak | Market Notification | Intermittent accessibility issues | Stabilization | Configuration changes and additional user training | 2006-11-14 | Configuration, market user setups, etc were part of stabilization the day of market go-live. | Complete - Green status
2006-11-09 | N/A | 12:34PM | 1:17PM | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP, Temporary fix implemented in October | Complete - Green status
2006-10-26 | 2006-10-26 | 1:23AM | 1:25AM | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP, Temporary fix implemented in October | Complete - Green status
2016-10-14 | 2006-10-16 | 10/14 7:40AM | 10/15 7:10AM | Paperfree | Outbound processing of 814 and 824 transactions suspended | Manual Troubleshooting | Degradation | Process hung | Already included in another project | 2006-10-15 | Process restarted. | Complete - SCR745 Phase 2 - implementation 11-11-06 - Green status
2006-10-10 | 2006-10-10 | n/a | n/a | TML (Report Explorer) | ERCOT was unable to successfully create and post all Siebel Service Order Full Extracts | Market Notification | Report Delay | Disk full on storage device | One time occurrence | 2006-10-10 |  | Complete - Green status
2006-10-09 | 2006-10-09 | n/a | n/a | TML (Report Explorer) | Errors when downloading Settlement Statements and the following extracts: ESIID Service History and Usage, Settlement & Billing, Load, Generation | Market Notification / Monitoring | Settlements and Extracts not available | Unknown | One time occurrence | n/a |  | Complete - Green status
2006-10-05 | 2006-10-05 14:49 | 12:36AM | 12:42AM | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP, Temporary fix implemented in October | Complete - Green status
2006-09-27 | 2006-09-27 | n/a | n/a | TIBCO | Delayed 867_03 IDR and NIDR Activity Reports | Monitoring | Report Delay | Data Exception | Already included in another project | 2006-09-28 | Increased Hawk monitoring to capture and correct exception immediately | Complete - Green status
2006-09-26 | 2006-09-29 | 12:02AM | 4:04PM | Paperfree | 997s not sent during outages | Market Notification / Daily Report | Transaction Loss | TBD | Not already included in another project | n/a | Result of Paperfree outage | Complete - SCR745 Phase 2 - implementation 11-11-06 - Green status
2006-09-25 | 2006-09-29 | 1:58AM | 3:47PM | Paperfree | 997s not sent during outages | Market Notification / Daily Report | Transaction Loss | TBD | Not already included in another project | n/a | Result of Paperfree outage | Complete - SCR745 Phase 2 - implementation 11-11-06 - Green status
9/22/06 - 9/26/06 | 9/22/06 - 9/27/06 | n/a | n/a | Paperfree | 814 and 867 transactions duplicated | Monitoring | Transaction Duplication | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
2006-09-20 | 2006-09-20 | n/a | n/a | TML API | Market Participants receiving the “No ESI ID found” message when using the API and to research | Market Notification | Information not available | Code issue | Already included in another project | 2006-09-28 |  | Complete - Green status
2006-09-21 | 2006-09-21 | ~2:00AM | ~4:00AM | Siebel | Siebel Batch continued following SBMI issue with future dated evaluation date | Market Notification | Order Cancellations | Incorrect date used | One time occurrence | 2006-09-21 | Process change and Training implemented | Complete - Green status
2006-09-21 | 2006-09-21 | 12:55AM | 1:03AM | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
2006-09-19 | 2006-09-19 | n/a | n/a | Paperfree | Annual Validation backlog of 814_20 Maintains | Market Coordination / Monitoring | Backlog | Annual Validation and system limitations | Annual occurrence | n/a | current backlog is ~300K | Complete for 2006 - Green status - long term fix to be implemented in Feb 07
2006-09-11 | 2006-09-11 | 12:46AM | 12:49AM | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
8/15/06 - 9/8/06 | 2006-09-08 | n/a | n/a | Siebel | ESIID address deleted from database | Exception Processing | Rejected Transactions | Software Bug | Already included in another project | n/a | Implementation date to be determined | Complete - Green status
2006-09-05 | 2006-09-05 | n/a | n/a | TIBCO | Posting delay for extracts and reports | Market Notification / Monitoring | Report Delay | Component Unresponsive | Already included in another project | 2006-09-06 | Redefined Hawk monitoring agent rules | Complete - Architecture change in place - Green Status
2006-08-30 | 2006-08-31 | 9:17PM | 9:28PM | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
2006-08-24 | 2006-08-24 | n/a | n/a | TIBCO | Posting delay for extracts and reports | Market Notification / Monitoring | Report Delay | Component Unresponsive | Already included in another project | 2006-08-24 | Implementation of Hawk monitoring agent | Complete - Architecture change in place - Green Status
2006-08-08 | 2006-08-08 | n/a | n/a | TIBCO | Delayed TDSP ESIID Report | Monitoring | Report Delay | Code issue with implementation | Already included in another project | 2006-08-24 |  | Complete - Architecture change in place - Green Status
2006-08-02 | 2006-08-02 | 1:10AM | 1:13AM | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
2006-07-27 | 2006-07-27 | 1:00AM | 9:30AM | Paperfree | 814 and 867 transactions duplicated | Monitoring | Transaction Duplication | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress

## 2007 Service Availability
Month | Service | Gross Available Minutes | Planned Outage Minutes | Net Available Minutes | Unplanned Outage Minutes | Percent Availability
January | Retail Transaction Processing | 44640 | 540 | 44100 | 1637 | 96.29%
February | Retail Transaction Processing | 40320 | 3060 | 37260 | 365 | 99.02%
March | Retail Transaction Processing | 44640 | 570 | 44070 | 0 | 100%
April | Retail Transaction Processing | 43200 |  | 43200 |  | 100%
May | Retail Transaction Processing | 44640 |  | 44640 |  | 100%
June | Retail Transaction Processing | 43200 |  | 43200 |  | 100%
July | Retail Transaction Processing | 44640 |  | 44640 |  | 100%
August | Retail Transaction Processing | 44640 |  | 44640 |  | 100%
September | Retail Transaction Processing | 43200 |  | 43200 |  | 100%
October | Retail Transaction Processing | 44640 |  | 44640 |  | 100%
November | Retail Transaction Processing | 43200 |  | 43200 |  | 100%
December | Retail Transaction Processing | 44640 |  | 44640 |  | 100%
Year to Date | Retail Transaction Processing | 129600 | 4170 | 125430 | 2002 | 98.4%
(to Mar. 31)

## 2006 Service Availability
Month | Service | Gross Available Minutes | Planned Outage Minutes | Net Available Minutes | Unplanned Outage Minutes | Percent Availability
January | Retail Transaction Processing | 44640 | 1620 | 43020 | 105 | 99.76%
February | Retail Transaction Processing | 40320 | 990 | 39330 | 556 | 98.59%
March | Retail Transaction Processing | 44640 | 960 | 43680 | 0 | 100%
April | Retail Transaction Processing | 43200 | 715 | 42485 | 0 | 100%
May | Retail Transaction Processing | 44640 | 3255 | 41385 | 402 | 99.03%
June | Retail Transaction Processing | 43200 | 0 | 43200 | 0 | 100%
July | Retail Transaction Processing | 44640 | 390 | 44250 | 304 | 99.31%
August | Retail Transaction Processing | 44640 | 885 | 43755 | 0 | 100%
September | Retail Transaction Processing | 43200 | 0 | 43200 | 1071 | 97.52%
October | Retail Transaction Processing | 44640 | 720 | 43920 | 183 | 99.58%
November | Retail Transaction Processing | 43200 | 569 | 42631 | 0 | 100%
December | Retail Transaction Processing | 44640 | 3790 | 40850 | 1079 | 97.36%
Year to Date | Retail Transaction Processing | 525600 | 13894 | 511706 | 3700 | 99.27%
(to Dec. 31)