## How To Use
Document Definition:
This document is a summary of ERCOT IT incidents, or service delivery failures, that have merited a Market Notice
This document also contains service availability reports for Retail Transaction Processing, MarkeTrak, and TML
Spreadsheet Tab: | Contents:
Annual Summary: | This tab summarizes the number of incident types and provides cumulative outage duration data by incident type, but provides no detail into the root cause
or specific dates regarding each incident
Monthly Summary: | This tab summarizes the number of incident types by month to inform the reader of what month to examine for detailed information regarding an incident
Detailed Incident data: | This tab contains the detailed information for each incident summarized on the annual and monthly tabs
2006 Retail Transaction Processing Availability | Retail transaction processing service availability for calendar year 2006
2007 Retail Transaction Processing Availability | Retail transaction processing service availability for calendar year 2007
2007 MarkeTrak Availability | MarkeTrak availability for June 2007 through December 2007
2007 TML Availability | TML availability for June 2007 through December 2007
General Definitions:
Outage: | An unplanned change in ERCOT IT systems that prevents users from being able to access the systems
Degradation: | An event that causes the normal levels of ERCOT IT systems to be impacted while still allowing for minimal processing of or access to these systems
Transaction Count: | Reflective of the number of duplicate transactions associated with an incident noticed by an initial ERCOT market notice
Duration: | Refers to the length of time, in minutes, of an incident involving the outage of one of systems covered in the Retail IT Market Services SLA
Market Input:
ERCOTRetailIncidentLog@ercot.com | Email address for the market to send Market Impact data to ERCOT
Incident Type Definitions:
Incident Type: | Definition:
PaperFree Application | A retail transaction processing incident caused by a failure within the PaperFree application (not infrastructure)
Siebel Application | A retail transaction processing incident caused by a failure within the Siebel application (not infrastructure)
NAESB Application | A retail transaction processing incident caused by a failure within the NAESB application (not infrastructure)
TIBCO Application | A retail transaction processing incident caused by a failure within the TIBCO application (not infrastructure)
Human Error | A retail transaction processing incident caused by human error
TML Application | A TML outage caused by failure of the TML application (not infrastructure)
TML (report explorer) Application | A TML (report explorer) outage caused by failure of the application (not infrastructure)
Database | A retail transaction processing incident caused by a database outage
Infrastructure | A retail transaction processing incident caused by an infrastructure failure (server, switch, etc…)
MarkeTrak Application | A MarkeTrak incident caused by a failure of the MarkeTrak application
PaperFree Duplicate Transactions | An incident resulting in duplicate retail transactions sent by ERCOT to Market Participants caused by a PaperFree application failure
Siebel Duplicate Transactions | An incident resulting in duplicate retail transactions sent by ERCOT to Market Participants caused by a Siebel application failure
TML Connectivity | An incident resulting in the inability of Market Participants being able to connect to TML
TML Functionality Error | A failure of TML to function correctly
MarkeTrak Connectivity | An incident resulting in the inability of Market Participants being able to connect to MarkeTrak
Slow System Performance | An incident resulting in abnormally slow or delayed retail transaction processing without system outages
Transaction Processing Errors | Any incident resulting in high exception counts or other errors related to retail transaction processing
Other | Any Retail Market IT systems incident that is not described by another defined incident type
Availability | The ability of a component or IT service to perform its required function over a stated period of time
Planned Outage | A planned change in ERCOT IT systems that prevents users from being able to access the systems
Unplanned Outage | An unplanned change in ERCOT IT systems that prevents users from being able to access the systems
Incident | Any event that causes the agreed levels of service of ERCOT IT systems to be impacted
NAESB | The Texas electric market has implemented NAESB EDM v1.6 as the required data transport mechanism.
EDI | Electronic Data Interchange – the transfer of data electronically
PaperFree | The data validation and transformation engine utilized in ERCOT’s retail transaction processing system
Integration | The creation of links between previously separate computer systems, applications, services or processes
Retail Transactions:
814 – Enrollment transaction used for registration in the retail market
824 – Application advice transaction used for responding to errors on 867 usage transactions
867 – Usage transaction used for reporting consumption or generation of electricity
997 – Acknowledgement transaction
Gross minutes | Total minutes in a month
Net minutes | Gross minutes minus planned outage minutes
Planned outage minutes | Minutes used by ERCOT during the maintenance and release windows
Unplanned outage minutes | Minutes retail transaction processing services were not available that are outside of the planned use of the maintenance and release windows
Exception outage minutes | Minutes outside of the maintenance and release outage windows that have been granted exception from the availability metric (TX Set, etc.)
Service availability percent | The percent of time that retail transaction processing services were available, not including planned outage minutes
Siebel | The customer registration software used in ERCOT's retail transaction processing system

## Annual Summary
ERCOT IT Incident Market Notice Summary
Annual Breakdown (July 2006 - Current)
2007
Incident Type |  |  | Incident Type |  | Incident Type
Outage - Root Cause |  |  | Degradation - Root Cause |  | Degradation - Effect
Root Cause | Number of occurrences | Duration (minutes) | Root Cause | Number of occurrences | Resulting effect | Number of occurrences | Transaction Count
PaperFree Application |  |  | PaperFree Application | 8 | PaperFree Duplicate Transactions | 4 | 3966
Siebel Application | 1 | 210 | Siebel Application | 3 | Siebel Duplicate Transactions | 1 | 790
NAESB Application | 2 | 292 | NAESB Application |  | TML Connectivity | 5
TIBCO Application | 6 | 563 | TIBCO Application | 2 | TML Functionality Error | 1
Human Error | 4 | 955 | Human Error | 2 | MarkeTrak Connectivity | 2
TML Application |  |  | TML Application | 4 | Slow System Performance | 1
TML (Report Explorer) Application | 2 | 135 | TML (Report Explorer) Application |  | Transaction Processing Errors | 12
Database | 4 | 1078 | Database | 2 | Other | 1
Infrastructure | 13 | 1304 | Infrastructure | 4
MarkeTrak Application | 3 | 685 | MarkeTrak Application | 1
Other |  |  | Other | 1
2006 (July - December)
Incident Type |  |  | Incident Type |  | Incident Type
Outage - Root Cause |  |  | Degradation - Root Cause |  | Degradation - Effect
Root Cause | Number of occurrences | Duration (minutes) | Root Cause | Number of occurrences | Resulting effect | Number of occurrences | Transaction Count
PaperFree Application |  |  | PaperFree Application | 7 | PaperFree Duplicate Transactions | 2 | 40544
Siebel Application |  |  | Siebel Application | 8 | Siebel Duplicate Transactions | 6 | n/a
NAESB Application | 2 | 55 | NAESB Application |  | TML Connectivity | 1
TIBCO Application |  |  | TIBCO Application | 1 | TML Functionality Error | 2
Human Error | 1 | 540 | Human Error |  | MarkeTrak Connectivity | 2
TML Application |  |  | TML Application | 3 | Slow System Performance | 2
TML (Report Explorer) Application |  |  | TML (Report Explorer) Application |  | Transaction Processing Errors | 5
Database | 1 | 502 | Database |  | Other
Infrastructure | 3 | 909 | Infrastructure
MarkeTrak Application |  |  | MarkeTrak Application | 1
Other |  |  | Other

## Monthly Summary
ERCOT IT Incident Market Notice Summary
Monthly Breakdown (July 2006 - Current)
Incident Summary
| Outage - Root Cause | [9 empty] | Degradation - Root Cause | [10 empty] | Degradation - Effect
2007 | PaperFree Application | Siebel Application | NAESB Application | TIBCO Application | Human Error | TML Application | TML (Report Explorer) Application | Database | Infrastructure | MarkeTrak Application | PaperFree Application | Siebel Application | NAESB Application | TIBCO Application | Human Error | TML Application | TML (Report Explorer) Application | Database | Infrastructure | MarkeTrak Application | Other | PaperFree Duplicate Transactions | Siebel Duplicate Transactions | TML Connectivity | TML Functionality Error | MarkeTrak Connectivity | Slow System Performance | Transaction Processing Errors | Other
January |  |  | 2 |  | 1 |  |  |  | 5 |  | 3 |  |  |  | 1 | 2 |  | 1 |  |  |  | 2 |  | 1 | 1 |  |  | 3
February |  | 1 |  |  |  |  | 1 | 1 | 1 |  | 1 | 1 | [6 empty] | 1 |  |  | 1 | 1 | 1
March |  |  |  | 2 | [5 empty] | 1 | 1 | 1 |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 3
April |  |  |  |  | 1 | [9 empty] | 1 | [12 empty] | 1
May | [13 empty] | 1 | [13 empty] | 1
June |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 | [5 empty] | 1 |  | 1
July |  |  |  | 1 | 1 |  |  |  | 2 |  | 1 | [16 empty] | 1
August | [8 empty] | 1 |  |  | 1 | [5 empty] | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 | 1 | 1
September | [9 empty] | 1 | [8 empty] | 1 | [8 empty] | 1
October |  |  |  | 2 |  |  |  |  | 2 | 1 | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1
November |  |  |  |  | 1 |  | 1 | 2 | 1
December
Incident Summary
| Outage - Root Cause | [9 empty] | Degradation - Root Cause | [10 empty] | Degradation - Effect
2006 | PaperFree Application | Siebel Application | NAESB Application | TIBCO Application | Human Error | TML Application | TML (Report Explorer) Application | Database | Infrastructure | MarkeTrak Application | PaperFree Application | Siebel Application | NAESB Application | TIBCO Application | Human Error | TML Application | TML (Report Explorer) Application | Database | Infrastructure | MarkeTrak Application | Other | PaperFree Duplicate Transactions | Siebel Duplicate Transactions | TML Connectivity | TML Functionality Error | MarkeTrak Connectivity | Slow System Performance | Transaction Processing Errors | Other
July | [10 empty] | 1 | [10 empty] | 1
August | [11 empty] | 2 | [10 empty] | 2
September | [8 empty] | 1 |  | 4 | 4 |  |  |  | 1 | [5 empty] | 1 | 2 |  | 1 |  | 1 | 4
October |  |  | 1 | [5 empty] | 2 |  | 1 | 1 | [10 empty] | 1 |  |  |  | 1
November | [11 empty] | 1 | [7 empty] | 1 |  |  | 1 |  |  | 1
December |  |  | 1 |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 2 | [7 empty] | 1 | 1 | 1 |  | 1

## 2007 Detailed Incident Data
ERCOT IT Incident Market Notice Summary
January 1, 2007 - November 30, 2007 Incidents
Month | Issue Date | Notification Date | Notification ID | Start Time | End Time | Duration (mins) | SLA Impacted | Application Impacted | Issue Description | Root Cause | Service Impact | Service Impact Detail | Identification Method | Market Impact | Root Cause Details | Resolution | Date (to be) Implemented | Notes | Current Status
November | 2007-11-18 | 2007-11-18 | M-A111807-03 | 8:00PM | 8:02PM | 2 | Retail Market | Retail Market | Planned Maintenance Outage over-run | Infrastructure | Outage | Unplanned Outage | Monitoring | Unknown | Planned Maintenance Outage over-run | Maintenance completed | 2007-11-18 |  | Complete - Green status
November | 2007-11-18 | 2007-11-14 | M-A111407-01, 02, 03 | 8:00AM | 8:00PM | 720 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-11-18 |  | Complete - Green status
November | 2007-11-14 | 2007-11-14 | M-B111407-01, 02, 03 | 10:15AM | 11:35AM | 80 | n/a | TML (report explorer) Application | Report Explorer was not available | TML (report explorer) Application | Outage | Unplanned Outage | Monitoring | Unknown | Unusual load pattern on server caused server to over-run capacity | Additional resources were allocated | 2007-11-14 | No known cause at this time. | Complete - Green status
November | 2007-11-13 | 2007-11-13 | R-A111307-01 | 8:51AM | 10:16AM | 85 | TML / MarkeTrak | TML / MarkeTrak API | TML and MarkeTrak API functionality was interrupted | Human Error | Outage | Unplanned Outage | Monitoring | Unknown | Scripting errors caused connection to the EAI server to be disabled | Script was corrected | 2007-11-13 |  | Complete - Green status
November | 2007-11-12 | 2007-11-12 | R-A111207-01 | 12:50PM | 2:15PM | 85 | Retail | TIBCO | Retail transaction processing was interrupted | Database | Outage | Unplanned Outage | Monitoring | Unknown | Storage path failed causing the database to suspend | Failed path was disabled | 2007-11-12 | Ticket opened with vendors | Complete - Green status
November | 2007-11-10 | 2007-10-10 | M-A101107-01, 02, 03, 04 | 12:00PM | 9:40PM | 580 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-11-10 |  | Complete - Green status
November | 2007-11-07 | 2007-11-07 | R-A110707-01, 02 | 1:47AM | 5:00AM | 193 | Retail Market | Retail Market | Retail Market applications offline | Database | Outage | Unplanned Outage | Monitoring | Unknown | Oracle bug was identified within the database listener because of this issue. | Database listener was modified to suppress this error. | 11/7.07 |  | Complete - Green status
November | 2007-11-04 | 2007-10-24 | M-A102407-01, 02, 03 | 8:00AM | 2:45PM | 405 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-11-04 |  | Complete - Green status
October | 2007-10-31 | n/a | n/a | n/a | n/a | n/a | MarkeTrak | MarkeTrak API | MarkeTrak API unavailable for a few Market Participants | MarkeTrak Application | MarkeTrak Connectivity | Connectivity issues for a few Market Participants | Market Notification | Unknown | The SSL Digital Certificate expired for the server | A new certificat was installed | 2007-11-01 |  | Complete - Green status
October | 2007-10-29 | 2007-10-31 | R-A103107-01, 02 | n/a | n/a |  | Retail | Paperfree | ERCOT experienced an issue with an inbound process which created a delay in processing transactions | Paperfree Application | Transaction Processing Errors | Delay in processing a small number of transactions | Monitoring | Unknown | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
October | 2007-10-22 | 2007-10-22 | M-A102207-01, 02 | 3:25PM | 3:45PM | 20 | TML | TML | FindESIID and FindTransaction not available | TIBCO Application | Outage | Unplanned Outage | Monitoring | Unknown | Components of the application hung and required restart | Restarted hung components | 2007-10-22 |  | Complete - Green status
October | 10/20/07 - 10/22/07 | 2007-10-15 | M-B101507-01, 02, 03, 04 | 10/20 5:30PM | 10/22 12:00PM | 2550 | TML | TML | Unplanned Maintenance Outage | n/a | n/a | Maintenance Outage | Maintenance | Unknown | n/a | n/a | 2007-10-22 |  | Complete - Green status
October | 2007-10-19 | 2007-10-19 | R-A101907-01 | 12:15PM | 12:45PM | 30 | MarkeTrak | MarkeTrak | Page cannot be displayed error message for users | MarkeTrak Application | Outage | Unplanned Outage | Monitoring / Market Notification | Unknown | The MarkeTrak outage was caused by user authentication and internal application restart errors. | Application did successfully restart | 2007-10-18 |  | Complete - Green status
October | 2007-10-15 | 2007-10-15 | M-C101507-01, 02 | 4:55PM | 5:30PM | 35 | Retail Market | Retail Market | ERCOT experienced an Unplanned Outage of Retail Market applications | TIBCO Application | Outage | Unplanned Outage | Monitoring | Unknown | The Enterprise Architecture Integration application failed and corrupted. Commercial Operations rebuilt the application in order to resume processing | Vendor recommends a version upgrade to resolve this issue. | 2007-12-09 | An emergency SIR is in Test now. Scheduled release date is 8/11/07 now 12/9/07 | In Test - 8/11/07 release date - Yellow status/monitoring in progress
October | 2007-10-14 | 2007-10-15 | M-A101507-01, 02 | 5:45PM | 8:45PM | 180 | Retail Market | Retail Market | Retail market outage caused by reboot of database server | Infrastructure | Outage | Unplanned Outage | Monitoring | Unknown | Backup service caused slowdown of transaction processing | Reboot of database server | 2007-10-14 |  | Complete - Green status
October | 2007-10-09 | 2007-10-09 | M-A100907-01 | 11:15AM | 11:50AM | 35 | TML | TML | TML accessibility issues | TML Application | TML Connectivity | Intermittent accessibility issues | Monitoring / Market Notification |  | ERCOT site failover caused errors within the application | ERCOT failed back to the previous site | 2007-10-09 |  | Complete - Green status
October | 2007-10-07 | 2007-10-07 | M-A092707-03 | 8:00PM | 9:37PM | 97 | Retail Market | Retail Market | The planned migration ran longer than the timeframe outlined in the approved exception | Infrastructure | Outage | Unplanned Outage | Maintenance | Unknown | Patching maintenance exceeded allowed maintenance window | Maintenance complete | 2007-10-07 |  | Complete - Green status
October | 2007-10-07 | 2007-09-27 | M-A092707-01, 02, 03 | 8:00AM | 8:00PM | 720 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-10-07 |  | Complete - Green status
September | 9/22/07 - 9/23/07 | 2007-08-09 | M-B080907-01, 02, 03, 04, 05 | 9/22 12:00PM | 9/23 2:00PM | 1560 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-09-23 |  | Complete - Green status
September | 2007-09-18 | 2007-09-20 | R-C092007-01, 02 | n/a | n/a |  |  | TIBCO | ERCOT experienced an issue with an inbound process which created a delay in processing transactions | Infrastructure | Transaction Processing Errors | Delay in processing a small number of transactions | Monitoring | Unknown | A storage infrastructure device failed causing a path issue with regard to transaction processing | Device was corrected | 2007-09-20 |  | Complete - Green status
September | 9/19/07 - 9/20/07 | 2007-09-20 | R-A092007-01 | 9/19 1:42PM | 9/20 11:01AM | 559 | MarkeTrak | MarkeTrak | ERCOT experienced a MarkeTrak API service outage | MarkeTrak Application | Outage | Unplanned Outage | Monitoring | Unknown | Web service components became inaccessible for the application thus causing the application not to function. | Web service components were restarted | 2007-09-20 | Monitoring and training regarding the monitoring in place were implemented. | Complete - Green status
September | 9/15/07 - 9/17/07 | 2007-08-29 | M-A090507-01, 02, 03 | 9/15 12:00PM | 9/16 10:00PM | 2040 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-09-16 | AIX Migration Successful | Complete - Green status
September | 9/8/07 - 9/10/07 | 2007-08-29 | M-A082907-01, 02, 03 | 9/8 12:00PM | 9/10 12:00AM | 2160 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-09-10 | AIX Rollback | Complete - Green status
August | 2007-08-27 | 2007-08-27 | R-A082707-01, 02, 03 | 5:00AM | 2:30PM | 570 | Retail | Siebel | ERCOT experienced a degradation of the Retail Transaction Processing system | Database | Slow System Performance | Delay in transaction processing | Monitoring | Unknown | The issue was identified to be a result of the database shutdown/startup due to the migration/rollback of the AIX migration | Database statistics were run and the application issues were resolved | 2007-08-27 | Transaction backlog was processed the same day | Complete - Green status
August | 2007-08-27 | 2007-08-27 | R-M081607-04 | 12:00AM | 2:40AM | 160 | Retail Market | Retail Market | The planned migration ran longer than the timeframe outlined in the approved exception | Infrastructure | Outage | Unplanned Outage | Maintenance | Unknown | Application infrastructure issues experienced while performing the rollback of the AIX migration | Issues resolved through the detailed rollback process | 2007-08-27 |  | Complete - Green status
August | 8/25/07 - 8/27/07 | 2007-08-16 | R-M081607-01, 02, 03, 04 | 8/25 12:00PM | 8/27 12:00AM | 2160 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-08-27 |  | Complete - Green status
August | 8/13/07 - 8/22//07 | 2007-08-23 | R-A082307-01 | n/a | n/a |  |  | Siebel | ERCOT experienced a Customer Registration System batch processing delay | Siebel Application | Transaction Processing Errors | Delay in processing a small number of batch process transactions | Monitoring | Unknown | TBD | TBD | TBD | The delayed transactions were processed on 8/23/07. | In investigation - Completion date to be determined - Yellow status/monitoring in progress
August | 8/03/07 - 8/14/07 | 2007-08-10 | R-A081007-01, 02, 03, 04 | n/a | n/a |  |  | NAESB | ERCOT experienced an issue with the Customer Care Notification process | Other | Other | Delay in processing customer care notification files | Monitoring | Unknown | The Customer Care vendor had difficulties updating their Secure Socket Layer (SSL) certificate | ERCOT assisted the vendor with the installation | 2007-08-14 |  | Complete - Green status
August | 8/07/07 - 8/14/07 | 2007-08-07 | R-A080707-01, 02, 03, 04 | n/a | n/a |  |  | MarkeTrak | ERCOT experienced an unplanned degradation for the MarkeTrak application | Infrastructure | MarkeTrak Connectivity | Degradation of application services | Monitoring / Market Notification | Unknown | This issue was related to a network setting | Network configuration changes were made | 2007-08-14 |  | Complete - Green status
July | 2007-07-29 | 2007-07-30 | R-A073007-01 | 8:00PM | 10:00PM | 120 | Retail | NAESB | ERCOT experienced a delay in processing of Electronic Data Interchange transactions | Human Error | Outage | Unplanned Outage | Monitoring | Unknown | During the planned maintenance outage scheduled for Sunday, July 29, 2007, ERCOT experienced difficulty with some of the configurations which caused a delay in processing | Configuration error was corrected and documented | 2007-07-29 |  | Complete - Green status
July | 2007-07-29 | 2007-07-24 | M-B072407-01, 02, 03 | 8:00AM | 6:30PM | 630 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-07-29 |  | Complete - Green status
July | 2007-07-25 | 2007-07-25 | R-A072507-01 | 10:41AM | 11:24AM | 43 | MarkeTrak | MarkeTrak | ERCOT experienced an Unplanned Outage of the MarkeTrak application | Infrastructure | Outage | Unplanned Outage | Monitoring | Unknown | The outage was related to the Storage Area Network (SAN). An emergency software upgrade of the SAN director was required | SAN director firmware was upgraded by the vendor on 7/25/07 | 2007-07-25 |  | Complete - Green status
July | 2007-07-24 | 2007-07-24 | R-A072407-01, 02, 03, 04 | 7:00AM | 11:15AM | 255 | Retail Market | Retail Market | ERCOT experienced an Unplanned Outage of Retail Market applications | TIBCO Application | Outage | Unplanned Outage | Monitoring | Unknown | The Enterprise Architecture Integration application failed and corrupted. Commercial Operations rebuilt the application in order to resume processing | Vendor recommends a version upgrade to resolve this issue. | 2007-08-11 | An emergency SIR is in Test now. Scheduled release date is 8/11/07 now 12/9/07 | In Test - 8/11/07 release date - Yellow status/monitoring in progress
July | 2007-07-23 | 2007-07-23 | R-A072307-01 | 10:16AM | 11:36AM | 80 | MarkeTrak | MarkeTrak | ERCOT experienced an Unplanned Outage of the MarkeTrak application | Infrastructure | Outage | Unplanned Outage | Monitoring | Unknown | The outage was related to the Storage Area Network (SAN). An emergency software upgrade of the SAN director was required | SAN director firmware was upgraded by the vendor on 7/25/07 | 2007-07-23 | The vendor indicated that this issue would not happen again. | Complete - Green status
July | 2007-07-22 | 2007-07-20 | M-A072007-01, 02 | 8:00AM | 7:00PM | 660 | TML | TML | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-07-22 |  | Complete - Green status
July | 2007-07-08 | 2007-07-05 | M-A070507-01, 02 | 8:00AM | 4:15PM | 495 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-07-08 |  | Complete - Green status
July | 7/3/07 - 7/5/07 | 2007-07-05 | R-A070507-01, 02 | n/a | n/a |  |  | Paperfree | ERCOT experienced difficulty in processing 867 transactions through TX Set validations | Paperfree Application | Transaction Processing Errors | 867 processing issues | Monitoring | Unknown | TBD | TBD | TBD | 867 processing was successful for more than a week after TX Set migration. The fix was suppressing the system logs. | In investigation - Completion date to be determined - Yellow status/monitoring in progress
July | 2007-07-01 | 2007-06-21 | M-B062107-01, 02, 03 | 8:00AM | 6:10PM | 610 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2006-06-24 |  | Complete - Green status
June | 2007-06-27 | 2007-06-27 | R-A062707-01, 02, 03 | 2:30AM | 2:40PM | 730 | Retail Market | Retail Market | ERCOT experienced an Unplanned Outage of Retail Market applications | Database | Outage | Unplanned Outage | Monitoring | Unknown | The root cause of the issue was due to database maintenance required on one of the main Registration system tables | Statistics were run on the Siebel database | 2007-06-27 | The current maintenance plan is being reviewed so that ERCOT is able to handle an increase in volume without causing these types of issues | Complete - Green status
June | 6/22/07 - 6/24/07 | 2007-05-30 | M-A053007-01, 02, 03, 04, 05, 06 | 6/22 1:45PM | 6/24 10:45AM | 2700 | Retail Market | Retail Market | Planned Maintenance Retail Release - TX Set 3.0 | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2006-06-24 |  | Complete - Green status
June | 2007-06-20 | 2007-06-21 | R-A062107-01, 02 | 6:50PM | 8:30PM | 100 | Retail | TIBCO | ERCOT unable to process transactions through TIBCO | TIBCO Application | Outage | Unplanned Outage | Monitoring | Unknown | The application over-committed the memory on the server. Proactive monitors and alerts have been implemented. | Memory was cleared and application was restarted | 2007-06-20 |  | Complete - Green status
June | 6/19/07 - 6/21/07 | 2007-06-19 | R-A061907-01, 02, 03 | n/a | n/a |  |  | TML | Intermittent TML and MarkeTrak connectivity issues | TML Application | TML Connectivity | Intermittent accessibility issues | Monitoring / Market Notification | Unknown | Single sign-on authentication application issues were causing the site to appear unavailable. | ERCOT worked with the vendor to resolve the issue | 2007-06-21 | A temporary fix was implemented. ERCOT is evaluating an additional service pack from the vendor which should resolve these types of issues in the future. | In Build - Completion date to be determined - Yellow status/monitoring in progress
June | 2007-06-07 | 2007-06-08 | R-A060807-01 | n/a | n/a |  |  | Paperfree | Duplicate transactions (3,845) | Paperfree Application | Paperfree Duplicate Transactions | Transaction Duplication | Monitoring | Unknown | One of the Paperfree processes hung causing duplicate transactions to be sent to the market | Process was killed and restarted | 2007-06-07 |  | Complete - Green status
June | 2007-06-03 | 2007-05-24 | M-A052407-01, 02, 03 | 8:00AM | 4:50PM | 530 | Retail Market | Retail Market | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-06-03 |  | Complete - Green status
May | 5/12/07 - 5/13/07 | 2007-05-02 | M-A050207-01, 02, 03 | 5/12 12:00PM | 5/13 10:55AM | 1375 | Retail | Retail | Planned Maintenance Retail Release | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-05-13 |  | Complete - Green status
May | 2007-05-06 | 2007-04-26 | M-A042607-01, 02, 03 | 8:00AM | 1:20PM | 320 | Retail | Retail | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-05-06 |  | Complete - Green status
May | 2007-05-02 | 2007-05-03 | R-A050307-01, 02, 03 | n/a | n/a |  |  | TIBCO | ERCOT experienced high exception counts | TIBCO Application | Transaction Processing Error | Transactions required reprocessing efforts. Transaction protocols should not have been impacted. | Monitoring | Unknown | This issue was caused by a TIBCO component issue. | TBD | 2007-05-02 | Stabilization from RBP implementation. This is a known issue. | In investigation - Completion date to be determined - Yellow status/monitoring in progress
April | 2007-04-12 | 2007-04-13 | R-A041307-01 | 11:51AM | 12:01AM |  |  | Paperfree | ERCOT experienced a degradation of retail transaction processing | Human Error | Transaction Processing Error | Delay in transaction processing | Market Notification | Unknown | Scheduled job was interrupted while processing transactions | Training implemented | 2007-04-13 |  | Complete - Green status
April | 2007-04-01 | 3/21/07, 3/30/07 |  | 8:00AM | 4:50PM | 530 | Retail | Retail | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-04-01 |  | Complete - Green status
March | 2007-03-23 | 2007-03-23 | In use starting 4/1/07 | 8:42AM 11:01AM | 9:32AM 11:29AM | 78 | TML | TML | Find ESIID and Find Transaction were not available | TIBCO Application | Outage | Unplanned Outage | Monitoring | Unknown | This issue was caused by a high volume of transactions. Monitors will be created to alert upon the recurrence of this issue. | Backlog was cleared | 2007-03-23 | A SIR (11321) was created for this issue and implemented in April | In implementation - Completion date to be determined - Yellow status/monitoring in progress UPDATE: Complete - Green status
March | 2007-03-21 | 2007-03-22 |  | n/a | n/a |  |  | Siebel | ERCOT experienced high exception counts which caused duplicates due to reprocessing | Siebel Application | Transaction Processing Error | As a result of the reprocessing effort, some Market Participant’s may receive a second 814_05 or 814_25 with a unique transaction id. | Monitoring | Unknown | The failure occurred while processing to Siebel for Service Order updates. ERCOT is continuing to research and identify the root cause. | TBD | TBD | Stabilization from RBP implementation. This is a known issue. | In investigation - Completion date to be determined - Yellow status/monitoring in progress
March | 2007-03-19 | 2007-03-19 |  | 9:00AM | 10:36AM | 96 | MarkeTrak | MarkeTrak | GUI and API not available | MarkeTrak Application | Outage | Unplanned Outage | Monitoring / Market Notification | Unknown | Application services locked-up. | Server and services restarted | 2007-03-19 |  | Complete - Green status
March | 12/10/06 - 3/6/07 | 2007-03-08 |  | n/a | n/a |  |  | TIBCO | 814_18 Delete transactions failing Texas Set Validation in Market Participant systems | TIBCO Application | Transaction Processing Error | Rejects from MPs | Market Notification | Unknown | ERCOT failed to eliminate the TDSP information segment of the 814_18 Delete | ERCOT implemented a code fix for this issue | 2007-03-06 |  | Complete - Green status
March | 2007-03-06 | 2007-03-07 |  | n/a | n/a |  |  | Paperfree | 814_20 transactions being forwarded with errors in the REF segment | Paperfree Application | Transaction Processing Error | Rejects from MPs | Market Notification | Unknown | ERCOT implemented an internal SIR which resulted in a small number of 814_20 transactions being forwarded with errors in the REF segment causing Market Participant’s to respond with a 997 Reject | SIR was backed out | 2007-03-06 |  | Complete - Green status
March | 2007-03-04 | 3/2/07, 3/4/07 |  | 8:00AM | 5:30PM | 570 | Retail | Retail | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-03-04 |  | Complete - Green status
March | 2007-03-04 | 2007-03-05 |  | 7:30PM | 10:30PM |  |  | TML | ERCOT experienced service degradation of the Find ESIID, PI API and ContentProxy / Report Explorer applications on Texas Market Link (TML) | Infrastructure | TML Connectivity | Intermittent accessibility issues | Market Notification | Unknown | Security port issue due to server replacement | Port was opened and applications began to function | 2007-03-04 |  | Complete - Green status
March | 2007-03-02 | 2007-03-02 |  | 8:30AM | 9:45AM | 75 | TML | TML | Find ESIID and Find Transaction were not available | TIBCO Application | Outage | Unplanned Outage | Monitoring | Unknown | This issue was caused by backed up transactions. Monitors will be created to alert upon the recurrence of this issue. | Backlog was cleared | 2007-03-02 | We thought this was a one time occurrence | Complete - Green status
February | 2007-02-26 | 2007-02-26 |  | 9:45AM | 12:15PM |  |  | TML | Intermittent TML and MarkeTrak connectivity issues | Infrastructure | TML Connectivity | Intermittent accessibility issues | Monitoring / Market Notification | Unknown | Domain controller and DNS issues due to planned maintenance | Server replaced | 2007-02-26 |  | Complete - Green status
February | 2007-02-25 | 2/14/07, 2/25/07 |  | 8:00AM | 6:00PM | 600 | Retail | Retail | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-02-25 |  | Complete - Green status
February | 2007-02-23 | 2007-02-23 |  | 11:05AM | 12:15PM | 70 | Retail | TIBCO Database | Inbound and outbound transaction processing halted | Database | Outage | Unplanned Outage | Monitoring | Unknown | Table space issue with the database | Additional storage was allocated to the database | 2007-02-23 | Stabilization from RBP implementation | Complete - Green status
February | 2007-02-18 | 2/8/07, 2/16/07, 2/18/07 |  | 8:00AM | 8:00PM | 720 | Retail | Retail | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-02-18 |  | Complete - Green status
February | 2/10/07 - 2/11/07 | 1/16/07, 1/30/07, 2/9/07, 2/11/07 |  | 2/10 12:00PM | 2/11 5:00PM | 1740 | Retail | Retail | Planned Maintenance Retail Release | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-02-11 |  | Complete - Green status
February | 2007-02-07 | 2007-02-08 |  | 9:15PM | 10:40PM | 85 | Retail | Paperfree | Connectivity issue between application and SAN | Infrastructure | Outage | Unplanned Outage | Monitoring | Unknown | Issue has been escalated to SAN vendor for root cause analysis | ERCOT effort underway | TBD | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
February | 2007-02-07 | 2007-02-07 |  | 11:05AM | 11:55AM | 50 | TML | TML (Report Explorer) | TML - Report Explorer unavailable during normal business hours | TML (report explorer) Application | Outage | Unplanned Outage | Market Notification | Unknown | Connectivity issue across applications | Server and services were restarted | 2007-02-07 | Proactive monitoring and automated recovery is being implemented to correct this issue. | Complete - Green status
February | 2007-02-06 | 2007-02-07 |  | n/a | n/a |  |  | Paperfree | Duplicate transactions (29) | Paperfree Application | Paperfree Duplicate Transactions | Transaction Duplication | Monitoring | Unknown | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
February | 2/5/07, 2/7/07 | 2/7/07, 2/9/07 |  | n/a | n/a |  |  | Siebel | 'DUP' reject transactions (790) sent due to multiple processing of the same transactions | Siebel Application | Siebel Duplicate Transactions | Reject transactions sent in error | Monitoring | Unknown | Siebel processed the same transactions multiple times | Database maintenance to resolve performance issues | 2007-02-11 | The underlying issue was a performance issue in Siebel causing transactions to take longer to process than normal at certain times of the day. This was resolved with database maintenance during a planned maintenance window. | Complete - Green status
February | 2007-02-02 | 2/2/07, 2/5/07 |  | 6:00AM | 9:30AM | 210 | Retail | Siebel | Inbound transaction processing was interrupted following Siebel Batch. | Siebel Application | Outage | Unplanned Outage | Monitoring | Unknown | Siebel workflow locked due to incomplete data entering Siebel. | Database maintenance to resolve performance issues | 2007-02-11 | The overlying issue was a performance issue in Siebel causing transactions to take longer to process than normal at certain times of the day. This was resolved with database maintenance during a planned maintenance window. | Complete - Green status
January | 2007-01-31 | 2007-02-01 |  | n/a | n/a |  |  | Paperfree | Duplicate transactions (32) | Paperfree Application | Paperfree Duplicate Transactions | Transaction Duplication | Monitoring | Unknown | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
January | 1/28/07, 1/29/07 | 2007-01-30 |  | n/a | n/a |  |  | Paperfree | Duplicate transactions (60) | Paperfree Application | Paperfree Duplicate Transactions | Transaction Duplication | Monitoring | Unknown | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
January | 2007-01-25 | 2007-01-25 |  | n/a | n/a |  |  | TIBCO/Siebel | ERCOT has been experiencing periodic failures of some transactions as they process to Siebel in some cases resulting in “OtherPermissionDenied” reject responses | Database | Transaction Processing Errors | Delay in processing until reprocessing is complete (generally same day) | Monitoring | Unknown | Siebel database performance issues | Database maintenance to resolve performance issues | 2007-02-11 | The overlying issue was a performance issue in Siebel causing transactions to take longer to process than normal at certain times of the day. This was resolved with database maintenance during a planned maintenance window. | Complete - Green status
January | 2007-01-24 | 2007-01-24 |  | 12:00PM | 3:00PM | 180 | Retail | NAESB | NAESB was unable to send transactions to Paperfree for processing | NAESB Application | Outage | Unplanned Outage | Monitoring | Unknown | Application frozen | Already included in another project | 2007-01-24 | System rebooted. | Complete - SCR745 Phase 1 would have handled this issue - Implementation 11-27-06 Scheduled completion Feb 16, 2007 - Green status
January | 2007-01-22 | 2007-01-22 |  | 10:06AM | 11:59AM | 112 | Retail | NAESB | The NAESB application locked up and required a reboot. All processing suspended. | NAESB Application | Outage | Unplanned Outage | Monitoring | Unknown | Application frozen | Already included in another project | 2007-01-22 | System rebooted. | Complete - SCR745 Phase 1 would have handled this issue - Implementation 11-27-06 Scheduled completion Feb 16, 2007 - Green status
January | 2007-01-21 | 1/10/07, 1/19/07, 1/21/07 |  | 8:00AM | 1:30PM | 330 | Retail | Retail | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-01-21 |  | Complete - Green status
January | 2007-01-18 | 2007-01-18 |  | 8:00AM | 8:45AM | 45 | TML | TML | Find ESIID and Find Transaction components of TML unavailable | Infrastructure | Outage | Unplanned Outage | Monitoring | Unknown | Server crash caused the disruption of service | Server was restarted | 2007-01-18 |  | Complete - Green status
January | 1/17/07 - 1/19/07 | 1/19/07, 1/23/07 |  | n/a | n/a |  |  | Paperfree | Outbound 814 transaction processing issue impacting subset of transactions | Paperfree Application | Transaction Processing Errors | Delayed processing of a subset of transactions | Monitoring | Unknown | Processing issue within Paperfree where certain file types within a directory were not correctly transferred | All of these transactions have been reprocessed by ERCOT | 2007-01-23 | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
January | 2007-01-14 | 1/12/07, 1/14/07 |  | 8:00AM | 11:30AM | 210 | Retail | Retail | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Unknown | n/a | n/a | 2007-01-14 | This outage was used to implement a portion of the Paperfree solution | Complete - Green status
January | 2007-01-10 | 1/10/07, 2/15/07 |  | n/a | n/a |  |  | TML | Some transactions are not displaying on the Texas Market Link (TML) Find Transactions function. | TML Application | TML Functionality Error | Information not available | Market Notification | Unknown | When the data conversion was done to support the implementation of RBP, a change was made that is causing transactions that were submitted and rejected prior to RBP to not display on TML | A SIR has been written | 2007-02-11 | All accepted pre-RBP orders and all accepted or rejected post-RBP orders are displaying correctly. All service order transactions should be visible. | Complete - Green status
January | 2007-01-09 | 2007-01-09 |  | 2:00PM | 2:17PM | 17 | TML | TML | Failed memory module | Infrastructure | Outage | Unplanned Outage | Monitoring | Unknown | Memory failure | Replaced server memory | 2007-01-09 |  | Complete - Green status
January | 2007-01-08 | 2007-01-08 |  | 5:00PM | 8:15PM | 195 | Retail | Paperfree | Attempted to replace the Paperfree architecture as identified by the on-going Paperfree issues analysis | Infrastructure | Outage | Unplanned Outage | Monitoring | Unknown | Server would not come online | Server backed out and implementation rescheduled | TBD | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
January | 2007-01-05 | 2007-01-05 |  | 3:00AM | 7:30AM | 270 | Retail | Paperfree | Problem pulling data from NAESB | Infrastructure | Outage | Unplanned Outage | Monitoring | Unknown | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | TBD | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
January | 2007-01-05 | 2007-01-05 |  | n/a | n/a |  |  | TML | Intermittent TML and API connectivity issues | TML Application | TML Connectivity | Intermittent accessibility issues | Market Notification | Unknown | Emergency Lodestar database partitioning maintenance | Partitioning completed | 2007-01-05 |  | Complete - Green status
January | 2007-01-03 | 2007-01-04 |  | n/a | n/a |  |  | TIBCO/Siebel | High exception counts | Human Error | Transaction Processing Errors | Delayed processing of a subset of transactions | Monitoring | Unknown | The way in which the TIBCO Siebel Adapter and Siebel Services were restarted caused processing issues | Once the services were restarted transaction processing returned to normal | 2007-01-26 | RBP stabilization | Complete - Green status
January | 2007-01-03 | 2007-01-04 |  | 5:21PM | 7:31PM | 130 | Retail | Paperfree | Memory failure in the clustered environment | Infrastructure | Outage | Unplanned Outage | Monitoring | Unknown | Memory issue caused a portion of the clustered environment to be replaced. The clustered hardware had specific identification required by the cluster software which cause the clustered solution to fail. | The new hardware was correctly setup and transaction processing was able to resume | 2007-01-03 | Veritas clustering software is a new solution being used to implement SCR745. This issue was a result of learning how to work with this software. | Complete - Green status
January | 2007-01-02 | 1/2/07, 1/3/07, 1/4/07 |  | 1/2 3:20PM | 1/3 9:50AM | 750 | Retail | TIBCO Database | TIBCO database indexing issue | Human Error | Outage | Unplanned Outage | Monitoring | Unknown | Indexing failed on the TIBCO database | Index rebuilds were required to resolve the issue | 2007-01-03 | Siebel Batch transactions were delayed on 1/2/07 due to this issue | Complete - Green status

## 2007 Retail Availability
2007 Retail Transaction Processing Service Availability
99.25% Service Availability Target
Month | Service | Gross Available Minutes | Planned Outage Minutes | Net Available Minutes | Unplanned Outage Minutes | Percent Availability
January | Retail Transaction Processing | 44640 | 540 | 44100 | 1637 | 96.29%
February | Retail Transaction Processing | 40320 | 3060 | 37260 | 365 | 99.02%
March | Retail Transaction Processing | 44640 | 570 | 44070 | 0 | 100%
April | Retail Transaction Processing | 43200 | 530 | 42670 | 0 | 100%
May | Retail Transaction Processing | 44640 | 1695 | 42945 | 0 | 100%
Jan - May 2007 | Retail Transaction Processing | 217440 | 6395 | 211045 | 2002 | 99.05%
(to May 31)
99.9% Service Availability Target
Month | Service | Gross Available Minutes | Planned Outage Minutes | Net Available Minutes | Unplanned Outage Minutes | Percent Availability
June | Retail Transaction Processing | 43200 | 3230 | 39970 | 830 | 97.92%
July | Retail Transaction Processing | 44640 | 1735 | 42905 | 375 | 99.13%
August | Retail Transaction Processing | 44640 | 2160 | 42480 | 160 | 99.62%
September | Retail Transaction Processing | 43200 | 5760 | 37440 | 0 | 100%
October | Retail Transaction Processing | 44640 | 720 | 43920 | 312 | 99.29%
November | Retail Transaction Processing | 43200 | 1705 | 41495 | 280 | 99.33%
December | Retail Transaction Processing | 44640 |  | 44640 |  | 0%
Jan - Dec 2007 | Retail Transaction Processing | 480960 | 21705 | 459255 | 3959 | 99.14%
(to Nov 30)

## 2007 MarkeTrak Availability
2007 MarkeTrak Service Availability
98% Service Availability Target
Month | Service | Gross Available Minutes | Planned Outage Minutes | Net Available Minutes | Unplanned Outage Minutes | Percent Availability
January | Retail Transaction Processing | 11880 |  | 11880 |  | 100% | 22
February | Retail Transaction Processing | 10800 |  | 10800 |  | 100% | 20
March | Retail Transaction Processing | 11880 |  | 11880 |  | 100% | 22
April | Retail Transaction Processing | 11340 |  | 11340 |  | 100% | 21
May | Retail Transaction Processing | 12420 |  | 12420 |  | 100% | 23
June | MarkeTrak Service Availability | 15120 | 315 | 14805 | 460 | 96.89% | 21 | 1260
July | MarkeTrak Service Availability | 15840 | 0 | 15840 | 378 | 97.61% | 22 | 1320
August | MarkeTrak Service Availability | 16560 | 0 | 16560 | 0 | 100% | 23 | 1380
September | MarkeTrak Service Availability | 14400 | 0 | 14400 | 559 | 96.12% | 20 | 1200
October | MarkeTrak Service Availability | 16560 | 0 | 16560 | 30 | 99.82% | 23 | 1380
November | MarkeTrak Service Availability | 14400 | 0 | 14400 | 85 | 99.41% | 20 | 1200
December | MarkeTrak Service Availability | 12960 |  | 12960 |  | 0% | 18 | 1080
June - Dec 2007 | MarkeTrak Service Availability | 92880 | 315 | 92565 | 1512 | 98.37%
(to Nov 30)

## 2007 TML Availability
2007 Texas Market Link Service Availability
99% Service Availability Target
Month | Service | Gross Available Minutes | Planned Outage Minutes | Net Available Minutes | Unplanned Outage Minutes | Percent Availability
January | Retail Transaction Processing | 44640 |  | 44640 |  | 100%
February | Retail Transaction Processing | 40320 |  | 40320 |  | 100%
March | Retail Transaction Processing | 44640 |  | 44640 |  | 100%
April | Retail Transaction Processing | 43200 |  | 43200 |  | 100%
May | Retail Transaction Processing | 44640 |  | 44640 |  | 100%
June | TML Service Availability | 43200 | 3230 | 39970 | 730 | 98.17%
July | TML Service Availability | 44640 | 2395 | 42245 | 255 | 99.4%
August | TML Service Availability | 44640 | 2160 | 42480 | 160 | 99.62%
September | TML Service Availability | 43200 | 5760 | 37440 | 0 | 100%
October | TML Service Availability | 44640 | 720 | 43920 | 2917 | 93.36%
November | TML Service Availability | 43200 | 1705 | 41495 | 280 | 99.33%
December | TML Service Availability | 44640 |  | 44640 |  | 0%
June - Dec 2007 | TML Service Availability | 263520 | 15970 | 247550 | 4342 | 98.25%
(to Nov 30)

## 2006 Detailed Incident Data
ERCOT IT Incident Market Notice Summary
July 26, 2006 - December 31, 2006 Incidents
Month | Issue Date | Notification Date | Notification ID | Start Time | End Time | Duration (mins) | SLA Impacted | Application Impacted | Issue Description | Root Cause | Service Impact | Service Impact Detail | Identification Method | Market Impact | Root Cause Details | Resolution | Date (to be) Implemented | Notes | Current Status
December | 2006-12-21 | 2006-12-22 |  | 12/21 5:45PM | 12/22 8:45AM | 540 | Retail | TIBCO | Following an emergency migration to correct the Customer Care process, not all components were reinstated | Human Error | Outage | Unplanned Outage | Monitoring | Cell will contain market participant and end customer impact - if known | An inbound processing component was not turned on | Pulse monitoring has been implemented to alert Operations if transactions are not processing | 2006-12-22 |  | Complete - Green status
December | 2006-12-20 | 12/20/06, 12/29/06, 2/16/07 |  | n/a | n/a |  |  | TML | Entering a phone number while creating customer enrollments/move ins/drops is causing transaction failures | TML Application | TML Functionality Error | TML only 814_03 outbound transaction failure | Monitoring | Cell will contain market participant and end customer impact - if known | The phone number entry is causing the TE segment of the 814_03 to be created but blank causing mapping status rejects | Market Participants have been asked to leave the phone entry field blank until a Priority 1 SIR can be implemented | 2007-02-11 |  | Complete - Green status
December | 12/15/06, 12/16/06, 12/21/06, 12/22/06, 12/23/06, 12/27/06 | 12/18/06, 12/28/06, 12/29/06, 1/2/07, 1/19/07 |  | n/a | n/a |  |  | Paperfree | TX Set validations not occurring on a subset of 867 transactions | Paperfree Application | Transaction Processing Errors | 867s not forwarded, delay in Siebel Service Order completion, delay in reprocessing | Monitoring | Cell will contain market participant and end customer impact - if known | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | TBD | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
December | 2006-12-14 | 2006-12-14 |  | 12:00AM | 8:22AM | 502 | Retail | TIBCO Database | TIBCO database partitioning error | Database | Outage | Unplanned Outage | Monitoring | Cell will contain market participant and end customer impact - if known | Table space on the TIBCO database was consumed | Partitioning rules changed to ensure table space is available | 2006-12-14 | Stabilization from RBP implementation | Complete - Green status
December | 12/14/06 - 12/18/06 | 12/14/06, 12/15/06, 12/18/06 |  | n/a | n/a |  |  | MarkeTrak | API timeout issues | TIBCO Application | MarkeTrak Connectivity | Market Participants utilizing the API are receiving a timeout response | Market Notification | Cell will contain market participant and end customer impact - if known | Processing time for submissions exceeded due to bad data handling | Additional exception handling added to the API functionality | 2006-12-18 |  | Complete - Green status
December | 2006-12-11 | 12/11/06, 12/12/06, 12/13/06 |  | n/a | n/a |  |  | TML/API | Intermittent TML and API connectivity issues | TML Application | TML Connectivity | Intermittent accessibility issues | Market Notification | Cell will contain market participant and end customer impact - if known | Memory allocation issue due to a process not closing connections properly | Process was modified and monitored | 2006-12-13 |  | Complete - Green status
December | 2006-12-08 | 11/14/06, 11/28/06, 11/29/06, 12/7/06, 12/10/06 |  | 12/8 7:00AM | 12/9 10:10PM | 2350 | Retail | Retail | Planned Maintenance Retail Release | n/a | n/a | Planned Outage | Planned Maintenance | Cell will contain market participant and end customer impact - if known | n/a | n/a | 2006-12-08 | Implementation of Retail Business Processes - PR50121, PR50025, PR40007, PR50030, PR50059, PR50060 | Complete - Implementation of RBP - Green status
December | 2006-12-05 | 2006-12-05 |  | 1:10PM | 1:47PM | 37 | Retail | NAESB | The NAESB application locked up and required a reboot. All processing suspended. | NAESB Application | Outage | Unplanned Outage | Monitoring | Cell will contain market participant and end customer impact - if known | Application frozen | Already included in another project | 2006-12-05 | System rebooted. | Complete - SCR745 Phase 1 would have handled this issue - Implementation 11-27-06 Scheduled completion Feb 16, 2007 - Green status
December | 2006-12-04 | 2006-12-04 |  | 7:00PM | 9:00PM | 120 | TML | TML (Report Explorer) | ERCOT TML Report Explorer unavailable and Lodestar Batch Extracts delivered late | n/a | n/a | Planned Outage | Planned Maintenance | Cell will contain market participant and end customer impact - if known | n/a | n/a | 2006-12-04 | Pre-migration activities to prepare for the RBP release on 12/8/06 | Complete - Green status
November | 2006-11-13 | 11/13/06, 11/14/06 |  | n/a | n/a |  |  | MarkeTrak | The MarkeTrak system was successfully implemented yesterday, November 13th. Throughout the day, ERCOT Identified four recurring issues Market Participants experienced with MarkeTrak | MarkeTrak Application | MarkeTrak Connectivity | Intermittent accessibility issues | Market Notification | Cell will contain market participant and end customer impact - if known | Stabilization | Configuration changes and additional user training | 2006-11-14 | Configuration, market user setups, etc were part of stabilization the day of market go-live. | Complete - Green status
November | 2006-11-11 | 10/30/06, 11/11/06 |  | 12:00PM | 10:49PM | 649 | Retail | Retail | Planned Maintenance Retail Release | n/a | n/a | Planned Outage | Planned Maintenance | Cell will contain market participant and end customer impact - if known | n/a | n/a | n/a | SCR745 Phase 2 - Paperfree implementation - PR60006 | Complete - Green status
November | 2006-11-09 | N/A (See Service Impact) |  | 12:34PM | 1:17PM |  |  | Siebel | SBMI, SBMO, SBSW transaction duplication | Siebel Application | Siebel Duplicate Transactions | Transaction ID Duplication (Transactions were caught prior to being sent to the market - no notification required) | Monitoring | Cell will contain market participant and end customer impact - if known | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP, Temporary fix implemented in October | Complete - Green status
October | 2006-10-17 | 2006-10-17 |  | 10:39AM | 10:57AM | 18 | Retail | NAESB | The NAESB application locked up and required a reboot. All processing suspended. | NAESB Application | Outage | Unplanned Outage | Monitoring | Cell will contain market participant and end customer impact - if known | Application frozen | Already included in another project | 2006-10-17 | System rebooted. | Complete - SCR745 Phase 1 would have handled this issue - Implementation 11-27-06 Scheduled completion Feb 16, 2007 - Green status
October | 2006-10-15 | 10/4/06, 10/9/06, 10/13/06 |  | 8:00AM | 8:00PM | 720 | Retail | Retail | Planned Maintenance Outage | n/a | n/a | Planned Outage | Planned Maintenance | Cell will contain market participant and end customer impact - if known | n/a | n/a | n/a |  | Complete - Green status
October | 2016-10-14 | 2006-10-16 |  | 10/14 7:40AM | 10/15 7:10AM |  |  | Paperfree | Outbound processing of 814 and 824 transactions suspended | Paperfree Application | Slow System Performance | Degradation | Manual Troubleshooting | Cell will contain market participant and end customer impact - if known | Process hung | Already included in another project | 2006-10-15 | Process restarted. | Complete - SCR745 Phase 2 - implementation 11-11-06 - Green status
October | 2006-10-11 | 2006-10-11 |  | 5:08PM | 6:10PM | 62 | Retail | Retail | Critical memory issue on a Retail Database Server | Infrastructure | Outage | Unplanned Outage | Monitoring | Cell will contain market participant and end customer impact - if known | Hardware failure | Already included in another project | 2006-10-11 | Conversion to the IBM P series server will allow for hot swap capabilities for this type of issue. | Complete - Green status
October | 2006-10-05 | 2006-10-05 14:49 |  | 12:36AM | 12:42AM |  |  | Siebel | SBMI, SBMO, SBSW transaction duplication | Siebel Application | Siebel Duplicate Transactions | Transaction ID Duplication | Monitoring | Cell will contain market participant and end customer impact - if known | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP, Temporary fix implemented in October | Complete - Green status
October | 2006-10-02 | 2006-10-03 |  | 7:46PM | 7:56PM | 18 | Retail | Paperfree | Paperfree File Server network outage | Infrastructure | Outage | Unplanned Outage | Monitoring | Cell will contain market participant and end customer impact - if known | Hardware failure | ERCOT effort underway | 2006-10-03 | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
September | 2006-09-26 | 2006-09-29 |  | 12:02AM | 4:04PM |  |  | Paperfree | 997s not sent during outages | Paperfree Application | Transaction Processing Errors | Transaction Processing Errors | Market Notification / Daily Report | Cell will contain market participant and end customer impact - if known | TBD | Not already included in another project | n/a | Result of Paperfree outage | Complete - SCR745 Phase 2 - implementation 11-11-06 - Green status
September | 2006-09-25 | 2006-09-25 |  | 1:58AM | 3:47PM | 829 | Retail | Paperfree | Paperfree File Server not responding | Infrastructure | Outage | Unplanned Outage | Market Notification / Monitoring | Cell will contain market participant and end customer impact - if known | NIC driver error | ERCOT effort underway | 2006-09-25 | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
September | 2006-09-25 | 2006-09-29 |  | 1:58AM | 3:47PM |  |  | Paperfree | 997s not sent during outages | Paperfree Application | Transaction Processing Errors | Transaction Processing Errors | Market Notification / Daily Report | Cell will contain market participant and end customer impact - if known | TBD | Not already included in another project | n/a | Result of Paperfree outage | Complete - SCR745 Phase 2 - implementation 11-11-06 - Green status
September | 9/22/06 - 9/26/06 | 9/22/06 - 9/27/06 |  | n/a | n/a |  |  | Paperfree | 814 and 867 transactions duplicated | Paperfree Application | Paperfree Duplicate Transactions | Transaction Duplication | Monitoring | Cell will contain market participant and end customer impact - if known | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress
September | 2006-09-20 | 2006-09-20 |  | n/a | n/a |  |  | TML API | Market Participants receiving the “No ESI ID found” message when using the API and to research | TML Application | TML Functionality Error | Information not available | Market Notification | Cell will contain market participant and end customer impact - if known | Code issue | Already included in another project | 2006-09-28 |  | Complete - Green status
September | 2006-09-21 | 2006-09-21 |  | ~2:00AM | ~4:00AM |  |  | Siebel | Siebel Batch continued following SBMI issue with future dated evaluation date | Siebel Application | Transaction Processing Errors | Order Cancellations | Market Notification | Cell will contain market participant and end customer impact - if known | Incorrect date used | One time occurrence | 2006-09-21 | Process change and Training implemented | Complete - Green status
September | 2006-09-21 | 2006-09-21 |  | 12:55AM | 1:03AM |  |  | Siebel | SBMI, SBMO, SBSW transaction duplication | Siebel Application | Siebel Duplicate Transactions | Transaction ID Duplication | Monitoring | Cell will contain market participant and end customer impact - if known | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
September | 2006-09-19 | 2006-09-19 |  | n/a | n/a |  |  | Paperfree | Annual Validation backlog of 814_20 Maintains | Paperfree Application | Slow System Performance | Backlog | Market Coordination / Monitoring | Cell will contain market participant and end customer impact - if known | Annual Validation and system limitations | Annual occurrence | n/a | current backlog is ~300K | Complete for 2006 - Green status - long term fix to be implemented in Feb 07
September | 2006-09-11 | 2006-09-11 |  | 12:46AM | 12:49AM |  |  | Siebel | SBMI, SBMO, SBSW transaction duplication | Siebel Application | Siebel Duplicate Transactions | Transaction ID Duplication | Monitoring | Cell will contain market participant and end customer impact - if known | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
September | 8/15/06 - 9/8/06 | 2006-09-08 |  | n/a | n/a |  |  | Siebel | ESIID address deleted from database | Siebel Application | Transaction Processing Errors | Rejected Transactions | Exception Processing | Cell will contain market participant and end customer impact - if known | Software Bug | Already included in another project | n/a | Implementation date to be determined | Complete - Green status
August | 2006-08-30 | 2006-08-31 |  | 9:17PM | 9:28PM |  |  | Siebel | SBMI, SBMO, SBSW transaction duplication | Siebel Application | Siebel Duplicate Transactions | Transaction ID Duplication | Monitoring | Cell will contain market participant and end customer impact - if known | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
August | 2006-08-02 | 2006-08-02 |  | 1:10AM | 1:13AM |  |  | Siebel | SBMI, SBMO, SBSW transaction duplication | Siebel Application | Siebel Duplicate Transactions | Transaction ID Duplication | Monitoring | Cell will contain market participant and end customer impact - if known | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
July | 2006-07-27 | 2006-07-27 |  | 1:00AM | 9:30AM |  |  | Paperfree | 814 and 867 transactions duplicated | Paperfree Application | Paperfree Duplicate Transactions | Transaction Duplication | Monitoring | Cell will contain market participant and end customer impact - if known | ERCOT has identified a communication protocol issue between Paperfree servers | ERCOT effort underway | n/a | ERCOT solution in the process of being implemented as discussed in the Jan '07 RMS Retail Transaction Processing presentation | In implementation - Completion date to be determined - Yellow status/monitoring in progress

## 2006 Retail Availability
2006 Retail Transaction Processing Service Availability
Month | Service | Gross Available Minutes | Planned Outage Minutes | Net Available Minutes | Unplanned Outage Minutes | Percent Availability
January | Retail Transaction Processing | 44640 | 1620 | 43020 | 105 | 99.76%
February | Retail Transaction Processing | 40320 | 990 | 39330 | 556 | 98.59%
March | Retail Transaction Processing | 44640 | 960 | 43680 | 0 | 100%
April | Retail Transaction Processing | 43200 | 715 | 42485 | 0 | 100%
May | Retail Transaction Processing | 44640 | 3255 | 41385 | 402 | 99.03%
June | Retail Transaction Processing | 43200 | 0 | 43200 | 0 | 100%
July | Retail Transaction Processing | 44640 | 390 | 44250 | 304 | 99.31%
August | Retail Transaction Processing | 44640 | 885 | 43755 | 0 | 100%
September | Retail Transaction Processing | 43200 | 0 | 43200 | 1071 | 97.52%
October | Retail Transaction Processing | 44640 | 720 | 43920 | 183 | 99.58%
November | Retail Transaction Processing | 43200 | 569 | 42631 | 0 | 100%
December | Retail Transaction Processing | 44640 | 3790 | 40850 | 1079 | 97.36%
Year to Date | Retail Transaction Processing | 525600 | 13894 | 511706 | 3700 | 99.27%
(to Dec. 31)