## SCR760 Summary
Revised Cost Benefit Analysis Summary
Request Information
PRR / SCR / PR / "New": | SCR760 |  |  | Estimator's Name: |  | ERCOT and TSPs
Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models |  |  | Sponsor's Name: |  | SSWG
|  |  |  | Estimate Date: |  | 2011-03-09
Project Description: | Implement and support nine (9) system changes that update the NMMS Database and/or the tools used to create the Annual Planning Model to support additional features required by the Transmission Service Provider Planning teams in an effort to more efficiently and accurately build the Annual Planning Models.
Benefits and Impacts
1 - Leverages existing TSP databases containing previously-vetted planning data to create future cases.
2 - Eliminates the need for the creation and on-going maintenance of approximately 4000 Standard Planning Model Change Requests (PMCR) as the required data will be applied directly to the Network Model through the one-time standard NOMCR process.
3 - Benefits for both ERCOT and TSPs primarily result from savings in labor costs associated with the creation, submittal and review of the Standard Planning Model Change Requests.
4 - The Planning Models will support the improvements being made to the load flow software being used by the ERCOT staff, ERCOT stakeholders, and the majority of the TSPs, which will improve the planning analysis being performed and keep ERCOT up to date with the analysis capability of the rest of the utility industry. ERCOT and the majority of TSPs currently upgrade to new PSS/E releases annually in accordance with good utility practice.
5 - Reduces the risk of errors due to the necessity to submit and review Standard Planning Model Changes Requests every time planning cases are built and updated, up to 10 times per year.
6 - Increases the consistency of the CRR and Annual Planning Models since SCR760 items will now be modeled in the CRR model.
Feasibility
Alternatives (Considered and Rejected)
1 - This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 - ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 - ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Assumptions are detailed on the itemized worksheets
Notes
1 - Year 0 Implementation Costs are different in the Cost Benefit Analysis from those shown in the Impact Analysis because the Cost Benefit Analysis assumes that 760-1 through 760-9 are approved and planned for implementation. It combines the implementation of 760-1 with 760-6 using an assumption that the cost to establish the process and setup the environment, as described in 760-1 plus implementation of FACTS devices and fixed shunts, as described in 760-6, are proposed for Year 0 implementation. The Impact Analysis assumes that an undefined number of new, yet to be defined, devices will be implemented. The uncertain nature of this causes the Implementation costs for 760-1, on its own, to be higher. This higher cost is shown in the Year 2 implementation cost where the number and types of new devices that will be implemented is yet to be defined. If the assumptions were the same as those for the Impact Analysis, Year 0 Implementation costs would be approximately $2.2M in the Cost Benefit Analysis compared with the estimate of $1.9M - $2.4M in the Impact Analysis.
2 - Year 1 through Year 3 Model Maintenance costs are different in the Cost Benefit Analysis from those shown in the Impact Analysis because the Cost Benefit Analysis assumes that 760-1 through 760-9 are approved and planned for implementation. It assumes that the Year 0 mplementation of 760-1 is the implementation of 760-6 so does not double-count the Additional Model Maintenance costs associated with each item. The Impact Analysis costs both 760-1 and 760-6 independently and shows the Additional Model Maintenance costs associated with the implementation of each assuming that only one or the other is implemented. If the assumptions were the same as those for the Impact Analysis, ERCOT Ongoing Costs over Years 1, 2 and 3 would be approximately $1M adjusted for NPV in the Cost Benefit Analysis compared with the estimate of $1M - 1.3M in the Impact Analysis.
Cost and Benefit Summary
Project Costs | ERCOT Implementation Cost | 1700000 |  |  |  |  | All values in this section are rounded to 2 significant digits
| Market Implementation Cost | 0
| Total Implementation Cost |  | 1700000 |  |  | *See Note 1
| ERCOT Ongoing Cost | 970000
| Market Ongoing Cost | 0
| Total Ongoing Cost |  | 970000 |  |  | *See Note 2
[5 empty] | 2700000 |  | Total Cost
Project Benefit | ERCOT Benefit | 950000
| Market Benefit | 2400000
[5 empty] | 3400000 |  | Total Benefit
|  | Net (Cost) - Benefit |  |  | 700000
Calculation Parameters
Market Cost | Impacted Number of QSEs |  |  | 0
| Impacted Number of CRs |  |  | #REF!
| Impacted Number of TDSPs |  |  | #REF!
| Impacted Number of Resources |  |  | #REF!
Present Value Interest Rate: |  |  |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows

## SCR760 Detail
Cost Benefit Analysis Data Entry Worksheet
PRR / SCR / Etc.: | SCR760 | Project Title: | Recommended Changes Needed for Information Model Manager and Topology Processor for Planning Models
Sponsor: | SSWG | Estimate Date: | 2011-03-09 | Estimator: | ERCOT and TSPs
Project Description: (please be clear and concise) | Implement and support nine (9) system changes that update the NMMS Database and/or the tools used to create the Annual Planning Model to support additional features required by the Transmission Service Provider Planning teams in an effort to more efficiently and accurately build the Annual Planning Models.
Benefits and Impacts
Click here for ideas on benefit and impact areas… ---------------------------------------------------------------------------------->>>
1 | Leverages existing TSP databases containing previously-vetted planning data to create future cases.
2 | Eliminates the need for the creation and on-going maintenance of approximately 4000 Standard Planning Model Change Requests (PMCR) as the required data will be applied directly to the Network Model through the one-time standard NOMCR process.
3 | Benefits for both ERCOT and TSPs primarily result from savings in labor costs associated with the creation, submittal and review of the Standard Planning Model Change Requests.
4 | The Planning Models will support the improvements being made to the load flow software being used by the ERCOT staff, ERCOT stakeholders, and the majority of the TSPs, which will improve the planning analysis being performed and keep ERCOT up to date with the analysis capability of the rest of the utility industry. ERCOT and the majority of TSPs currently upgrade to new PSS/E releases annually in accordance with good utility practice.
5 | Reduces the risk of errors due to the necessity to submit and review Standard Planning Model Changes Requests every time planning cases are built and updated, up to 10 times per year.
6 | Increases the consistency of the CRR and Annual Planning Models since SCR760 items will now be modeled in the CRR model.
Feasibility
Click here for ideas on feasibility… ---------------------------------------------------------------------------------->>>
Dependencies
Other 1
Other 2
Other 3
Alternatives (Considered and Rejected)
Click here for ideas on alternatives… ---------------------------------------------------------------------------------->>>
1 | This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 | ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 | ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Assumptions are detailed on the itemized worksheets
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
Notes
1 | Year 0 Implementation Costs are different in the Cost Benefit Analysis from those shown in the Impact Analysis because the Cost Benefit Analysis assumes that 760-1 through 760-9 are approved and planned for implementation. It combines the implementation of 760-1 with 760-6 using an assumption that the cost to establish the process and setup the environment, as described in 760-1 plus implementation of FACTS devices and fixed shunts, as described in 760-6, are proposed for Year 0 implementation. The Impact Analysis assumes that an undefined number of new, yet to be defined, devices will be implemented. The uncertain nature of this causes the Implementation costs for 760-1, on its own, to be higher. This higher cost is shown in the Year 2 implementation cost where the number and types of new devices that will be implemented is yet to be defined. If the assumptions were the same as those for the Impact Analysis, Year 0 Implementation costs would be approximately $2.2M in the Cost Benefit Analysis compared with the estimate of $1.9M - $2.4M in the Impact Analysis.
2 | Year 1 through Year 3 Model Maintenance costs are different in the Cost Benefit Analysis from those shown in the Impact Analysis because the Cost Benefit Analysis assumes that 760-1 through 760-9 are approved and planned for implementation. It assumes that the Year 0 mplementation of 760-1 is the implementation of 760-6 so does not double-count the Additional Model Maintenance costs associated with each item. The Impact Analysis costs both 760-1 and 760-6 independently and shows the Additional Model Maintenance costs associated with the implementation of each assuming that only one or the other is implemented. If the assumptions were the same as those for the Impact Analysis, ERCOT Ongoing Costs over Years 1, 2 and 3 would be approximately $1M adjusted for NPV in the Cost Benefit Analysis compared with the estimate of $1M - 1.3M in the Impact Analysis.
ERCOT Cost and Benefit Detail
ERCOT Internal Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Project | 1722500 | 0 | 0 | 0 | *See Note 1 | NPV = | 0
Ongoing Cost | Additional Model Maintenance | 0 | 245000 | 245000 | 245000 | *See Note 2 | NPV = | 654887.9276
| Additional Costs for PSS/E upgrade project biennually | 0 | 0 | 350000 | 0 |  | NPV = | 311498.754
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Present Value of Internal ERCOT Cost: | 2700000
ERCOT Internal Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Direct Cost Savings | Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
Productivity Increases | Staffing | 256945 | 259142 | 259142 | 259142 |  | NPV = | 692689.6626
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Present Value of Internal ERCOT Benefit: | 950000
Market Cost and Benefit Detail
Market Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Select type… | [5 empty] | NPV = | 0
Ongoing Cost | Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Present Value of Market Cost: | 0
Market Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Benefits for Market | Staffing | 658833.3333 | 664466.6667 | 664466.6667 | 664466.6667 |  | NPV = | 1776127.34
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Total Present Value of Market Benefit: | 2400000
Total Cost | 2700000 |  | Net (Cost) - Benefit ($) |  | 700000
Total Benefit | 3400000 |  | Cost Benefit Ratio |  | 1.2593
Summary values are rounded to 2 significant digits.
Additional Comments
Enter any additional comments here…
1 | The number of Planning Models could increase. The ERCOT stakeholders and the Planning Working Group have discussed the need for additional models, such as a 10-year model or high wind model. Each additional model will increase the costs by $100,000 based on the TSPs assumptions.
2 | Because the process of developing the Planning Models has not actually begun, the TSPs are continuing to determine if there is a need for additional standard PMCRs, which could increase the costs further.
3 | With new versions of PSS/E load flow software, there could be costs for additional Standard PMCRs.
4 | Several TSPs have not participated in the Cost-Benefit analysis; therefore, those benefits are not included in the estimates.
5 | New market entrants do not know the impact; therefore, their costs cannot be quantified at this point.
6 | New Topology Processor downloads will be used twice a year, once for Data Set A and once for Data Set B. If Market Participants want the Transmission Information and Tracking (“TPIT”) quarterly updates to be built from new topology processor downloads, then the costs will increase.
Benefit and Impact Prompts
GOVERNANCE: Is the project required to support a PUCT rulemaking or government requirement?
GOVERNANCE: Is the project required by a market or ERCOT committee?
GOVERNANCE: Will the project provide better information for management decision making?
RELIABILITY: Does the project improve the reliability of the grid?
RELIABILITY: Does the project improve the reliability of ERCOT's computing infrastructure?
RELIABILITY: Is there a significant operational need for the project?
SAFETY: Will the project enhance safety within ERCOT?
SECURITY: Is there a physical or cyber-security issue that is addressed by this effort?
SECURITY: Does the project address an audit finding?
SECURITY: Will the project decrease the chance of fraud or help protect sensitive data?
RISK REDUCTION: Does this reduce risk to ERCOT in some significant manner?
RESOURCES: Does the project reduce the number of resources needed to support current operations?
RESOURCES: Does the project deliver infrastructure components that are more efficient or more easily upgraded?
DATA MANAGEMENT: Does this improve the accuracy, timeliness and transparency of transactions or settlements?
DATA MANAGEMENT: Does this enhance or optimize our data storage capability?
DATA MANAGEMENT: Does this improve reporting capabilities (financial, operational, etc.)?
EFFICIENCY: Does the project improve the efficiency or effectiveness of ERCOT?
EFFICIENCY: Does the project automate, improve or streamline a necessary function?
INVESTMENT: Is the project an investment in new capability or does it support the current architecture?
OTHER: Are there other areas that will indirectly benefit from this project?
Feasibility Prompts
REQUIREMENTS: Are high level requirements clearly defined?
REQUIREMENTS: How complex are the potential solutions?
REQUIREMENTS: Does a required completion date make delivery more difficult?
DELIVERY: Can the project be broken down into smaller sections or delivered in stages to reduce risk?
DELIVERY: Will training be required as the project is rolled out?
DEPENDENCIES: Are there major dependencies on other projects that make this difficult to implement?
Alternative Prompts
DELIVERY: Is a manual workaround an option (short-term or long-term)?
DELIVERY: Does a partial implementation provide enough value to be worth considering?
DELIVERY: Should a phased implementation be considered to reduce risk or accelerate key benefits?
DELIVERY: If this is an automation project is it reasonable to consider using the current process?
Assumption Prompts
DEPENDENCIES: Is this request is dependent on another ERCOT project (either active or planned)?
DELIVERABLES: Are specific key deliverables required from this project?
DELIVERABLES: What is the useful life of the deliverables of this project?
RESOURCES: Are computing resources assumed that are not to be delivered by this project?
RESOURCES: Are specific key resources assumed to be available for this project?
RESOURCES: Are there facilities requirements necessary for this project?
REQUIREMENTS: Is completion required by a specific date?

## SCR760-2, -4, -5, -9 Summary
Cost Benefit Analysis Summary
Request Information
PRR / SCR / PR / "New": | SCR760-2, -4, -5, -9 |  |  | Estimator's Name: |  | ERCOT and TSPs
Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models |  |  | Sponsor's Name: |  | SSWG
|  |  |  | Estimate Date: |  | 2011-03-09
Project Description: | (2) Represent Distribution Capacitor Banks on the proper bus in Topology Processor PSS/E case. Provide Capacitor Bank parameters necessary for PSS/E (MVAR, ID, fixed/switch shunt, number of blocks). Allow for multiple capacitor banks on the same bus. In Information Model Manager, define new Class called DistributionCapBank and create it in a new directory outside of the substations (similar to TransformerKluges). Then have a new link in a Class, such as the BusbarSection, that can be associated with the DistributionCapBank. (4) Planning should be able to model loads and capacitor banks on the correct PSS/E busses. In Information Model Manager, create a new attribute that would enable the user to select the PSS/E bus where the capacitor bank should appear in the Topology Processor case. (5) Represent the actual transformer models in the PSS/E cases. The planning transformer model is an appropriate model for the transformer to ensure stakeholders the power flow results will be accurate. Additional data attributes such as the number of taps, location of tapped winding, maximum and minimum tap ratios. In Information Model Manager, store Planning transformer data in a separate file (or in a new Class outside of the ERCOT Texas Network directory similar to Transformer Kluges). The Topology Processor will select the Planning transformer data to generate the Topology Processor PSS/E case. Necessary data includes number of taps, location of tapped winding, maximum and minimum tap ratios, and specifying the voltage control bus. (9) Represent multisection line groupings properly in TP PSSE cases Allow capability to mark unique Line Id. Show “&X” line identifier properly in the TP data records. In Information Model Manager, define new Class called MultisectionLineGroup and create it in a new directory outside of the substations (similar to TransformerKluges). MultisectionLineGroup attributes will include string “Line Id” and Boolean “Metered”. Then add a new link in the ACLineSegment objects that can be associated with a MultisectionLineGroup. An ACLineSegment cannot be linked to more than one MultisectionLineGroup.
Benefits and Impacts
Feasibility
Alternatives (Considered and Rejected)
1 - This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 - ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 - ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Joint ERCOT & Market Assumptions
1 - The cost to identify equipment needing NOMCR following the implementation of these changes is equal to the cost to identify the equipment needing a standard PMCR prior to implementation of these changes resulting in no cost/benefit.
2 - The cost to create NOMCR following the implementation of these changes is equal to the cost to create PMCR prior to implementation of these changes resulting in no cost/benefit.
3 - The Topology Processor case is a one-time download before work begins on a new data set case build process. There will be a minimum of two downloads of the Topology Processor data each year (Data Set A and Data Set B).
4 - Costs from the Preliminary Impact Analysis (IA) have been used in the Cost portions of this document based on the mid-point of the range in the Prelimiary IA.
5 - The Cost-Benefit Analysis considers costs and benefits over a four-year time period because 4 years is generally the depreciation life of software projects from a capital point of view. Since this project will be capitalized, from an accounting perspective , its economic life will end at 4 years and there is likely to be no salvage value. The useful life could be much longer than the economic life. It is very possible that four years from now, a completely different solution will make the SCR760 effort obsolete. But then there is chance that our SCR760 solution will continue to work. Because of this unknown, software projects have a standard life of 4 years. However, it is understood that the operation and maintenance costs outlined as ERCOT and Market Benefits will not end in four years given that conditions causing the need for SCR760 remain the same.
6 - Costs and Benefits in Years 1 through 3 have not been escalated for inflation.
7 - Staffing Productivity Benefit is calculated as follows: (#standard PMCRs/# PMCRs per hour * hourly rate) * # case building and/or case updating periods per year
8 - The maximum number of records that can be eliminated as a result of the implementation of these changes is (#2=628, #4=442, #5=665, #9=232) one thousand eight hundred and eighty-three (1967).
Additional ERCOT Assumptions
1 - ERCOT is responsible for reviewing and accepting standard PMCRs submitted by TSPs.
2 - ERCOT is responsible for reviewing and validating NOMCRs
3 - Benefit is derived from one time entry for NOMCR versus review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
4 - The benefit is measured as the annual time saved because there are fewer PMCRs to review during each case building and/or case updating period following the implementation of these changes.
5 - ERCOT uses a blended rate of $65/hour for internal labor for all project estimates.
6 - On average, ten (10) standard PMCRs can be reviewed and accepted per hour.
Additional TSP Assumptions
1 - TSPs are responsible for the creation, review and maintenance of standard PMCRs.
2 - TSPs are responsible for the creation and submittal of NOMCRs
3 - All standard PMCRs will be built from scratch and reviewed for each model each time there is a Topology Processor download and reviewed for quarterly updates to avoid data errors.
4 - Benefit is derived from one time entry for NOMCR versus creation and review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
5 - Experienced transmission planners must be responsible for creating standard PMCRs. The hourly rate of $100 reflects the fully loaded cost of such an employee.
6 - On average, six (6) standard PMCRs can be created and submitted per hour.
Cost and Benefit Summary
Project Costs | ERCOT Implementation Cost | 760000 |  |  |  |  | All values in this section are rounded to 2 significant digits
| Market Implementation Cost | 0
| Total Implementation Cost |  | 760000
| ERCOT Ongoing Cost | 290000
| Market Ongoing Cost | 0
| Total Ongoing Cost |  | 290000
[5 empty] | 1100000 |  | Total Cost
Project Benefit | ERCOT Benefit | 470000
| Market Benefit | 1200000
[5 empty] | 1700000 |  | Total Benefit
|  | Net (Cost) - Benefit |  |  | 600000
Calculation Parameters
Market Cost | Impacted Number of QSEs |  |  | 0
| Impacted Number of CRs |  |  | #REF!
| Impacted Number of TDSPs |  |  | #REF!
| Impacted Number of Resources |  |  | #REF!
Present Value Interest Rate: |  |  |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows

## SCR760-2, -4, -5, -9 Detail
Cost Benefit Analysis Data Entry Worksheet
NPRR / SCR / Etc.: | SCR760-2, -4, -5, -9 | Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models
Sponsor: | SSWG | Estimate Date: | 2011-03-09 | Estimator: | ERCOT and TSPs
Project Description: (please be clear and concise) | (2) Represent Distribution Capacitor Banks on the proper bus in Topology Processor PSS/E case. Provide Capacitor Bank parameters necessary for PSS/E (MVAR, ID, fixed/switch shunt, number of blocks). Allow for multiple capacitor banks on the same bus. In Information Model Manager, define new Class called DistributionCapBank and create it in a new directory outside of the substations (similar to TransformerKluges). Then have a new link in a Class, such as the BusbarSection, that can be associated with the DistributionCapBank. (4) Planning should be able to model loads and capacitor banks on the correct PSS/E busses. In Information Model Manager, create a new attribute that would enable the user to select the PSS/E bus where the capacitor bank should appear in the Topology Processor case. (5) Represent the actual transformer models in the PSS/E cases. The planning transformer model is an appropriate model for the transformer to ensure stakeholders the power flow results will be accurate. Additional data attributes such as the number of taps, location of tapped winding, maximum and minimum tap ratios. In Information Model Manager, store Planning transformer data in a separate file (or in a new Class outside of the ERCOT Texas Network directory similar to Transformer Kluges). The Topology Processor will select the Planning transformer data to generate the Topology Processor PSS/E case. Necessary data includes number of taps, location of tapped winding, maximum and minimum tap ratios, and specifying the voltage control bus. (9) Represent multisection line groupings properly in TP PSSE cases Allow capability to mark unique Line Id. Show “&X” line identifier properly in the TP data records. In Information Model Manager, define new Class called MultisectionLineGroup and create it in a new directory outside of the substations (similar to TransformerKluges). MultisectionLineGroup attributes will include string “Line Id” and Boolean “Metered”. Then add a new link in the ACLineSegment objects that can be associated with a MultisectionLineGroup. An ACLineSegment cannot be linked to more than one MultisectionLineGroup.
Benefits and Impacts
Click here for ideas on benefit and impact areas… ---------------------------------------------------------------------------------->>>
1
2
3
5
6
7
8
Feasibility
Click here for ideas on feasibility… ---------------------------------------------------------------------------------->>>
Dependencies
Other 1
Other 2
Other 3
Alternatives (Considered and Rejected)
Click here for ideas on alternatives… ---------------------------------------------------------------------------------->>>
1 | This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 | ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 | ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Joint ERCOT & Market Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | The cost to identify equipment needing NOMCR following the implementation of these changes is equal to the cost to identify the equipment needing a standard PMCR prior to implementation of these changes resulting in no cost/benefit.
2 | The cost to create NOMCR following the implementation of these changes is equal to the cost to create PMCR prior to implementation of these changes resulting in no cost/benefit.
3 | The Topology Processor case is a one-time download before work begins on a new data set case build process. There will be a minimum of two downloads of the Topology Processor data each year (Data Set A and Data Set B).
4 | Costs from the Preliminary Impact Analysis (IA) have been used in the Cost portions of this document based on the mid-point of the range in the Prelimiary IA.
5 | The Cost-Benefit Analysis considers costs and benefits over a four-year time period because 4 years is generally the depreciation life of software projects from a capital point of view. Since this project will be capitalized, from an accounting perspective , its economic life will end at 4 years and there is likely to be no salvage value. The useful life could be much longer than the economic life. It is very possible that four years from now, a completely different solution will make the SCR760 effort obsolete. But then there is chance that our SCR760 solution will continue to work. Because of this unknown, software projects have a standard life of 4 years. However, it is understood that the operation and maintenance costs outlined as ERCOT and Market Benefits will not end in four years given that conditions causing the need for SCR760 remain the same.
6 | Costs and Benefits in Years 1 through 3 have not been escalated for inflation.
7 | Staffing Productivity Benefit is calculated as follows: (#standard PMCRs/# PMCRs per hour * hourly rate) * # case building and/or case updating periods per year
8 | The maximum number of records that can be eliminated as a result of the implementation of these changes is (#2=628, #4=442, #5=665, #9=232) one thousand eight hundred and eighty-three (1967).
Additional ERCOT Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | ERCOT is responsible for reviewing and accepting standard PMCRs submitted by TSPs.
2 | ERCOT is responsible for reviewing and validating NOMCRs
3 | Benefit is derived from one time entry for NOMCR versus review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
4 | The benefit is measured as the annual time saved because there are fewer PMCRs to review during each case building and/or case updating period following the implementation of these changes.
5 | ERCOT uses a blended rate of $65/hour for internal labor for all project estimates.
6 | On average, ten (10) standard PMCRs can be reviewed and accepted per hour.
Additional TSP Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | TSPs are responsible for the creation, review and maintenance of standard PMCRs.
2 | TSPs are responsible for the creation and submittal of NOMCRs
3 | All standard PMCRs will be built from scratch and reviewed for each model each time there is a Topology Processor download and reviewed for quarterly updates to avoid data errors.
4 | Benefit is derived from one time entry for NOMCR versus creation and review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
5 | Experienced transmission planners must be responsible for creating standard PMCRs. The hourly rate of $100 reflects the fully loaded cost of such an employee.
6 | On average, six (6) standard PMCRs can be created and submitted per hour.
ERCOT Cost and Benefit Detail
ERCOT Internal Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Project | 757500 | 0 | 0 | 0 | NPV = | 0
Ongoing Cost | Additional Model Maintenance | 0 | 110000 | 110000 | 110000 | NPV = | 294031.3144
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Internal ERCOT Cost: | 1100000
ERCOT Internal Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Direct Cost Savings | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
Productivity Increases | Staffing | 127855 | 127855 | 127855 | 127855 | NPV = | 341757.9428
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Internal ERCOT Benefit: | 470000
Market Cost and Benefit Detail
Market Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Select type… |  |  |  |  | NPV = | 0
Ongoing Cost | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Market Cost: | 0
Market Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Benefits for Market | Staffing | 327833.3333 | 327833.3333 | 327833.3333 | 327833.3333 | NPV = | 876302.4174
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Total Present Value of Market Benefit: | 1200000
Total Cost | 1100000 |  | Net (Cost) - Benefit ($) |  | 600000
Total Benefit | 1700000 |  | Cost Benefit Ratio |  | 1.5455
Summary values are rounded to 2 significant digits.
Additional Comments
Enter any additional comments here…
1 | The Planning Models will support the improvements being made to the load flow software being used by the ERCOT staff, ERCOT stakeholders, and the majority of the TSPs, which will improve the planning analysis being performed and keep ERCOT up to date with the analysis capability of the rest of the utility industry.
2 | The number of Planning Models could increase. The ERCOT stakeholders and the Planning Working Group have discussed the need for additional models, such as a 10-year model or high wind model. Each additional model will increase the costs by $100,000 based on the TSPs assumptions.
3 | Because the process of developing the Planning Models has not actually begun, the TSPs are continuing to determine if there is a need for additional standard PMCRs, which could increase the costs further.
4 | With new versions of PSS/E load flow software, there could be costs for additional Standard PMCRs.
5 | Several TSPs have not participated in the Cost-Benefit analysis; therefore, those benefits are not included in the estimates.
6 | New market entrants do not know the impact; therefore, their costs cannot be quantified at this point.
7 | New Topology Processor downloads will be used twice a year, once for Data Set A and once for Data Set B. If Market Participants want the Transmission Information and Tracking (“TPIT”) quarterly updates to be built from new topology processor downloads, then the costs will increase.
Benefit and Impact Prompts
GOVERNANCE: Is the project required to support a PUCT rulemaking or government requirement?
GOVERNANCE: Is the project required by a market or ERCOT committee?
GOVERNANCE: Will the project provide better information for management decision making?
RELIABILITY: Does the project improve the reliability of the grid?
RELIABILITY: Does the project improve the reliability of ERCOT's computing infrastructure?
RELIABILITY: Is there a significant operational need for the project?
SAFETY: Will the project enhance safety within ERCOT?
SECURITY: Is there a physical or cyber-security issue that is addressed by this effort?
SECURITY: Does the project address an audit finding?
SECURITY: Will the project decrease the chance of fraud or help protect sensitive data?
RISK REDUCTION: Does this reduce risk to ERCOT in some significant manner?
RESOURCES: Does the project reduce the number of resources needed to support current operations?
RESOURCES: Does the project deliver infrastructure components that are more efficient or more easily upgraded?
DATA MANAGEMENT: Does this improve the accuracy, timeliness and transparency of transactions or settlements?
DATA MANAGEMENT: Does this enhance or optimize our data storage capability?
DATA MANAGEMENT: Does this improve reporting capabilities (financial, operational, etc.)?
EFFICIENCY: Does the project improve the efficiency or effectiveness of ERCOT?
EFFICIENCY: Does the project automate, improve or streamline a necessary function?
INVESTMENT: Is the project an investment in new capability or does it support the current architecture?
OTHER: Are there other areas that will indirectly benefit from this project?
Feasibility Prompts
REQUIREMENTS: Are high level requirements clearly defined?
REQUIREMENTS: How complex are the potential solutions?
REQUIREMENTS: Does a required completion date make delivery more difficult?
DELIVERY: Can the project be broken down into smaller sections or delivered in stages to reduce risk?
DELIVERY: Will training be required as the project is rolled out?
DEPENDENCIES: Are there major dependencies on other projects that make this difficult to implement?
Alternative Prompts
DELIVERY: Is a manual workaround an option (short-term or long-term)?
DELIVERY: Does a partial implementation provide enough value to be worth considering?
DELIVERY: Should a phased implementation be considered to reduce risk or accelerate key benefits?
DELIVERY: If this is an automation project is it reasonable to consider using the current process?
Assumption Prompts
DEPENDENCIES: Is this request is dependent on another ERCOT project (either active or planned)?
DELIVERABLES: Are specific key deliverables required from this project?
DELIVERABLES: What is the useful life of the deliverables of this project?
RESOURCES: Are computing resources assumed that are not to be delivered by this project?
RESOURCES: Are specific key resources assumed to be available for this project?
RESOURCES: Are there facilities requirements necessary for this project?
REQUIREMENTS: Is completion required by a specific date?

## SCR760-7 Summary
Cost Benefit Analysis Summary
Request Information
PRR / SCR / PR / "New": | SCR760-7 |  |  | Estimator's Name: |  | ERCOT and TSPs
Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models |  |  | Sponsor's Name: |  | SSWG
|  |  |  | Estimate Date: |  | 2011-03-09
Project Description: | Allow any valid PSS/E ID’s to be assigned, in particular where breakers and switches are used to split up branches. Current SSWG cases allow zero impedance branches to have any valid two character PSS/E ID. Simply maintain this ability for SSWG members because circuit IDs have already been assigned for particular reasons. In Information Model Manager, allow the capability to assign any valid PSS/E ID to Breakers and Switches by including an additional attribute. Also, remove validation rules that limit the PSS/E ID on series devices to Sx.
Benefits and Impacts
Feasibility
Alternatives (Considered and Rejected)
1 - This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 - ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 - ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Joint ERCOT & Market Assumptions
1 - The cost to identify equipment needing NOMCR following the implementation of these changes is equal to the cost to identify the equipment needing a standard PMCR prior to implementation of these changes resulting in no cost/benefit.
2 - The cost to create NOMCR following the implementation of these changes is equal to the cost to create PMCR prior to implementation of these changes resulting in no cost/benefit.
3 - The Topology Processor case is a one-time download before work begins on a new data set case build process. There will be a minimum of two downloads of the Topology Processor data each year (Data Set A and Data Set B).
4 - Costs from the Preliminary Impact Analysis (IA) have been used in the Cost portions of this document based on the mid-point of the range in the Prelimiary IA.
5 - The Cost-Benefit Analysis considers costs and benefits over a four-year time period because 4 years is generally the depreciation life of software projects from a capital point of view. Since this project will be capitalized, from an accounting perspective , its economic life will end at 4 years and there is likely to be no salvage value. The useful life could be much longer than the economic life. It is very possible that four years from now, a completely different solution will make the SCR760 effort obsolete. But then there is chance that our SCR760 solution will continue to work. Because of this unknown, software projects have a standard life of 4 years. However, it is understood that the operation and maintenance costs outlined as ERCOT and Market Benefits will not end in four years given that conditions causing the need for SCR760 remain the same.
6 - Costs and Benefits in Years 1 through 3 have not been escalated for inflation.
7 - Staffing Productivity Benefit is calculated as follows: (#standard PMCRs/# PMCRs per hour * hourly rate) * # case building and/or case updating periods per year
8 - The maximum number of records that can be eliminated as a result of the implementation of these changes is five hundred and fifty (550).
Additional ERCOT Assumptions
1 - ERCOT is responsible for reviewing and accepting standard PMCRs submitted by TSPs.
2 - ERCOT is responsible for reviewing and validating NOMCRs
3 - Benefit is derived from one time entry for NOMCR versus review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
4 - The benefit is measured as the annual time saved because there are fewer PMCRs to review during each case building and/or case updating period following the implementation of these changes.
5 - ERCOT uses a blended rate of $65/hour for internal labor for all project estimates.
6 - On average, ten (10) standard PMCRs can be reviewed and accepted per hour.
Additional TSP Assumptions
1 - TSPs are responsible for the creation, review and maintenance of standard PMCRs.
2 - TSPs are responsible for the creation and submittal of NOMCRs
3 - All standard PMCRs will be built from scratch and reviewed for each model each time there is a Topology Processor download and reviewed for quarterly updates to avoid data errors.
4 - Benefit is derived from one time entry for NOMCR versus creation and review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
5 - Experienced transmission planners must be responsible for creating standard PMCRs. The hourly rate of $100 reflects the fully loaded cost of such an employee.
6 - On average, six (6) standard PMCRs can be created and submitted per hour.
Cost and Benefit Summary
Project Costs | ERCOT Implementation Cost | 120000 |  |  |  |  | All values in this section are rounded to 2 significant digits
| Market Implementation Cost | 0
| Total Implementation Cost |  | 120000
| ERCOT Ongoing Cost | 0
| Market Ongoing Cost | 0
| Total Ongoing Cost |  | 0
[5 empty] | 120000 |  | Total Cost
Project Benefit | ERCOT Benefit | 130000
| Market Benefit | 340000
[5 empty] | 470000 |  | Total Benefit
|  | Net (Cost) - Benefit |  |  | 350000
Calculation Parameters
Market Cost | Impacted Number of QSEs |  |  | 0
| Impacted Number of CRs |  |  | #REF!
| Impacted Number of TDSPs |  |  | #REF!
| Impacted Number of Resources |  |  | #REF!
Present Value Interest Rate: |  |  |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows

## SCR760-7 Detail
Cost Benefit Analysis Data Entry Worksheet
PRR / SCR / Etc.: | SCR760-7 | Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models
Sponsor: | SSWG | Estimate Date: | 2011-03-09 | Estimator: | ERCOT and TSPs
Project Description: (please be clear and concise) | Allow any valid PSS/E ID’s to be assigned, in particular where breakers and switches are used to split up branches. Current SSWG cases allow zero impedance branches to have any valid two character PSS/E ID. Simply maintain this ability for SSWG members because circuit IDs have already been assigned for particular reasons. In Information Model Manager, allow the capability to assign any valid PSS/E ID to Breakers and Switches by including an additional attribute. Also, remove validation rules that limit the PSS/E ID on series devices to Sx.
Benefits and Impacts
Click here for ideas on benefit and impact areas… ---------------------------------------------------------------------------------->>>
1
2
3
5
6
7
8
Feasibility
Click here for ideas on feasibility… ---------------------------------------------------------------------------------->>>
Dependencies
Other 1
Other 2
Other 3
Alternatives (Considered and Rejected)
Click here for ideas on alternatives… ---------------------------------------------------------------------------------->>>
1 | This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 | ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 | ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Joint ERCOT & Market Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | The cost to identify equipment needing NOMCR following the implementation of these changes is equal to the cost to identify the equipment needing a standard PMCR prior to implementation of these changes resulting in no cost/benefit.
2 | The cost to create NOMCR following the implementation of these changes is equal to the cost to create PMCR prior to implementation of these changes resulting in no cost/benefit.
3 | The Topology Processor case is a one-time download before work begins on a new data set case build process. There will be a minimum of two downloads of the Topology Processor data each year (Data Set A and Data Set B).
4 | Costs from the Preliminary Impact Analysis (IA) have been used in the Cost portions of this document based on the mid-point of the range in the Prelimiary IA.
5 | The Cost-Benefit Analysis considers costs and benefits over a four-year time period because 4 years is generally the depreciation life of software projects from a capital point of view. Since this project will be capitalized, from an accounting perspective , its economic life will end at 4 years and there is likely to be no salvage value. The useful life could be much longer than the economic life. It is very possible that four years from now, a completely different solution will make the SCR760 effort obsolete. But then there is chance that our SCR760 solution will continue to work. Because of this unknown, software projects have a standard life of 4 years. However, it is understood that the operation and maintenance costs outlined as ERCOT and Market Benefits will not end in four years given that conditions causing the need for SCR760 remain the same.
6 | Costs and Benefits in Years 1 through 3 have not been escalated for inflation.
7 | Staffing Productivity Benefit is calculated as follows: (#standard PMCRs/# PMCRs per hour * hourly rate) * # case building and/or case updating periods per year
8 | The maximum number of records that can be eliminated as a result of the implementation of these changes is five hundred and fifty (550).
Additional ERCOT Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | ERCOT is responsible for reviewing and accepting standard PMCRs submitted by TSPs.
2 | ERCOT is responsible for reviewing and validating NOMCRs
3 | Benefit is derived from one time entry for NOMCR versus review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
4 | The benefit is measured as the annual time saved because there are fewer PMCRs to review during each case building and/or case updating period following the implementation of these changes.
5 | ERCOT uses a blended rate of $65/hour for internal labor for all project estimates.
6 | On average, ten (10) standard PMCRs can be reviewed and accepted per hour.
Additional TSP Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | TSPs are responsible for the creation, review and maintenance of standard PMCRs.
2 | TSPs are responsible for the creation and submittal of NOMCRs
3 | All standard PMCRs will be built from scratch and reviewed for each model each time there is a Topology Processor download and reviewed for quarterly updates to avoid data errors.
4 | Benefit is derived from one time entry for NOMCR versus creation and review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
5 | Experienced transmission planners must be responsible for creating standard PMCRs. The hourly rate of $100 reflects the fully loaded cost of such an employee.
6 | On average, six (6) standard PMCRs can be created and submitted per hour.
ERCOT Cost and Benefit Detail
ERCOT Internal Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Project | 122500 | 0 | 0 | 0 | NPV = | 0
Ongoing Cost | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Internal ERCOT Cost: | 120000
ERCOT Internal Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Direct Cost Savings | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
Productivity Increases | Staffing | 35750 | 35750 | 35750 | 35750 | NPV = | 95560.1772
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Internal ERCOT Benefit: | 130000
Market Cost and Benefit Detail
Market Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Select type… |  |  |  |  | NPV = | 0
Ongoing Cost | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Market Cost: | 0
Market Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Benefits for Market | Staffing | 91666.6667 | 91666.6667 | 91666.6667 | 91666.6667 | NPV = | 245026.0954
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Total Present Value of Market Benefit: | 340000
Total Cost | 120000 |  | Net (Cost) - Benefit ($) |  | 350000
Total Benefit | 470000 |  | Cost Benefit Ratio |  | 3.9167
Summary values are rounded to 2 significant digits.
Additional Comments
Enter any additional comments here…
1 | The Planning Models will support the improvements being made to the load flow software being used by the ERCOT staff, ERCOT stakeholders, and the majority of the TSPs, which will improve the planning analysis being performed and keep ERCOT up to date with the analysis capability of the rest of the utility industry.
2 | The number of Planning Models could increase. The ERCOT stakeholders and the Planning Working Group have discussed the need for additional models, such as a 10-year model or high wind model. Each additional model will increase the costs by $100,000 based on the TSPs assumptions.
3 | Because the process of developing the Planning Models has not actually begun, the TSPs are continuing to determine if there is a need for additional standard PMCRs, which could increase the costs further.
4 | With new versions of PSS/E load flow software, there could be costs for additional Standard PMCRs.
5 | Several TSPs have not participated in the Cost-Benefit analysis; therefore, those benefits are not included in the estimates.
6 | New market entrants do not know the impact; therefore, their costs cannot be quantified at this point.
7 | New Topology Processor downloads will be used twice a year, once for Data Set A and once for Data Set B. If Market Participants want the Transmission Information and Tracking (“TPIT”) quarterly updates to be built from new topology processor downloads, then the costs will increase.
GOVERNANCE: Is the project required to support a PUCT rulemaking or government requirement?
GOVERNANCE: Is the project required by a market or ERCOT committee?
GOVERNANCE: Will the project provide better information for management decision making?
RELIABILITY: Does the project improve the reliability of the grid?
RELIABILITY: Does the project improve the reliability of ERCOT's computing infrastructure?
RELIABILITY: Is there a significant operational need for the project?
SAFETY: Will the project enhance safety within ERCOT?
SECURITY: Is there a physical or cyber-security issue that is addressed by this effort?
SECURITY: Does the project address an audit finding?
SECURITY: Will the project decrease the chance of fraud or help protect sensitive data?
RISK REDUCTION: Does this reduce risk to ERCOT in some significant manner?
RESOURCES: Does the project reduce the number of resources needed to support current operations?
RESOURCES: Does the project deliver infrastructure components that are more efficient or more easily upgraded?
DATA MANAGEMENT: Does this improve the accuracy, timeliness and transparency of transactions or settlements?
DATA MANAGEMENT: Does this enhance or optimize our data storage capability?
DATA MANAGEMENT: Does this improve reporting capabilities (financial, operational, etc.)?
EFFICIENCY: Does the project improve the efficiency or effectiveness of ERCOT?
EFFICIENCY: Does the project automate, improve or streamline a necessary function?
INVESTMENT: Is the project an investment in new capability or does it support the current architecture?
OTHER: Are there other areas that will indirectly benefit from this project?
Feasibility Prompts
REQUIREMENTS: Are high level requirements clearly defined?
REQUIREMENTS: How complex are the potential solutions?
REQUIREMENTS: Does a required completion date make delivery more difficult?
DELIVERY: Can the project be broken down into smaller sections or delivered in stages to reduce risk?
DELIVERY: Will training be required as the project is rolled out?
DEPENDENCIES: Are there major dependencies on other projects that make this difficult to implement?
Alternative Prompts
DELIVERY: Is a manual workaround an option (short-term or long-term)?
DELIVERY: Does a partial implementation provide enough value to be worth considering?
DELIVERY: Should a phased implementation be considered to reduce risk or accelerate key benefits?
DELIVERY: If this is an automation project is it reasonable to consider using the current process?
Assumption Prompts
DEPENDENCIES: Is this request is dependent on another ERCOT project (either active or planned)?
DELIVERABLES: Are specific key deliverables required from this project?
DELIVERABLES: What is the useful life of the deliverables of this project?
RESOURCES: Are computing resources assumed that are not to be delivered by this project?
RESOURCES: Are specific key resources assumed to be available for this project?
RESOURCES: Are there facilities requirements necessary for this project?
REQUIREMENTS: Is completion required by a specific date?

## SCR760-8 Summary
Cost Benefit Analysis Summary
Request Information
PRR / SCR / PR / "New": | SCR760-8 |  |  | Estimator's Name: |  | ERCOT and TSPs
Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models |  |  | Sponsor's Name: |  | SSWG
|  |  |  | Estimate Date: |  | 2011-03-09
Project Description: | Allow representation of a phase shift for an autotransformer winding in the Topology Processor PSS/E cases. Topology Processor should check the value in the “Connection Type” attribute between TransformerWindings objects. If two windings are Y-Δ, then process as a 30 degree phase shift.
Benefits and Impacts
Feasibility
Alternatives (Considered and Rejected)
1 - This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 - ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 - ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Joint ERCOT & Market Assumptions
1 - The cost to identify equipment needing NOMCR following the implementation of these changes is equal to the cost to identify the equipment needing a standard PMCR prior to implementation of these changes resulting in no cost/benefit.
2 - The cost to create NOMCR following the implementation of these changes is equal to the cost to create PMCR prior to implementation of these changes resulting in no cost/benefit.
3 - The Topology Processor case is a one-time download before work begins on a new data set case build process. There will be a minimum of two downloads of the Topology Processor data each year (Data Set A and Data Set B).
4 - Costs from the Preliminary Impact Analysis (IA) have been used in the Cost portions of this document based on the mid-point of the range in the Prelimiary IA.
5 - The Cost-Benefit Analysis considers costs and benefits over a four-year time period because 4 years is generally the depreciation life of software projects from a capital point of view. Since this project will be capitalized, from an accounting perspective , its economic life will end at 4 years and there is likely to be no salvage value. The useful life could be much longer than the economic life. It is very possible that four years from now, a completely different solution will make the SCR760 effort obsolete. But then there is chance that our SCR760 solution will continue to work. Because of this unknown, software projects have a standard life of 4 years. However, it is understood that the operation and maintenance costs outlined as ERCOT and Market Benefits will not end in four years given that conditions causing the need for SCR760 remain the same.
6 - Costs and Benefits in Years 1 through 3 have not been escalated for inflation.
7 - Staffing Productivity Benefit is calculated as follows: (#standard PMCRs/# PMCRs per hour * hourly rate) * # case building and/or case updating periods per year
8 - The maximum number of records that can be eliminated as a result of the implementation of these changes is three hundred and four (304).
Additional ERCOT Assumptions
1 - ERCOT is responsible for reviewing and accepting standard PMCRs submitted by TSPs.
2 - ERCOT is responsible for reviewing and validating NOMCRs
3 - Benefit is derived from one time entry for NOMCR versus review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
4 - The benefit is measured as the annual time saved because there are fewer PMCRs to review during each case building and/or case updating period following the implementation of these changes.
5 - ERCOT uses a blended rate of $65/hour for internal labor for all project estimates.
6 - On average, ten (10) standard PMCRs can be reviewed and accepted per hour.
Additional TSP Assumptions
1 - TSPs are responsible for the creation, review and maintenance of standard PMCRs.
2 - TSPs are responsible for the creation and submittal of NOMCRs
3 - All standard PMCRs will be built from scratch and reviewed for each model each time there is a Topology Processor download and reviewed for quarterly updates to avoid data errors.
4 - Benefit is derived from one time entry for NOMCR versus creation and review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
5 - Experienced transmission planners must be responsible for creating standard PMCRs. The hourly rate of $100 reflects the fully loaded cost of such an employee.
6 - On average, six (6) standard PMCRs can be created and submitted per hour.
Cost and Benefit Summary
Project Costs | ERCOT Implementation Cost | 110000 |  |  |  |  | All values in this section are rounded to 2 significant digits
| Market Implementation Cost | 0
| Total Implementation Cost |  | 110000
| ERCOT Ongoing Cost | 20000
| Market Ongoing Cost | 0
| Total Ongoing Cost |  | 20000
[5 empty] | 130000 |  | Total Cost
Project Benefit | ERCOT Benefit | 73000
| Market Benefit | 190000
[5 empty] | 260000 |  | Total Benefit
|  | Net (Cost) - Benefit |  |  | 130000
Calculation Parameters
Market Cost | Impacted Number of QSEs |  |  | 0
| Impacted Number of CRs |  |  | #REF!
| Impacted Number of TDSPs |  |  | #REF!
| Impacted Number of Resources |  |  | #REF!
Present Value Interest Rate: |  |  |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows

## SCR760-8 Detail
Cost Benefit Analysis Data Entry Worksheet
PRR / SCR / Etc.: | SCR760-8 | Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models
Sponsor: | SSWG | Estimate Date: | 2011-03-09 | Estimator: | ERCOT and TSPs
Project Description: (please be clear and concise) | Allow representation of a phase shift for an autotransformer winding in the Topology Processor PSS/E cases. Topology Processor should check the value in the “Connection Type” attribute between TransformerWindings objects. If two windings are Y-Δ, then process as a 30 degree phase shift.
Benefits and Impacts
Click here for ideas on benefit and impact areas… ---------------------------------------------------------------------------------->>>
1
2
3
5
6
7
8
Feasibility
Click here for ideas on feasibility… ---------------------------------------------------------------------------------->>>
Dependencies
Other 1
Other 2
Other 3
Alternatives (Considered and Rejected)
Click here for ideas on alternatives… ---------------------------------------------------------------------------------->>>
1 | This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 | ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 | ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Joint ERCOT & Market Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | The cost to identify equipment needing NOMCR following the implementation of these changes is equal to the cost to identify the equipment needing a standard PMCR prior to implementation of these changes resulting in no cost/benefit.
2 | The cost to create NOMCR following the implementation of these changes is equal to the cost to create PMCR prior to implementation of these changes resulting in no cost/benefit.
3 | The Topology Processor case is a one-time download before work begins on a new data set case build process. There will be a minimum of two downloads of the Topology Processor data each year (Data Set A and Data Set B).
4 | Costs from the Preliminary Impact Analysis (IA) have been used in the Cost portions of this document based on the mid-point of the range in the Prelimiary IA.
5 | The Cost-Benefit Analysis considers costs and benefits over a four-year time period because 4 years is generally the depreciation life of software projects from a capital point of view. Since this project will be capitalized, from an accounting perspective , its economic life will end at 4 years and there is likely to be no salvage value. The useful life could be much longer than the economic life. It is very possible that four years from now, a completely different solution will make the SCR760 effort obsolete. But then there is chance that our SCR760 solution will continue to work. Because of this unknown, software projects have a standard life of 4 years. However, it is understood that the operation and maintenance costs outlined as ERCOT and Market Benefits will not end in four years given that conditions causing the need for SCR760 remain the same.
6 | Costs and Benefits in Years 1 through 3 have not been escalated for inflation.
7 | Staffing Productivity Benefit is calculated as follows: (#standard PMCRs/# PMCRs per hour * hourly rate) * # case building and/or case updating periods per year
8 | The maximum number of records that can be eliminated as a result of the implementation of these changes is three hundred and four (304).
Additional ERCOT Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | ERCOT is responsible for reviewing and accepting standard PMCRs submitted by TSPs.
2 | ERCOT is responsible for reviewing and validating NOMCRs
3 | Benefit is derived from one time entry for NOMCR versus review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
4 | The benefit is measured as the annual time saved because there are fewer PMCRs to review during each case building and/or case updating period following the implementation of these changes.
5 | ERCOT uses a blended rate of $65/hour for internal labor for all project estimates.
6 | On average, ten (10) standard PMCRs can be reviewed and accepted per hour.
Additional TSP Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | TSPs are responsible for the creation, review and maintenance of standard PMCRs.
2 | TSPs are responsible for the creation and submittal of NOMCRs
3 | All standard PMCRs will be built from scratch and reviewed for each model each time there is a Topology Processor download and reviewed for quarterly updates to avoid data errors.
4 | Benefit is derived from one time entry for NOMCR versus creation and review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
5 | Experienced transmission planners must be responsible for creating standard PMCRs. The hourly rate of $100 reflects the fully loaded cost of such an employee.
6 | On average, six (6) standard PMCRs can be created and submitted per hour.
ERCOT Cost and Benefit Detail
ERCOT Internal Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Project | 112500 | 0 | 0 | 0 | NPV = | 0
Ongoing Cost | Additional Model Maintenance | 0 | 7500 | 7500 | 7500 | NPV = | 20047.5896
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Internal ERCOT Cost: | 130000
ERCOT Internal Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Direct Cost Savings | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
Productivity Increases | Staffing | 19760 | 19760 | 19760 | 19760 | NPV = | 52818.7161
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Internal ERCOT Benefit: | 73000
Market Cost and Benefit Detail
Market Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Select type… |  |  |  |  | NPV = | 0
Ongoing Cost | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Market Cost: | 0
Market Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Benefits for Market | Staffing | 50666.6667 | 50666.6667 | 50666.6667 | 50666.6667 | NPV = | 135432.6054
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Total Present Value of Market Benefit: | 190000
Total Cost | 130000 |  | Net (Cost) - Benefit ($) |  | 130000
Total Benefit | 260000 |  | Cost Benefit Ratio |  | 2
Summary values are rounded to 2 significant digits.
Additional Comments
Enter any additional comments here…
1 | The Planning Models will support the improvements being made to the load flow software being used by the ERCOT staff, ERCOT stakeholders, and the majority of the TSPs, which will improve the planning analysis being performed and keep ERCOT up to date with the analysis capability of the rest of the utility industry.
2 | The number of Planning Models could increase. The ERCOT stakeholders and the Planning Working Group have discussed the need for additional models, such as a 10-year model or high wind model. Each additional model will increase the costs by $100,000 based on the TSPs assumptions.
3 | Because the process of developing the Planning Models has not actually begun, the TSPs are continuing to determine if there is a need for additional standard PMCRs, which could increase the costs further.
4 | With new versions of PSS/E load flow software, there could be costs for additional Standard PMCRs.
5 | Several TSPs have not participated in the Cost-Benefit analysis; therefore, those benefits are not included in the estimates.
6 | New market entrants do not know the impact; therefore, their costs cannot be quantified at this point.
7 | New Topology Processor downloads will be used twice a year, once for Data Set A and once for Data Set B. If Market Participants want the Transmission Information and Tracking (“TPIT”) quarterly updates to be built from new topology processor downloads, then the costs will increase.
Benefit and Impact Prompts
GOVERNANCE: Is the project required to support a PUCT rulemaking or government requirement?
GOVERNANCE: Is the project required by a market or ERCOT committee?
GOVERNANCE: Will the project provide better information for management decision making?
RELIABILITY: Does the project improve the reliability of the grid?
RELIABILITY: Does the project improve the reliability of ERCOT's computing infrastructure?
RELIABILITY: Is there a significant operational need for the project?
SAFETY: Will the project enhance safety within ERCOT?
SECURITY: Is there a physical or cyber-security issue that is addressed by this effort?
SECURITY: Does the project address an audit finding?
SECURITY: Will the project decrease the chance of fraud or help protect sensitive data?
RISK REDUCTION: Does this reduce risk to ERCOT in some significant manner?
RESOURCES: Does the project reduce the number of resources needed to support current operations?
RESOURCES: Does the project deliver infrastructure components that are more efficient or more easily upgraded?
DATA MANAGEMENT: Does this improve the accuracy, timeliness and transparency of transactions or settlements?
DATA MANAGEMENT: Does this enhance or optimize our data storage capability?
DATA MANAGEMENT: Does this improve reporting capabilities (financial, operational, etc.)?
EFFICIENCY: Does the project improve the efficiency or effectiveness of ERCOT?
EFFICIENCY: Does the project automate, improve or streamline a necessary function?
INVESTMENT: Is the project an investment in new capability or does it support the current architecture?
OTHER: Are there other areas that will indirectly benefit from this project?
Feasibility Prompts
REQUIREMENTS: Are high level requirements clearly defined?
REQUIREMENTS: How complex are the potential solutions?
REQUIREMENTS: Does a required completion date make delivery more difficult?
DELIVERY: Can the project be broken down into smaller sections or delivered in stages to reduce risk?
DELIVERY: Will training be required as the project is rolled out?
DEPENDENCIES: Are there major dependencies on other projects that make this difficult to implement?
Alternative Prompts
DELIVERY: Is a manual workaround an option (short-term or long-term)?
DELIVERY: Does a partial implementation provide enough value to be worth considering?
DELIVERY: Should a phased implementation be considered to reduce risk or accelerate key benefits?
DELIVERY: If this is an automation project is it reasonable to consider using the current process?
Assumption Prompts
DEPENDENCIES: Is this request is dependent on another ERCOT project (either active or planned)?
DELIVERABLES: Are specific key deliverables required from this project?
DELIVERABLES: What is the useful life of the deliverables of this project?
RESOURCES: Are computing resources assumed that are not to be delivered by this project?
RESOURCES: Are specific key resources assumed to be available for this project?
RESOURCES: Are there facilities requirements necessary for this project?
REQUIREMENTS: Is completion required by a specific date?

## SCR760-3 Summary
Cost Benefit Analysis Summary
Request Information
PRR / SCR / PR / "New": | SCR760-3 |  |  | Estimator's Name: |  | ERCOT and TSPs
Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models |  |  | Sponsor's Name: |  | SSWG
|  |  |  | Estimate Date: |  | 2011-03-09
Project Description: | Represent the proper ratings on zero impedance lines in the Topology Processor PSS/E cases. IMM already has rating attributes associated with breakers and switches. ERCOT may make these rating attributes available to the TSP NOMCR process, and modify the topology processer to transfer these ratings into the Model on Demand process as zero impedance elements with a rating.
Benefits and Impacts
Feasibility
Alternatives (Considered and Rejected)
1 - This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 - ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 - ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Joint ERCOT & Market Assumptions
1 - The cost to identify equipment needing NOMCR following the implementation of these changes is equal to the cost to identify the equipment needing a standard PMCR prior to implementation of these changes resulting in no cost/benefit.
2 - The cost to create NOMCR following the implementation of these changes is equal to the cost to create PMCR prior to implementation of these changes resulting in no cost/benefit.
3 - The Topology Processor case is a one-time download before work begins on a new data set case build process. There will be a minimum of two downloads of the Topology Processor data each year (Data Set A and Data Set B).
4 - Costs from the Preliminary Impact Analysis (IA) have been used in the Cost portions of this document based on the mid-point of the range in the Prelimiary IA.
5 - The Cost-Benefit Analysis considers costs and benefits over a four-year time period because 4 years is generally the depreciation life of software projects from a capital point of view. Since this project will be capitalized, from an accounting perspective , its economic life will end at 4 years and there is likely to be no salvage value. The useful life could be much longer than the economic life. It is very possible that four years from now, a completely different solution will make the SCR760 effort obsolete. But then there is chance that our SCR760 solution will continue to work. Because of this unknown, software projects have a standard life of 4 years. However, it is understood that the operation and maintenance costs outlined as ERCOT and Market Benefits will not end in four years given that conditions causing the need for SCR760 remain the same.
6 - Costs and Benefits in Years 1 through 3 have not been escalated for inflation.
7 - Staffing Productivity Benefit is calculated as follows: (#standard PMCRs/# PMCRs per hour * hourly rate) * # case building and/or case updating periods per year
8 - The maximum number of records that can be eliminated as a result of the implementation of these changes is nine hundred and sixty-three (963).
Additional ERCOT Assumptions
1 - ERCOT is responsible for reviewing and accepting standard PMCRs submitted by TSPs.
2 - ERCOT is responsible for reviewing and validating NOMCRs
3 - Benefit is derived from one time entry for NOMCR versus review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
4 - The benefit is measured as the annual time saved because there are fewer PMCRs to review during each case building and/or case updating period following the implementation of these changes.
5 - ERCOT uses a blended rate of $65/hour for internal labor for all project estimates.
6 - On average, ten (10) standard PMCRs can be reviewed and accepted per hour.
Additional TSP Assumptions
1 - TSPs are responsible for the creation, review and maintenance of standard PMCRs.
2 - TSPs are responsible for the creation and submittal of NOMCRs
3 - All standard PMCRs will be built from scratch and reviewed for each model each time there is a Topology Processor download and reviewed for quarterly updates to avoid data errors.
4 - Benefit is derived from one time entry for NOMCR versus creation and review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
5 - Experienced transmission planners must be responsible for creating standard PMCRs. The hourly rate of $100 reflects the fully loaded cost of such an employee.
6 - On average, six (6) standard PMCRs can be created and submitted per hour.
Cost and Benefit Summary
Project Costs | ERCOT Implementation Cost | 240000 |  |  |  |  | All values in this section are rounded to 2 significant digits
| Market Implementation Cost | 0
| Total Implementation Cost |  | 240000
| ERCOT Ongoing Cost | 60000
| Market Ongoing Cost | 0
| Total Ongoing Cost |  | 60000
[5 empty] | 300000 |  | Total Cost
Project Benefit | ERCOT Benefit | 230000
| Market Benefit | 590000
[5 empty] | 820000 |  | Total Benefit
|  | Net (Cost) - Benefit |  |  | 520000
Calculation Parameters
Market Cost | Impacted Number of QSEs |  |  | 0
| Impacted Number of CRs |  |  | #REF!
| Impacted Number of TDSPs |  |  | #REF!
| Impacted Number of Resources |  |  | #REF!
Present Value Interest Rate: |  |  |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows

## SCR760-3 Detail
Cost Benefit Analysis Data Entry Worksheet
PRR / SCR / Etc.: | SCR760-3 | Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models
Sponsor: | SSWG | Estimate Date: | 2011-03-09 | Estimator: | ERCOT and TSPs
Project Description: (please be clear and concise) | Represent the proper ratings on zero impedance lines in the Topology Processor PSS/E cases. IMM already has rating attributes associated with breakers and switches. ERCOT may make these rating attributes available to the TSP NOMCR process, and modify the topology processer to transfer these ratings into the Model on Demand process as zero impedance elements with a rating.
Benefits and Impacts
Click here for ideas on benefit and impact areas… ---------------------------------------------------------------------------------->>>
1
2
3
5
6
7
8
Feasibility
Click here for ideas on feasibility… ---------------------------------------------------------------------------------->>>
Dependencies
Other 1
Other 2
Other 3
Alternatives (Considered and Rejected)
Click here for ideas on alternatives… ---------------------------------------------------------------------------------->>>
1 | This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 | ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 | ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Joint ERCOT & Market Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | The cost to identify equipment needing NOMCR following the implementation of these changes is equal to the cost to identify the equipment needing a standard PMCR prior to implementation of these changes resulting in no cost/benefit.
2 | The cost to create NOMCR following the implementation of these changes is equal to the cost to create PMCR prior to implementation of these changes resulting in no cost/benefit.
3 | The Topology Processor case is a one-time download before work begins on a new data set case build process. There will be a minimum of two downloads of the Topology Processor data each year (Data Set A and Data Set B).
4 | Costs from the Preliminary Impact Analysis (IA) have been used in the Cost portions of this document based on the mid-point of the range in the Prelimiary IA.
5 | The Cost-Benefit Analysis considers costs and benefits over a four-year time period because 4 years is generally the depreciation life of software projects from a capital point of view. Since this project will be capitalized, from an accounting perspective , its economic life will end at 4 years and there is likely to be no salvage value. The useful life could be much longer than the economic life. It is very possible that four years from now, a completely different solution will make the SCR760 effort obsolete. But then there is chance that our SCR760 solution will continue to work. Because of this unknown, software projects have a standard life of 4 years. However, it is understood that the operation and maintenance costs outlined as ERCOT and Market Benefits will not end in four years given that conditions causing the need for SCR760 remain the same.
6 | Costs and Benefits in Years 1 through 3 have not been escalated for inflation.
7 | Staffing Productivity Benefit is calculated as follows: (#standard PMCRs/# PMCRs per hour * hourly rate) * # case building and/or case updating periods per year
8 | The maximum number of records that can be eliminated as a result of the implementation of these changes is nine hundred and sixty-three (963).
Additional ERCOT Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | ERCOT is responsible for reviewing and accepting standard PMCRs submitted by TSPs.
2 | ERCOT is responsible for reviewing and validating NOMCRs
3 | Benefit is derived from one time entry for NOMCR versus review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
4 | The benefit is measured as the annual time saved because there are fewer PMCRs to review during each case building and/or case updating period following the implementation of these changes.
5 | ERCOT uses a blended rate of $65/hour for internal labor for all project estimates.
6 | On average, ten (10) standard PMCRs can be reviewed and accepted per hour.
Additional TSP Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | TSPs are responsible for the creation, review and maintenance of standard PMCRs.
2 | TSPs are responsible for the creation and submittal of NOMCRs
3 | All standard PMCRs will be built from scratch and reviewed for each model each time there is a Topology Processor download and reviewed for quarterly updates to avoid data errors.
4 | Benefit is derived from one time entry for NOMCR versus creation and review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
5 | Experienced transmission planners must be responsible for creating standard PMCRs. The hourly rate of $100 reflects the fully loaded cost of such an employee.
6 | On average, six (6) standard PMCRs can be created and submitted per hour.
ERCOT Cost and Benefit Detail
ERCOT Internal Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Project | 237500 | 0 | 0 | 0 | NPV = | 0
Ongoing Cost | Additional Model Maintenance | 0 | 22500 | 22500 | 22500 | NPV = | 60142.7689
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Internal ERCOT Cost: | 300000
ERCOT Internal Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Direct Cost Savings | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
Productivity Increases | Staffing | 62595 | 62595 | 62595 | 62595 | NPV = | 167317.183
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Internal ERCOT Benefit: | 230000
Market Cost and Benefit Detail
Market Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Select type… |  |  |  |  | NPV = | 0
Ongoing Cost | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Market Cost: | 0
Market Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Benefits for Market | Staffing | 160500 | 160500 | 160500 | 160500 | NPV = | 429018.4179
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Total Present Value of Market Benefit: | 590000
Total Cost | 300000 |  | Net (Cost) - Benefit ($) |  | 520000
Total Benefit | 820000 |  | Cost Benefit Ratio |  | 2.7333
Summary values are rounded to 2 significant digits.
Additional Comments
Enter any additional comments here…
1 | The Planning Models will support the improvements being made to the load flow software being used by the ERCOT staff, ERCOT stakeholders, and the majority of the TSPs, which will improve the planning analysis being performed and keep ERCOT up to date with the analysis capability of the rest of the utility industry.
2 | The number of Planning Models could increase. The ERCOT stakeholders and the Planning Working Group have discussed the need for additional models, such as a 10-year model or high wind model. Each additional model will increase the costs by $100,000 based on the TSPs assumptions.
3 | Because the process of developing the Planning Models has not actually begun, the TSPs are continuing to determine if there is a need for additional standard PMCRs, which could increase the costs further.
4 | With new versions of PSS/E load flow software, there could be costs for additional Standard PMCRs.
5 | Several TSPs have not participated in the Cost-Benefit analysis; therefore, those benefits are not included in the estimates.
6 | New market entrants do not know the impact; therefore, their costs cannot be quantified at this point.
7 | New Topology Processor downloads will be used twice a year, once for Data Set A and once for Data Set B. If Market Participants want the Transmission Information and Tracking (“TPIT”) quarterly updates to be built from new topology processor downloads, then the costs will increase.
Benefit and Impact Prompts
GOVERNANCE: Is the project required to support a PUCT rulemaking or government requirement?
GOVERNANCE: Is the project required by a market or ERCOT committee?
GOVERNANCE: Will the project provide better information for management decision making?
RELIABILITY: Does the project improve the reliability of the grid?
RELIABILITY: Does the project improve the reliability of ERCOT's computing infrastructure?
RELIABILITY: Is there a significant operational need for the project?
SAFETY: Will the project enhance safety within ERCOT?
SECURITY: Is there a physical or cyber-security issue that is addressed by this effort?
SECURITY: Does the project address an audit finding?
SECURITY: Will the project decrease the chance of fraud or help protect sensitive data?
RISK REDUCTION: Does this reduce risk to ERCOT in some significant manner?
RESOURCES: Does the project reduce the number of resources needed to support current operations?
RESOURCES: Does the project deliver infrastructure components that are more efficient or more easily upgraded?
DATA MANAGEMENT: Does this improve the accuracy, timeliness and transparency of transactions or settlements?
DATA MANAGEMENT: Does this enhance or optimize our data storage capability?
DATA MANAGEMENT: Does this improve reporting capabilities (financial, operational, etc.)?
EFFICIENCY: Does the project improve the efficiency or effectiveness of ERCOT?
EFFICIENCY: Does the project automate, improve or streamline a necessary function?
INVESTMENT: Is the project an investment in new capability or does it support the current architecture?
OTHER: Are there other areas that will indirectly benefit from this project?
Feasibility Prompts
REQUIREMENTS: Are high level requirements clearly defined?
REQUIREMENTS: How complex are the potential solutions?
REQUIREMENTS: Does a required completion date make delivery more difficult?
DELIVERY: Can the project be broken down into smaller sections or delivered in stages to reduce risk?
DELIVERY: Will training be required as the project is rolled out?
DEPENDENCIES: Are there major dependencies on other projects that make this difficult to implement?
Alternative Prompts
DELIVERY: Is a manual workaround an option (short-term or long-term)?
DELIVERY: Does a partial implementation provide enough value to be worth considering?
DELIVERY: Should a phased implementation be considered to reduce risk or accelerate key benefits?
DELIVERY: If this is an automation project is it reasonable to consider using the current process?
Assumption Prompts
DEPENDENCIES: Is this request is dependent on another ERCOT project (either active or planned)?
DELIVERABLES: Are specific key deliverables required from this project?
DELIVERABLES: What is the useful life of the deliverables of this project?
RESOURCES: Are computing resources assumed that are not to be delivered by this project?
RESOURCES: Are specific key resources assumed to be available for this project?
RESOURCES: Are there facilities requirements necessary for this project?
REQUIREMENTS: Is completion required by a specific date?

## SCR760-1, -6 Summary
Cost Benefit Analysis Summary
Request Information
PRR / SCR / PR / "New": | SCR760-1, -6 |  |  | Estimator's Name: |  | ERCOT and TSPs
Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models |  |  | Sponsor's Name: |  | SSWG
|  |  |  | Estimate Date: |  | 2011-03-09
Project Description: | (1) Modify Information Model Manager and Topology Processor to allow outputting of the latest version of Power System Simulation For Engineering (PSS/E). To do this, implement an evaluation process where Steady State Working Group (SSWG) and ERCOT jointly recommend to ROS and ROS approves which new PSS/E data models should be evaluated for implementation into the IMM. The evaluation would be done on an annual basis and timed so that new data types could be used for SSWG case-building the following year. TSPs would be required to use MOD for modeling the data types until implemented in the IMM. (6) Allow capability to convert a FACTS device model in Information Model Manager to any possible FACTS device model allowed in PSS/E version 32. In Information Model Manager, Add an attribute to allow the TSP to be able to select for each object (generator, switch shunt, or FACTS Device). The TSP should be able to select the object it would like to see as a FACTS Device appear in the Topology Processor case as opposed to all FACTS Devices be modeled as generators. Any additional data parameters needed should be included as attributes, so that the Topology Processor can convert to the appropriate PSS/E model.
Benefits and Impacts
1 - The Planning Models will support the improvements being made to the load flow software being used by the ERCOT staff, ERCOT stakeholders, and the majority of the TSPs, which will improve the planning analysis being performed and keep ERCOT up to date with the analysis capability of the rest of the utility industry. ERCOT and the majority of TSPs currently update to new PSS/E releases annually in accordance with good utility practice.
Feasibility
Alternatives (Considered and Rejected)
1 - This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 - ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 - ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Joint ERCOT & Market Assumptions
1 - The cost to identify equipment needing NOMCR following the implementation of these changes is equal to the cost to identify the equipment needing a standard PMCR prior to implementation of these changes resulting in no cost/benefit.
2 - The cost to create NOMCR following the implementation of these changes is equal to the cost to create PMCR prior to implementation of these changes resulting in no cost/benefit.
3 - The Topology Processor case is a one-time download before work begins on a new data set case build process. There will be a minimum of two downloads of the Topology Processor data each year (Data Set A and Data Set B).
4 - Costs from the Preliminary Impact Analysis (IA) have been used in the Cost portions of this document based on the mid-point of the range in the Prelimiary IA.
5 - The Cost-Benefit Analysis considers costs and benefits over a four-year time period because 4 years is generally the depreciation life of software projects from a capital point of view. Since this project will be capitalized, from an accounting perspective , its economic life will end at 4 years and there is likely to be no salvage value. The useful life could be much longer than the economic life. It is very possible that four years from now, a completely different solution will make the SCR760 effort obsolete. But then there is chance that our SCR760 solution will continue to work. Because of this unknown, software projects have a standard life of 4 years. However, it is understood that the operation and maintenance costs outlined as ERCOT and Market Benefits will not end in four years given that conditions causing the need for SCR760 remain the same.
6 - Costs and Benefits in Years 1 through 3 have not been escalated for inflation.
7 - Staffing Productivity Benefit is calculated as follows: (#standard PMCRs/# PMCRs per hour * hourly rate) * # case building and/or case updating periods per year
8 - The cost to establish the process, setup the environment and implement FACTS devices and fixed shunts, as described in 760-6, are proposed for Year 0 implementation of 760-1.
9 - SSWG will convene an annual meeting to discuss and decide which new PSS/E data models should be implemented in IMM.
10 - The cost to to implement other devices, which are not yet defined, are estimated to occur every other year and are included in Year 1 and Year 3 Ongoing Model Maintenance costs.
11 - Year 2 Ongoing Model Maintenance costs are lower they include only the ongoing FTE support costs for previously implemented device types. It is assumed that the implementation of new devices from the latest PSS/E are required approximately every other year.
12 - ERCOT will provide an analysis of new device types submitted to the Planning Model through PMCR so that these devices can be considered in the joint planning meeting.
13 - The maximum number of known records that can be eliminated as a result of the implementation of this change is one hundred and sixty-nine (169). This is used for calculating the Year 0 benefit. For Years 1-Year 3, the number of records is increased by 20%.
Additional ERCOT Assumptions
1 - ERCOT is responsible for reviewing and accepting standard PMCRs submitted by TSPs.
2 - ERCOT is responsible for reviewing and validating NOMCRs
3 - Benefit is derived from one time entry for NOMCR versus review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
4 - The benefit is measured as the annual time saved because there are fewer PMCRs to review during each case building and/or case updating period following the implementation of these changes.
5 - ERCOT uses a blended rate of $65/hour for internal labor for all project estimates.
6 - On average, ten (10) standard PMCRs can be reviewed and accepted per hour.
Additional TSP Assumptions
1 - TSPs are responsible for the creation, review and maintenance of standard PMCRs.
2 - TSPs are responsible for the creation and submittal of NOMCRs
3 - All standard PMCRs will be built from scratch and reviewed for each model each time there is a Topology Processor download and reviewed for quarterly updates to avoid data errors.
4 - Benefit is derived from one time entry for NOMCR versus creation and review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
5 - Experienced transmission planners must be responsible for creating standard PMCRs. The hourly rate of $100 reflects the fully loaded cost of such an employee.
6 - On average, six (6) standard PMCRs can be created and submitted per hour.
Notes
1 - Year 0 Implementation Costs are different in the Cost Benefit Analysis from those shown in the Impact Analysis because the Cost Benefit Analysis assumes that 760-1 through 760-9 are approved and planned for implementation. It combines the implementation of 760-1 with 760-6 using an assumption that the cost to establish the process and setup the environment, as described in 760-1 plus implementation of FACTS devices and fixed shunts, as described in 760-6, are proposed for Year 0 implementation. The Impact Analysis assumes that an undefined number of new, yet to be defined, devices will be implemented. The uncertain nature of this causes the Implementation costs for 760-1, on its own, to be higher. This higher cost is shown in the Year 2 implementation cost where the number and types of new devices that will be implemented is yet to be defined. If the assumptions were the same as those for the Impact Analysis, Year 0 Implementation costs would be approximately $2.2M in the Cost Benefit Analysis compared with the estimate of $1.9M - $2.4M in the Impact Analysis.
2 - Year 1 through Year 3 Model Maintenance costs are different in the Cost Benefit Analysis from those shown in the Impact Analysis because the Cost Benefit Analysis assumes that 760-1 through 760-9 are approved and planned for implementation. It assumes that the Year 0 mplementation of 760-1 is the implementation of 760-6 so does not double-count the Additional Model Maintenance costs associated with each item. The Impact Analysis costs both 760-1 and 760-6 independently and shows the Additional Model Maintenance costs associated with the implementation of each assuming that only one or the other is implemented. If the assumptions were the same as those for the Impact Analysis, ERCOT Ongoing Costs over Years 1, 2 and 3 would be approximately $1M adjusted for NPV in the Cost Benefit Analysis compared with the estimate of $1M - 1.3M in the Impact Analysis.
Cost and Benefit Summary
Project Costs | ERCOT Implementation Cost | 490000 |  |  |  |  | All values in this section are rounded to 2 significant digits
| Market Implementation Cost | 0
| Total Implementation Cost |  | 490000
| ERCOT Ongoing Cost | 590000
| Market Ongoing Cost | 0
| Total Ongoing Cost |  | 590000
[5 empty] | 1100000 |  | Total Cost
Project Benefit | ERCOT Benefit | 46000
| Market Benefit | 120000
[5 empty] | 170000 |  | Total Benefit
|  | Net (Cost) - Benefit |  |  | -930000
Calculation Parameters
Market Cost | Impacted Number of QSEs |  |  | 0
| Impacted Number of CRs |  |  | #REF!
| Impacted Number of TDSPs |  |  | #REF!
| Impacted Number of Resources |  |  | #REF!
Present Value Interest Rate: |  |  |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows

## SCR760-1, -6 Detail
Cost Benefit Analysis Data Entry Worksheet
PRR / SCR / Etc.: | SCR760-1, -6 | Project Title: | Recommended Changes Needed from Information Model Manager and Topology Processor for Planning Models
Sponsor: | SSWG | Estimate Date: | 2011-03-09 | Estimator: | ERCOT and TSPs
Project Description: (please be clear and concise) | (1) Modify Information Model Manager and Topology Processor to allow outputting of the latest version of Power System Simulation For Engineering (PSS/E). To do this, implement an evaluation process where Steady State Working Group (SSWG) and ERCOT jointly recommend to ROS and ROS approves which new PSS/E data models should be evaluated for implementation into the IMM. The evaluation would be done on an annual basis and timed so that new data types could be used for SSWG case-building the following year. TSPs would be required to use MOD for modeling the data types until implemented in the IMM. (6) Allow capability to convert a FACTS device model in Information Model Manager to any possible FACTS device model allowed in PSS/E version 32. In Information Model Manager, Add an attribute to allow the TSP to be able to select for each object (generator, switch shunt, or FACTS Device). The TSP should be able to select the object it would like to see as a FACTS Device appear in the Topology Processor case as opposed to all FACTS Devices be modeled as generators. Any additional data parameters needed should be included as attributes, so that the Topology Processor can convert to the appropriate PSS/E model.
Benefits and Impacts
Click here for ideas on benefit and impact areas… ---------------------------------------------------------------------------------->>>
1 | The Planning Models will support the improvements being made to the load flow software being used by the ERCOT staff, ERCOT stakeholders, and the majority of the TSPs, which will improve the planning analysis being performed and keep ERCOT up to date with the analysis capability of the rest of the utility industry. ERCOT and the majority of TSPs currently update to new PSS/E releases annually in accordance with good utility practice.
2
3
4
5
6
7
8
Feasibility
Click here for ideas on feasibility… ---------------------------------------------------------------------------------->>>
Dependencies
Other 1
Other 2
Other 3
Alternatives (Considered and Rejected)
Click here for ideas on alternatives… ---------------------------------------------------------------------------------->>>
1 | This functionality is fully supported via the Model on Demand (MOD). TSPs can continue to use MOD as designed.
2 | ERCOT will load standard Planning Model Change Requests (PMCRs) via the Model on Demand and work with TSPs to resolve discrepancies.
3 | ERCOT will create a MOD environment (TP-MOD) that will use a Topology-Processed seed from NMMS. ERCOT will use PMCRs (future projects) and profiles submitted by TSPs in order to build future cases. Concurrently, ERCOT will maintain a second MOD environment (SSWG-MOD) that ERCOT will "seed" with an existing SSWG case chosen by SSWG. ERCOT will submit necessary ERCOT data, facilitate use of the MOD application, and apply TSP submitted PMCRs and Profiles as required for SSWG. TSPs can include any PMCRs they deem necessary in building cases to support their planning functions but must submit PMCRs that will work in ERCOT TP-MOD environment described above. ERCOT, TSPs, and any other Market Participant will be free to use either or both sets of cases.
Joint ERCOT & Market Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | The cost to identify equipment needing NOMCR following the implementation of these changes is equal to the cost to identify the equipment needing a standard PMCR prior to implementation of these changes resulting in no cost/benefit.
2 | The cost to create NOMCR following the implementation of these changes is equal to the cost to create PMCR prior to implementation of these changes resulting in no cost/benefit.
3 | The Topology Processor case is a one-time download before work begins on a new data set case build process. There will be a minimum of two downloads of the Topology Processor data each year (Data Set A and Data Set B).
4 | Costs from the Preliminary Impact Analysis (IA) have been used in the Cost portions of this document based on the mid-point of the range in the Prelimiary IA.
5 | The Cost-Benefit Analysis considers costs and benefits over a four-year time period because 4 years is generally the depreciation life of software projects from a capital point of view. Since this project will be capitalized, from an accounting perspective , its economic life will end at 4 years and there is likely to be no salvage value. The useful life could be much longer than the economic life. It is very possible that four years from now, a completely different solution will make the SCR760 effort obsolete. But then there is chance that our SCR760 solution will continue to work. Because of this unknown, software projects have a standard life of 4 years. However, it is understood that the operation and maintenance costs outlined as ERCOT and Market Benefits will not end in four years given that conditions causing the need for SCR760 remain the same.
6 | Costs and Benefits in Years 1 through 3 have not been escalated for inflation.
7 | Staffing Productivity Benefit is calculated as follows: (#standard PMCRs/# PMCRs per hour * hourly rate) * # case building and/or case updating periods per year
8 | The cost to establish the process, setup the environment and implement FACTS devices and fixed shunts, as described in 760-6, are proposed for Year 0 implementation of 760-1.
9 | SSWG will convene an annual meeting to discuss and decide which new PSS/E data models should be implemented in IMM.
10 | The cost to to implement other devices, which are not yet defined, are estimated to occur every other year and are included in Year 1 and Year 3 Ongoing Model Maintenance costs.
11 | Year 2 Ongoing Model Maintenance costs are lower they include only the ongoing FTE support costs for previously implemented device types. It is assumed that the implementation of new devices from the latest PSS/E are required approximately every other year.
12 | ERCOT will provide an analysis of new device types submitted to the Planning Model through PMCR so that these devices can be considered in the joint planning meeting.
13 | The maximum number of known records that can be eliminated as a result of the implementation of this change is one hundred and sixty-nine (169). This is used for calculating the Year 0 benefit. For Years 1-Year 3, the number of records is increased by 20%.
Additional ERCOT Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | ERCOT is responsible for reviewing and accepting standard PMCRs submitted by TSPs.
2 | ERCOT is responsible for reviewing and validating NOMCRs
3 | Benefit is derived from one time entry for NOMCR versus review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
4 | The benefit is measured as the annual time saved because there are fewer PMCRs to review during each case building and/or case updating period following the implementation of these changes.
5 | ERCOT uses a blended rate of $65/hour for internal labor for all project estimates.
6 | On average, ten (10) standard PMCRs can be reviewed and accepted per hour.
Additional TSP Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | TSPs are responsible for the creation, review and maintenance of standard PMCRs.
2 | TSPs are responsible for the creation and submittal of NOMCRs
3 | All standard PMCRs will be built from scratch and reviewed for each model each time there is a Topology Processor download and reviewed for quarterly updates to avoid data errors.
4 | Benefit is derived from one time entry for NOMCR versus creation and review of standard PMCRs at case building and/or case updating time to make sure it is needed x 10 case building and/or case updating periods per year.
5 | Experienced transmission planners must be responsible for creating standard PMCRs. The hourly rate of $100 reflects the fully loaded cost of such an employee.
6 | On average, six (6) standard PMCRs can be created and submitted per hour.
Notes
1 | Year 0 Implementation Costs are different in the Cost Benefit Analysis from those shown in the Impact Analysis because the Cost Benefit Analysis assumes that 760-1 through 760-9 are approved and planned for implementation. It combines the implementation of 760-1 with 760-6 using an assumption that the cost to establish the process and setup the environment, as described in 760-1 plus implementation of FACTS devices and fixed shunts, as described in 760-6, are proposed for Year 0 implementation. The Impact Analysis assumes that an undefined number of new, yet to be defined, devices will be implemented. The uncertain nature of this causes the Implementation costs for 760-1, on its own, to be higher. This higher cost is shown in the Year 2 implementation cost where the number and types of new devices that will be implemented is yet to be defined. If the assumptions were the same as those for the Impact Analysis, Year 0 Implementation costs would be approximately $2.2M in the Cost Benefit Analysis compared with the estimate of $1.9M - $2.4M in the Impact Analysis.
2 | Year 1 through Year 3 Model Maintenance costs are different in the Cost Benefit Analysis from those shown in the Impact Analysis because the Cost Benefit Analysis assumes that 760-1 through 760-9 are approved and planned for implementation. It assumes that the Year 0 mplementation of 760-1 is the implementation of 760-6 so does not double-count the Additional Model Maintenance costs associated with each item. The Impact Analysis costs both 760-1 and 760-6 independently and shows the Additional Model Maintenance costs associated with the implementation of each assuming that only one or the other is implemented. If the assumptions were the same as those for the Impact Analysis, ERCOT Ongoing Costs over Years 1, 2 and 3 would be approximately $1M adjusted for NPV in the Cost Benefit Analysis compared with the estimate of $1M - 1.3M in the Impact Analysis.
ERCOT Cost and Benefit Detail
ERCOT Internal Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Project | 492500 | 0 | 0 | 0 | *See Note 1 | NPV = | 0
Ongoing Cost | Additional Model Maintenance | 0 | 105000 | 105000 | 105000 | *See Note 2 | NPV = | 280666.2547
| Additional Costs for PSS/E upgrade project biennually | 0 | 0 | 350000 | 0 |  | NPV = | 311498.754
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Present Value of Internal ERCOT Cost: | 1100000
ERCOT Internal Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Direct Cost Savings | Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
Productivity Increases | Staffing | 10985 | 13182 | 13182 | 13182 |  | NPV = | 35235.6435
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Present Value of Internal ERCOT Benefit: | 46000
Market Cost and Benefit Detail
Market Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Select type… | [5 empty] | NPV = | 0
Ongoing Cost | Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Present Value of Market Cost: | 0
Market Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Benefits for Market | Staffing | 28166.6667 | 33800 | 33800 | 33800 |  | NPV = | 90347.8039
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0
| Total Present Value of Market Benefit: | 120000
Total Cost | 1100000 |  | Net (Cost) - Benefit ($) |  | -930000
Total Benefit | 170000 |  | Cost Benefit Ratio |  | 0.15455
Summary values are rounded to 2 significant digits.
Additional Comments
Enter any additional comments here…
1 | The Planning Models will support the improvements being made to the load flow software being used by the ERCOT staff, ERCOT stakeholders, and the majority of the TSPs, which will improve the planning analysis being performed and keep ERCOT up to date with the analysis capability of the rest of the utility industry.
2 | The number of Planning Models could increase. The ERCOT stakeholders and the Planning Working Group have discussed the need for additional models, such as a 10-year model or high wind model. Each additional model will increase the costs by $100,000 based on the TSPs assumptions.
3 | Because the process of developing the Planning Models has not actually begun, the TSPs are continuing to determine if there is a need for additional standard PMCRs, which could increase the costs further.
4 | With new versions of PSS/E load flow software, there could be costs for additional Standard PMCRs.
5 | Several TSPs have not participated in the Cost-Benefit analysis; therefore, those benefits are not included in the estimates.
6 | New market entrants do not know the impact; therefore, their costs cannot be quantified at this point.
7 | New Topology Processor downloads will be used twice a year, once for Data Set A and once for Data Set B. If Market Participants want the Transmission Information and Tracking (“TPIT”) quarterly updates to be built from new topology processor downloads, then the costs will increase.