## Summary
Average Years between IA and Commercial Operations Approval = |  |  | 2.1203
Average Years between IA and Commercial Operations Approval (excluding coal and outlier Baffin Wind) = |  |  | 1.8884
Max Years between IA and Commercial Operations Approval = |  |  | 7.1382
Max Years between IA and Commercial Operations Approval (excluding coal and outlier Baffin Wind) = |  |  | 3.8459
Fuel Type | Months from IA Signed to Commercial Operations Approval | Years from IA Signed to Commercial Operations Approval
Coal | 75.1645 | 6.2637
Gas | 24.7799 | 2.065
Solar | 13.4342 | 1.1195
Storage | 7.0395 | 0.58662
Wind | 25.2181 | 2.1015
Grand Total | 25.5079 | 2.1257
Fuel Type | Months from IA Signed to Commercial Operations Approval
Coal | 75.1645
Sandow Unit 5 | 68.1579
Sandy Creek 1 | 82.1711
Gas | 24.7799
Antelope & Elk 1 | 38.3882
Channel Energy Center 138/345kV CT | 17.0066
Deer Park Energy Center | 18.5855
Ector County Energy Center G | 20.3618
Elk 2 | 29.8355
Elk 3 | 29.8355
Ferguson Replacement Project | 26.4803
Lamar Power Upgrade | 24.1447
Panda Sherman Power | 29.8026
Panda Temple 1 | 25.2303
Panda Temple 2 G | 34.5395
Rentech Project | 21.3158
WA Parish Addition | 6.6118
Solar | 13.4342
Barilla Solar | 12.3355
Bryan Solar | 17.7303
Downie Ranch Solar | 18.8158
OCI Alamo 1 | 10.625
OCI Alamo 4 (Brackettville / ECLIPSE) | 7.6645
Storage | 7.0395
Notrees Battery Storage | 7.0395
Wind | 25.2181
Anacacho Windfarm | 14.7039
Baffin Wind | 85.6579
Blue Summit Windfarm | 21.8092
Bobcat Bluff | 17.5987
Briscoe Wind | 22.1053
Cameron County Wind | 29.6382
Colbeck's Corner W | 42.8289
Goldthwaite Wind Energy | 21.7434
Grandview Phase I (Conway Windfarm) | 25.625
Green Pastures W | 23.0263
Hereford Wind | 23.3224
Javelina Wind | 14.5395
Jumbo Road Wind | 21.9737
Keechi Wind 138 kV Joplin | 14.5066
Logans Gap Wind I | 21.6447
Longhorn North | 33.3882
Los Vientos | 29.8355
Los Vientos III | 26.3487
Mesquite Creek W | 30.8882
Miami Wind 1 Project | 21.1513
Panhandle Wind 1 | 18.2566
Panhandle Wind 2 | 13.3224
Rattlesnake W 1 | 26.8092
Redfish Wind Project | 19.0789
Route 66 Wind | 21.3487
Senate Wind Project | 46.1513
Sendero Wind | 29.9013
Shannon Wind | 32.6316
South Plains I | 22.3684
South Plains II Phase a | 29.2105
South Plains II Phase b | 29.2105
Spinning Spur W 3 | 21.7763
Spinning Spur Wind Two | 15.6908
Stephens Ranch Wind B | 10
Stephens Ranch Wind Energy Phase 1 | 33.1579
Whitetail Wind Energy Project | 12.2039
Windthorst 2 | 15.8882
WKN Mozart | 18.9474
Grand Total | 25.5079

## Raw Data
ProjectName | Fuel | IA Signed | Commissioning Part 3 Commercial Approval | Months from IA Signed to Commercial
Sandy Creek 1 | Coal | 2006-09-13 | 2013-07-16 01:00 | 82.1711
Baffin Wind | Wind | 2009-05-08 | 2016-06-24 | 85.6579
Senate Wind Project | Wind | 2009-02-13 | 2012-12-17 | 46.1513
Goldthwaite Wind Energy | Wind | 2012-08-06 | 2014-05-29 | 21.7434
Los Vientos | Wind | 2011-03-07 | 2013-08-30 | 29.8355
Bobcat Bluff | Wind | 2011-10-10 | 2013-03-28 | 17.5987
Cameron County Wind | Wind | 2013-08-09 | 2016-01-27 | 29.6382
Grandview Phase I (Conway Windfarm) | Wind | 2012-10-24 | 2014-12-12 | 25.625
Rattlesnake W 1 | Wind | 2013-06-28 | 2015-09-21 | 26.8092
Ferguson Replacement Project | Gas | 2012-05-29 | 2014-08-12 | 26.4803
Whitetail Wind Energy Project | Wind | 2011-12-15 | 2012-12-20 | 12.2039
Antelope & Elk 1 | Gas | 2013-03-28 | 2016-06-07 | 38.3882
Barilla Solar | Solar | 2013-12-26 | 2015-01-05 | 12.3355
Sendero Wind | Wind | 2013-06-26 | 2015-12-22 | 29.9013
Green Pastures W | Wind | 2013-12-17 | 2015-11-17 | 23.0263
Anacacho Windfarm | Wind | 2011-10-07 | 2012-12-27 | 14.7039
Blue Summit Windfarm | Wind | 2012-02-22 | 2013-12-16 | 21.8092
OCI Alamo 1 | Solar | 2013-01-24 | 2013-12-13 | 10.625
Hereford Wind | Wind | 2013-06-10 | 2015-05-20 | 23.3224
Mesquite Creek W | Wind | 2012-09-18 | 2015-04-15 | 30.8882
WKN Mozart | Wind | 2011-05-24 | 2012-12-20 | 18.9474
Panda Sherman Power | Gas | 2012-02-13 | 2014-08-07 | 29.8026
Panda Temple 1 | Gas | 2012-06-21 | 2014-07-28 | 25.2303
Panda Temple 2 G | Gas | 2012-06-21 | 2015-05-07 | 34.5395
Redfish Wind Project | Wind | 2011-02-25 | 2012-09-27 | 19.0789
Stephens Ranch Wind Energy Phase 1 | Wind | 2012-03-26 | 2014-12-29 | 33.1579
Shannon Wind | Wind | 2013-04-05 | 2015-12-23 | 32.6316
Notrees Battery Storage | Storage | 2012-06-21 | 2013-01-21 | 7.0395
Rentech Project | Gas | 2013-02-25 | 2014-12-05 | 21.3158
Miami Wind 1 Project | Wind | 2013-03-01 | 2014-12-04 | 21.1513
Deer Park Energy Center | Gas | 2013-01-02 | 2014-07-21 | 18.5855
Channel Energy Center 138/345kV CT | Gas | 2013-02-19 | 2014-07-21 | 17.0066
WA Parish Addition | Gas | 2012-12-07 | 2013-06-26 | 6.6118
Spinning Spur Wind Two | Wind | 2013-02-27 | 2014-06-19 | 15.6908
Logans Gap Wind I | Wind | 2013-12-11 | 2015-09-30 | 21.6447
Longhorn North | Wind | 2012-12-10 | 2015-09-21 | 33.3882
OCI Alamo 4 (Brackettville / ECLIPSE) | Solar | 2014-01-07 | 2014-08-28 | 7.6645
South Plains I | Wind | 2014-01-02 | 2015-11-13 | 22.3684
Los Vientos III | Wind | 2013-10-18 | 2015-12-28 | 26.3487
Javelina Wind | Wind | 2014-10-07 | 2015-12-23 | 14.5395
Windthorst 2 | Wind | 2013-08-15 | 2014-12-11 | 15.8882
Panhandle Wind 1 | Wind | 2012-12-19 | 2014-06-27 | 18.2566
Panhandle Wind 2 | Wind | 2013-10-02 | 2014-11-11 | 13.3224
Route 66 Wind | Wind | 2013-10-31 | 2015-08-11 | 21.3487
Ector County Energy Center G | Gas | 2014-01-17 | 2015-09-28 | 20.3618
Bryan Solar | Solar | 2011-12-28 | 2013-06-19 | 17.7303
Elk 2 | Gas | 2013-12-13 | 2016-06-07 | 29.8355
Elk 3 | Gas | 2013-12-13 | 2016-06-07 | 29.8355
Spinning Spur W 3 | Wind | 2013-12-20 | 2015-10-13 | 21.7763
Downie Ranch Solar | Solar | 2014-05-29 | 2015-12-22 | 18.8158
Keechi Wind 138 kV Joplin | Wind | 2013-11-08 | 2015-01-23 | 14.5066
South Plains II Phase a | Wind | 2014-01-02 | 2016-06-08 | 29.2105
Lamar Power Upgrade | Gas | 2014-04-22 | 2016-04-25 | 24.1447
Jumbo Road Wind | Wind | 2013-06-10 | 2015-04-09 | 21.9737
Sandow Unit 5 | Coal | 2009-04-27 | 2014-12-29 | 68.1579
Briscoe Wind | Wind | 2014-01-10 | 2015-11-13 | 22.1053
Stephens Ranch Wind B | Wind | 2014-07-21 | 2015-05-21 | 10
Colbeck's Corner W | Wind | 2012-10-24 | 2016-05-18 | 42.8289
South Plains II Phase b | Wind | 2014-01-02 | 2016-06-08 | 29.2105
Formulas:
Months from IA Signed to Commercial = DAYS([Commissioning Part 3 Commercial Approval],[IA Signed])/30.4