## Slide 1
Energy Storage Initiative
Strategy & Timeline
Sandip Sharma
BESTF
October 18, 2019

## Slide 2: Acronyms
CLR – Controllable Load Resource
MMS – Market Management System
EMS – Energy Management System
GR – Generation Resource
ESR – Energy Storage Resource
NMMS – Network Model Management System
RARF – Resource Asset Registration Form
RIOO – Resource Integration and On-Going Operations

## Slide 3: ERCOT Evolution for Battery Energy Storage Resources
Registration
(RARF or RIOO)
Siebel, NMMS, EMS, MMS, Settlements
Phase
A
GR
GR
CLR
CLR
Today
C
Single
Resource
Single
Resource
EMS Upgrade + RTC Go-Live
Mark the GR and CLR so that it can be seen they are a pair
ESR
ESR
ESR
ESR
B
By Dec 31, 2020
Single
Resource
GR
ESR
CLR
ESR

## Slide 4: Energy Storage Roadmap
September 2019
2020
Jan 1, 2021
2024
Combination model for ES
Single-Model ES Improvement NPRRs
Combination model
NPRRs
Single Model NPRR Approved
Single-unit model for ES
Implementation
Implementation Goal
RTC and EMS 3.3 Go-Live
File Single Model NPRR
MMS Change Freeze
EMS/MMS Change Freeze
These include NPRRs 963 and 967, as well as several ERCOT-sponsored NPRRs under development

## Slide 5
Review Process for BESTF and TAC
Kenneth Ragsdale

## Slide 6: Distribution Generation Resources (DGR) and Distributed Energy Storage Resources (DESR)
DGR/DESR issues identified in the market notice will be addressed at the workshop and not at the BESTF.
A Market Notice is currently in effect for Distribution Generation Resources (DGRs). The notice also applies to Distribution Energy Storage Resources (DESRs) : http://www.ercot.com/services/comm/mkt_notices/archives/4288
ERCOT Stakeholders have requested that this topic be addressed at the October TAC meeting and that a workshop be scheduled.
  Workshop is tentatively scheduled for the afternoon of either November 4 or 5.

## Slide 7: Key Milestones
File key NPRRs needed to sustain/improve the current “combo model”: (before the end of Q1 2020)
File NPRRs related to Single Model (and RTC): (before the end of Q1 2020)
Single Model (and RTC) NPRRs BOD approved: (before January 1, 2021)
Start discussion on the integration of hybrid (battery and a Gas Turbine), and DC-coupled (battery and solar behind the inverter) resources: (early January 2020)
Identify solutions (NPRRs, system changes etc.) for hybrids: (before the end of Q2 2020)

## Slide 8: Discussion on charter with the group
Review process:
  Initially ERCOT will bring forward proposals on key topics and concepts as they are developed
  Market Participants will be asked to review and provide feedback on the proposals
  ERCOT will work collaboratively to refine and develop the final key recommendations to be taken to TAC
For non-consensus recommendations, the BESTF Chair will communicate those issues and alternate options to TAC for further consideration and possible vote.
BESTF will report to TAC on those items which are deemed to be beyond the scope of the task force.

## Slide 9: TAC Review Process
TAC serves as the stakeholder body to vote on Policy recommendations from the BESTF
  Policy recommendations narrow the scope and operational and market design decisions to set direction for ERCOT in developing NPRRs upon completion of the Policy recommendations.
  Templates are being used to capture the key dates of review, any significant contention or modifications, and the TAC vote.
BESTF Policy recommendations are non-binding and will not go directly to the Board after TAC consideration.
  Procedures set forth in Protocol Section 21 do not apply to discussions, opinions or approvals by TAC with respect to BESTF Policy recommendations.
  Section VIII of the ERCOT Board Policies and Procedures does not apply to discussions, opinions or unofficial approvals by TAC with respect to BESTF Policy recommendations.
ERCOT will group TAC approved BESTF policy recommendations and file ERCOT sponsored NPRRs on an ongoing basis to address the recommendations.
  ERCOT will maintain TAC reviewed BESTF Policy recommendations in template form and post in a central location.

## Slide 10: BESTF Review Process
Internal ERCOT draft policy recommendations and recommendation concepts (elements)
ERCOT presents recommendations for meeting in presentation format
ERCOT takes feedback and posts in 2 days as initial document for MP edits
MPs submit feedback as edits to document and any
- Concerns
Alternatives
MPs share initial feedback, concern, request for additional information
MPs must document concerns and alternative approach prior to meeting, and be prepared to discuss
ERCOT provides responses to finalize supporting policy recommendations
Meeting #1 Meeting #2 Meeting #3
Take consensus and non-consensus items to TAC for vote
ERCOT posts all MP feedback and responds to MP redlines, concerns, alternatives. Issues that have broad consensus may go to TAC for approval following second discussion

## Slide 11: Review Process for BESTF, and TAC
At BESTF: Develop policy recommendations and scope
At TAC: Vote on policy recommendations and scope
Status updates to TAC and seek endorsement of incremental recommendations and scope
ERCOT sponsored NPRRs, following TAC’s approval of BESTF recommendations.

## Slide 12: Communications
ERCOT has established a dedicated web page for the Task Force under TAC
Sign up for email list: http://lists.ercot.com/
  Scroll down to BEST
  Click subscribe
  Email confirmation process to verify
  If assistance needed, email Helpdesk@ercot.com
While there are numerous ERCOT team members, primary ERCOT points of contact are Sandip Sharma (Sandip.sharma@ercot.com ) and Kenneth Ragsdale (Kenneth.Ragsdale@ercot.com ).

## Slide 13: Questions