## ImprovementCostSummary06102024
| Project Cost |  |  |  |  | XFMR MVA
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total
2023 | 804773000 | 1338626414 | 243978000 | 2387377414 | 2023 | 4560 | 330 | 0 | 4890 | For ROS and BOD Reports
2024 | 1127962000 | 2475754052 | 574437577.09 | 4178153629.09 | 2024 | 7550 | 977.8 | -300 | 8227.8 | ·All Projects (in engineering, routing, licensing and construction): |  |  |  | 14183567312
2025 | 1692900000 | 1973844674 | 461542000 | 4128286674 | 2025 | 7300 | 300 | 320 | 7920 | ·Transmission Projects Energized in 2024: |  |  |  | 2160892629.09
2026 | 3155310638 | 1681314000 | 15000000 | 4851624638 | 2026 | 5550 | 260 | 0 | 5810
2027 | 758996000 | 472658000 | 347609000 | 1579263000 | 2027 | 1200 | 810 | 0 | 2010
2028 | 643120000 | 257474000 | 244337000 | 1144931000 | 2028 | 1350 | 0 | 0 | 1350
2029 | 0 | 160255000 | 108853000 | 269108000 | 2029 | 0 | 0 | 0 | 0
2030+ | 0 | 179460000 | 13633000 | 193093000 | 2030+ | 0 | 0 | 0 | 0
2024COM | 448968000 | 1309311052 | 402613577.09 | 2160892629.09 | 2024COM | 2300 | 720.8 | -400 | 2620.8
2024PLAN | 678994000 | 1166443000 | 171824000 | 2017261000 | 2024PLAN | 5250 | 257 | 100 | 5607
2023-2030+ | 8183061638 | 8539386140 | 2009389577.09 | 18731837355.09 | 2023-2030+ | 27510 | 2677.8 | 20 | 30207.8
2023-2024 | 1932735000 | 3814380466 | 818415577.09 | 6565531043.09 | 2023-2024 | 12110 | 1307.8 | -300 | 13117.8
2025-2030+ | 6250326638 | 4725005674 | 1190974000 | 12166306312 | 2025-2030+ | 15400 | 1370 | 320 | 17090
| Circuit Miles New |  |  |  | Circuit Miles Rebuilt, Reconductored or Upgraded |  |  |  |  | Total
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total | 345 | 138 | 69 | Total
2023 | 228.641 | 60.22 | 19.5 | 308.361 | 2023 | 32.92 | 311.031 | 74.36 | 418.311 | 261.561 | 371.251 | 93.86 | 726.672
2024 | 190.84 | 157.084 | 9.8 | 357.724 | 2024 | 22.9 | 887.22 | 246.19 | 1156.31 | 213.74 | 1044.304 | 255.99 | 1514.034
2025 | 53.2 | 118.3 | 1.33 | 172.83 | 2025 | 103.17 | 356.48 | 292.01 | 751.66 | 156.37 | 474.78 | 293.34 | 924.49
2026 | 644.47 | 77.9 | 3 | 725.37 | 2026 | 209.27 | 561.6 | 0 | 770.87 | 853.74 | 639.5 | 3 | 1496.24
2027 | 14.17 | 23.32 | 13.1 | 50.59 | 2027 | 97.7 | 193.06 | 187.091 | 477.851 | 111.87 | 216.38 | 200.191 | 528.441
2028 | 46 | 16.44 | 0 | 62.44 | 2028 | 247 | 122.848 | 144.18 | 514.028 | 293 | 139.288 | 144.18 | 576.468
2029 | 0 | 0.1 | 2 | 2.1 | 2029 | 0 | 76.87 | 71.92 | 148.79 | 0 | 76.97 | 73.92 | 150.89
2030+ | 0 | 16.4 | 0 | 16.4 | 2030+ | 0 | 126.18 | 2 | 128.18 | 0 | 142.58 | 2 | 144.58
2024COM | 116.34 | 79.84 | 3.8 | 199.98 | 2024COM | 3.9 | 450.67 | 141.01 | 595.58 | 120.24 | 530.51 | 144.81 | 795.56
2024PLAN | 74.5 | 77.244 | 6 | 157.744 | 2024PLAN | 19 | 436.55 | 105.18 | 560.73 | 93.5 | 513.794 | 111.18 | 718.474
2023-2030+ | 1177.321 | 469.764 | 48.73 | 1695.815 | 2023-2030+ | 712.96 | 2635.289 | 1017.751 | 4366 | 1890.281 | 3105.053 | 1066.481 | 6061.815
2023-2024 | 419.481 | 217.304 | 29.3 | 666.085 | 2023-2024 | 55.82 | 1198.251 | 320.55 | 1574.621
2025-2030+ | 757.84 | 252.46 | 19.43 | 1029.73 | 2025-2030+ | 657.14 | 1437.038 | 697.201 | 2791.379

## FutureTPIT060124NoCost
JUNE BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 6/1/2024
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
75518 | Rising Star Area Conversions |  |  | Carlton Switch | Carlton (298) | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-06-10 |  | 69 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 297, 298, 299 | Y |  |  | 0 | 75519 | 75518
66216 | Upgrade and convert Waco West - Temple 69 kV Line to 138 kV | Upgrade and convert Waco West - Temple 69 kV Line to 138 kV |  | Waco West | Temple | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6191 | 2024-06-15 |  | 138 | 0.7 | 6.7 | 0 |  | McLennan | Bell | Tier 4 | 22RPG046 | 2022-12-01 | 2023-01-01 |  | 147, 3361, 3417, 3437, 3446, 3544, 3578, 3580, 3581, 13436, 3644, 13662 | Y |  |  | 0 | 67582 | 66216
66522 | Andrews North - Paul Davis Tap 138 kV Line Rebuild | Add Andrews North - Paul Davis Tap 138 kV Line Rebuild |  | Andrews North | Paul Davis Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8596 | 2024-06-15 |  | 138 | 0 | 25 | 0 |  | Andrews | Dawson | Tier 4 | 21RPG012 | 2021-08-03 | 2021-08-26 |  | 1167, 1159, 1168 | Y |  |  | 0 | 76409 | 66522
71901 | Install 110.4 Mvar 138 kV capacitor bank at Thorndale North | Install 110.4 Mvar 138 kV capacitor bank at Thorndale North |  | Thorndale North | Thorndale North | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6236 | 2024-06-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Milam | Milam | Tier 4 |  |  |  |  | 3659 | Y |  |  | 0 | 71902 | 71901
72586 | Seward Junction capacitor bank addition | Install 31.3 Mvar capacitor bank at Seward Junction. Replaces ERCOT Project # 70361. |  | Seward Junction |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-06-15 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson |  | Tier 4 |  |  |  |  | 70524 | Y | Y |  | 0 | 72587 | 72586
71873 | CPSE_Hill Country Auto# 2 Impedance Upgrade |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2024-06-20 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2022-07-09 |  | 5211, 5210, 5213 | Y |  |  | 0 | 71874 | 71873
60625 | AEN_22TPIT60625_DECKER_BUS_TIE_CLOSE | Close the Decker 138 kV bus tie |  | 9187 | 9188 |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-06-21 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 | [5 empty] | Y | N |  | 0 | 60626 | 60625
61350 | Antler-Highway 46 Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the T610 Antler to Highway 46 138-kV and T389 Bergheim to Hays Energy 345-kV 10.4-mile double-circuit transmission line by replacing the aging conductors from Antler to Highway 46 substations. |  | Antler | Highway 46 | Planned | 61406, 61358, 61392, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-06-21 |  | 345 | 0 | 10.4 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7171, 7770, 7043, 7177 | Y | N |  | 0 | 78332 | 61350
52670 | Rising Star Area voltage conversion | This portion of the project connects Green Creek Switch |  | Stephenville | Carlton Switch | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-06-24 |  | 138 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 286, 33286, 294 | Y |  |  | 0 | 52671 | 52670
18TPIT0001 | Wiederstein Substation Transformer Replacement | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Wiederstein |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2024-06-28 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7461 | Y | N |  |  | 10675 | 3319
61230 | Altair - Garwood Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 9.4-mile Altair ¿ Garwood (T542) (including all the tap lines) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Altair | Garwood | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-06-28 |  | 69 | 0 | 0 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  |  | 78106, 78530 | Y | N |  | 0 | 61231 | 61230
50948 | Angstrom - Grissom: Build New Line | Angstrom - Grissom: Build New Line | In-Service Date Update | Angstrom | Grissom | Planned | 1063 - 1236 | AEP TCC | Teresa Trotman mlforcum@aep.com 918-599-2674 | 3797 | 2024-06-30 |  | 345 | 17 | 0 | 0 |  | San Patricio | Bee | Tier 1 | 19RPG0016 | 2023-10-19 | 2023-05-20 | 2023-06-20 | 8249, 8624 | Y | N |  | 0 | 50949 | 50948
61513 | New RELLIS Substation |  |  | Steele Store | Smetana | Under Construction |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2024-06-30 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32780, 32852, 32853 | Y |  |  | 0 | 80552 | 61513
70192 | LCRATSC_Doss_Headwaters_TL_Overhaul | LCRA TSC will perform an overhaul on the 14.2-mile Doss ¿ Headwaters (T508) 69-kV transmission line. |  | Doss | Headwaters | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org +151-257-84514 |  | 2024-06-30 |  | 69 | 0 | 14.2 | 0 |  | Gillespie | Gillespie | Tier 4 |  |  |  |  | 7408, 7410 | Y | Y |  | 0 | 70193 | 70192
11TPIT0008 | RAINEY_ST 138kV substation | Establish a new 138kV Rainey St. Substation with (2) 50MVA transformers and cut into existing Ckt 1015 (Pedernales to Seaholm). |  | Rainey St Substation | Rainey St Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P158 PLAN_117_P166 PLAN_117_P167 | 2024-07-01 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9261, 9118, 9132 | Y | N |  |  | 8208 | 1032
5430N | Conversion to 138kV | Construct a new 138kV Eagle substation along the 138kV Hickory - Locust line |  | Eagle |  | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 926 | Y | N | N/A | 0 | 55208 | 5430
66120 | Rebuild Freeway Park-Dickinson with bundled 795 ACSS |  |  | Freeway Park (bus # 38820) | Dickinson (bus # 38820) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-07-01 |  | 138 | 0 | 6.25 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38820, 38850 | Y |  |  | 0 | 66121 | 66120
75520 | Rising Star Area Conversions |  |  | Green Creek | Carlton | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-07-10 |  | 69 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 298, 299, 33286 | Y |  |  | 0 | 75521 | 75520
49572 | Goodlett to Quanah: Build a new portion of 69 kV line | Build new section of 69 kV line between Goodlett and Quanah | TSP/Company Contact Update | Goodlett | Quanah | Planned | 1022 - 1200 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 2784 | 2024-07-15 |  | 69 | 6 | 0 | 0 |  | Hardeman |  | Tier 2 | 19RPG020 | 2019-11-01 | 2020-01-01 |  | 6052, 6051, 60446 | Y | N |  | 0 | 49573 | 49572
70742 | Pleak 35kV Distribution Substation | Install new Pleak (PLK) 138/35kV Distribution Substation. Loop from existing Ckt.89A to create new Ckt.89 Big Creek to Pleak to Fort Bend. Convert Needville to a breakered substation. |  | Pleak | Big Creek/Fort Bend | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-07-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42380, 44680, 42370, 42390, 44280 | Y | N |  | 0 | 70743 | 70742
70777 | Bunsen: Install Cap Bank | Bunsen Capacitor | In-Service Date Update | Bunsen |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022722 | 2024-07-31 |  | 138 | 0 | 0 | 0 | 0,15.4 | Nueces |  | Tier 4 |  |  |  |  | 8459 | Y |  |  | 0 | 70778 | 70777
78457 | Pledger Distibution Substation | Rebuild Pledger distribution substation from tap to loop-tap service. |  | Pledger |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-07-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43120, 43121, 48281, 43110, 43340 | Y | N |  | 0 | 80967 | 78457
52179 | Rising Star Area Conversions | This converts Hasse to Downing to 138 KV |  | Downing | Hasse | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-08-10 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 278, 33281, 277, 281, 1649 | Y |  |  | 0 | 52180 | 52179
75522 | Rising Star Area Conversions |  |  | Stephenville | Stephenville | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-08-10 |  | 138 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 299, 286, 295 | Y |  |  | 0 | 75523 | 75522
78683B | POI for Connolly Storage (Denton Creek Switch) | Establish Denton Creek Switch tie line to Connolly storage |  | Bennett Road Switch | Krum Tap Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3500 | 2024-08-16 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 1510, 154272 | Y |  |  | 0 | 79646 | 78683
48774 | Fincas: Build new 138Â kV distribution station | Build new distribution station on the University to Wormser 138 kV line | Estimated Cost Update | Fincas |  | Planned | 1026 - 1204 | AEP | Travis Coody mlforcum@aep.com 918-599-2674 | 3765 | 2024-08-30 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8039, 8649, 8653 | Y | N |  | 0 | 81145 | 48774
57750 | Seabrook 138kV Distribution Substation | Build new 138kV Seabrook distribution substation. Double tap from Ckt.79F PH Robinson to Hanna and Ckt.96A PH Robinson to Bayou. |  | Seabrook |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-08-30 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42852, 42853, 48282, 48283, 42160, 42780 | Y | N |  | 0 | 57751 | 57750
76618 | Expand 345kV Refuge substation for Peyton Creek Wind II (20INR0155) | Expand 345kV Refuge substation for Peyton Creek Wind II (20INR0155) |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-08-31 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | 0 | 76619 | 76618
63497 | Bakersfield to Cedar Canyon 2nd circuit | Add the 2nd circuit to CREZ Bakersfield to Cedar Canyon 345 kV line |  | Bakersfield | Cedar Canyon | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-09-01 |  | 345 | 21.1 | 0 | 0 |  | Pecos | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76002, 76015 | Y | N |  |  | 63498 | 63497
61138 | Bergstrom Sub Cap Addition | Add a 31.2 MVAR Cap Bank at the Bergstrom Substation |  | Bergstrom | Bergstrom | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-09-13 |  | 138 | 0 | 0 | 0 | 0,31.2 | Travis | Travis | Tier 4 |  |  |  |  | 9165 | Y |  |  | 0 | 61139 | 61138
45693 | Rocky Road - Stiles 138 kV Line | Upgrade the existing 138 kV line |  | Rocky Road | Stiles | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8599 | 2024-09-15 |  | 138 | 0 | 6.6 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  |  | 23864, 23868 | Y |  |  | 0 | 71171 | 45693
66200B | Upgrade Taylor - Holland 69 kV Line | Rebuild the Bartlett Tap - Bartlett 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6173 | 2024-09-15 |  | 69 | 0 | 5.3 | 0 |  | Bell | Williamson | Tier 4 | 22RPG036 |  |  |  | 3647, 13647 | Y |  |  | 0 | 71895 | 66200
77622 | Pacific Switch Sw (Baker Branch Solar) |  |  | Paris | Valley | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5323 | 2024-09-15 |  | 345 | 0 | 0 | 0 |  | Lamar | Fannin | Tier 4 |  |  |  |  | 11683, 144565 | Y | N |  | 0 | 77623 | 77622
73338A | Pythias (PYT) 138kV CNP Station for Second Division Solar (20INR0248) | Loop new CNP 138kV substation Pythias (PYT) into Ckt.60H to create new Ckt.60 San Bernard to Pythias to West Columbia. |  | Pythias | San Bernard/ West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-09-16 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43090, 43110, 43380 | Y | N |  | 0 | 73339 | 73338
73338B | Pythias (PYT) 138kV CNP Station for Second Division Solar (20INR0248) | Install one generator lead for new interconnection to DAMAZO / Second Division Solar |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-09-16 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 73342 | 73338
77035 | New Mathis Substation | Remove Mathis substation, construct new Mathis substation |  | Mathis |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | DP20X0003 | 2024-09-21 |  | 69 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8407, 8671, 5666, 5668, 8107, 8424 | Y |  |  | 0 | 77036 | 77035
59093 | Starr Solar Connection | Starr Solar Connection | In-Service Date Update | Roma Tap |  | Under Construction |  | AEP TCC | William Lovelace mlforcum@aep.com 918-599-2674 | TP2020209 | 2024-09-30 |  | 138 | 0.1 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 88795, 8795 | Y |  |  | 0 | 59094 | 59093
76369 | BRINE Substation Upgrades | Upgrade substation equipment at BRINE on Ckt.86H DALTON to BRINE to Mont Belvieu. |  | BRINE | DALTON/Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-09-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40220, 40740 | Y | N |  | 0 | 76370 | 76369
78425 | Danbury to LONG / Longbow BESS (25INR0328) | Expand facilities at customer-owned LONG substation for Longbow BESS (25INR0328). Utilize existing generator lead LONG to Longbow Solar. |  | Danbury | LONG | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-09-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 78426 | 78425
75567 | Create_Magness_Bus |  |  |  |  | Planned |  | RYBRN | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2024-10-01 |  | 138 | 0 | 0 | 0 |  | Hunt | Hunt | Tier 4 |  |  |  |  | 6817, 6879, 6883 | Y |  |  | 0 | 75568 | 75567
76694 | Calmont 69 kV line rebuild | Calmont 69 kV line rebuild |  | Calmont | Calmont | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5137 | 2024-10-01 |  | 69 | 0 | 2.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 11956, 12089 | Y |  |  | 0 | 76695 | 76694
61932B | Holliday - Seymour 69 kV Line | Re-terminate line into new bay at Seymour Switch |  | Holliday | Seymour | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4028 | 2024-10-15 |  | 69 | 0 | 0 | 0 |  | Archer | Baylor | Tier 3 | 21RPG007 | 2021-04-26 | 2021-05-18 |  | 1527, 1532, 1530, 1534 | Y |  |  | 0 | 73028 | 61932
62643 | Rebuild Waco East 138 kV Switch | Rebuild Waco East 138 kV Switch |  | Waco East | Waco East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6146 | 2024-10-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3481, 3482, 3438, 3434, 3443, 3452, 3551, 3559, 3708, 3439, 13438 | Y |  |  | 0 | 62664 | 62643
67919 | Avanzada: Construct New 345 kV Station | Interconnect Outpost Solar to the Lobo to Fowlerton 345 kV line | Project Title, Project Description, Transmission Status, and Transmission Owner Update | Avanzada |  | Under Construction |  | ETT TCC | Adam Wells mlforcum@aep.com 918-599-2674 |  | 2024-10-15 |  | 345 | 0.1 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80235, 5709, 80219 | Y |  |  | 0 | 67920 | 67919
11TPIT0011 | East_Village138kV Substation | East_Village 138kV Substation |  | Techridge | East_Village SUB |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-10-18 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9195, 9045, 9190 | Y |  |  |  | 13043 | 5357
48327 | Reconductor 138kV ckt 972 Howard Lane to McNeil to 3000A. |  |  | 9079 | 9217 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinene (512) 322-6740 |  | 2024-10-18 |  | 138 | 0 | 2.81 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9079, 9217 | Y |  |  | 0 | 48328 | 48327
61358 | Highway 46-River Oaks Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T518 Highway 46 to River Oaks 138-kV and T389 Bergheim to Hays Energy 345-kV 8.6-mile double-circuit transmission line by replacing the aging conductor. Project ID 61356 captures the T389 Bergheim - Hays Energy 345-kV conductor upgrade for modeling purposes. |  | Highway 46 | River Oaks | Planned | 61406, 61392, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-10-25 |  | 345 | 0 | 8.6 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7043, 7173, 7177, 7770 | Y | N |  | 0 | 78326 | 61358
49574 | Tesla: Build 345 kV terminal | Interconnect Misae II solar farm at Tesla |  | Tesla |  | Planned | 1023 - 1201 | ETT TNC | Raza Ansari mlforcum@aep.com 918-599-2674 | 2785 | 2024-10-30 |  | 345 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501 | Y | N |  | 0 | 49575 | 49574
66221L | Galena Park Area Conversion Project | De-energize Ckt.20 Greens Bayou to GYPSUM. |  | Greens Bayou | GYPSUM | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-30 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40619, 40751, 40725 | Y | N |  | 0 | 80626 | 66221
72213 | Cedar Hill: Upgrade Relays | Upgrade Relay at the Sterling City terminal and Miles terminal at Cedar Hill station | Schedule Update | Cedar Hill |  | Planned |  | AEP TNC | Douglas Jansen twang1@aep.com 918-599-2635 | TP2022739 | 2024-10-30 |  | 69 | 0 | 0 | 0 |  | Lee |  | Tier 4 |  |  |  |  | 6422, 6423, 6431 | Y | N |  | 0 | 72214 | 72213
69283 | Naismith to Resnik: Build New 138 kV Line | Build New 138 kV Line from Naismith to Resnik | Schedule, Cost Update | Naismith | Resnik | Planned | 1063 - 1236 | AEP TCC | Thomas Reynolds mlforcum@aep.com 918-599-2674 | TP2017032 | 2024-10-30 12:00 |  | 138 | 3 | 0 | 0 |  | San Patricio | San Patricio | Tier 1 | 19RPG0016 | 2019-10-07 | 2020-05-19 | 2020-06-15 | 8660, 8674, 8580 | Y | N |  | 0 | 69284 | 69283
3297 | Tezel Road - New 138kV Substation | Loop new 138 kV substation into the existing 138 kV Helotes to Bandera line. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2024-10-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5421, 5020, 5200 | Y |  |  | There are no transformers associated with this project | 10840 | 3297
6373 | Hamilton Road to Picacho Ckt #2: Rebuild 138 kV Line | Rebuild Hamilton Road to Picacho 138 kV line ckt #2 | Project Title Update | Hamilton Road | Picacho | Planned | 870-1051 | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 | 3660 | 2024-10-31 |  | 138 | 0 | 8.4 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8186, 8255, 8690, 8688, 8684 | Y | N |  | 0 | 65505 | 6373
55873 | Upgrade Moore to Hondo Creek 138 kV line | Replace the 336 ACSR with 1020 ACCC conductor while keeping the existing structures that still meet our standards. |  | Moore | Hondo Creek | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-10-31 |  | 138 | 0 | 13.5 | 0 |  | Medina | Frio | Tier 2 | 19RPG021 | 2019-11-20 | 2020-05-21 |  | 5819, 5827 | Y | N | Field engineering is still occurring due to short timeline for this upgrade. Details may change. | Current plan is to upgrade the line using mostly existing structures. Detailed field engineering is underway and could change the plan. | 55874 | 55873
66130 | North Shore Reactive Project | Install 57.6 Mvar Capacitor Banks at Hecker and Resnik 138 kV stations. | In-Service Date Update | Hecker | Resnik | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2021207 | 2024-10-31 |  | 138 | 0 | 0 | 0 | 0,69.2 | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8565, 8580 | Y |  |  | 0 | 66131 | 66130
69281 | Angstrom to Naismith: Build New 345 kV Line | Build New 345 kV Line from Angstrom to Naismith | Transmission Status and In-Service Date Update | Angstrom | Naismith | Under Construction | TP2020205 | AEP TCC | William Lovelace mlforcum@aep.com 918-599-2674 |  | 2024-10-31 |  | 345 | 19 | 0 | 0 |  | San Patricio | San Patricio | Tier 1 | 19RPG0016 | 2019-10-07 | 2020-05-19 | 2020-06-15 | 8249, 8659 | Y | N |  | 0 | 69282 | 69281
69902B | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. | Upgrade Ckt.71C TH Wharton to Zenith in order to increase thermal limits |  | TH Wharton | Zenith | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45500, 44900 | Y | N |  | 0 | 78231 | 69902
73057 | Tulsita Solar Interconnection | Interconnect Tulsita Solar at new Basil 138 kV station |  | Basil |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2024-10-31 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8731, 8162, 8590, 8595 | Y |  |  | 0 | 73058 | 73057
75628 | Poetry 345 kV Switch | Establish Poetry 345 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3228 | 2024-10-31 |  | 345 | 0 | 0 | 0 |  | Kaufman |  | Tier 4 |  |  |  |  | 2485, 2478, 3103 | Y |  |  | 0 | 75629 | 75628
78464 | Refuge 345kV Substation Expansion for Peyton Creek Wind II (20INR0155) | Expand 345kV Refuge substation for Peyton Creek Wind II (20INR0155) |  | Refuge |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-31 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | 0 | 78465 | 78464
57549A | Garden Villas 138kV Load Conversion | Reposition existing Garden Villas dual-voltage transformers TR1/TR2. Reposition one of the transformers with Ckt.06G Garden Villas to Drouet and rename transformer as TR4. |  | Garden Villas | Drouet | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42680, 42690 | Y | N |  | 0 | 79860 | 57549
57549B | Garden Villas 138kV Load Conversion | Reposition existing Garden Villas dual-voltage transformers TR1/TR2. Reposition one of the transformers with Ckt.07A Garden Villas to Chocolate Bayou tap and rename transformer as TR3. |  | Garden Villas | Chocolate Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42680, 42690, 42042, 42681, 42683 | Y | N |  | Cost included in main project | 79859 | 57549
61232 | RGEC Persimmon Gap Substation 69-kV Transmission Line Extension and Substation Expansion | Extend Alpine-Persimmon Gap 69-kV Transmission Line at Switch# 6669 and Install Circuit Switcher to accommodate new substation power transformer and distribution bays. New power transformer capacity will be 12/16/20 MVA. | Scheduled RUS Construction Work Plan Project | Persimmon Gap | Persimmon Gap | Planned |  | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2024-11-01 |  | 69 | 0 | 0 | 0 |  | Brewster | Brewster | Tier 4 | [5 empty] | Y | N |  | 0 | 61233 | 61232
68254 | Friend Ranch: Build new 138 kV Terminal | Interconnect Blue Sky Solar to the Friend Ranch 138 kV Station | Schedule Update | Friend Ranch |  | Planned |  | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 |  | 2024-11-01 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 | [5 empty] | Y | N |  | 0 | 68255 | 68254
51010 | Heron to Ollin: Rebuild and convert to 138 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | TSP/ Company Contact Update | Heron | Ollin | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2798 | 2024-11-15 |  | 138 | 0 | 2 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60448, 60441 | Y | N |  | 0 | 51011 | 51010
52728 | Add Foundry 138 kV Switch | Oncor's portion of AEP's Crane Area Transmission Project |  | LCRA Arco Crane | Navajo Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8502 | 2024-11-15 |  | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  | 2019-06-01 | 2019-07-22 |  | 10002, 11202, 60448, 71199 | Y |  |  | 0 | 52730 | 52728
73025 | CPSE_New_Shaula_POI | [6 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2024-11-21 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5380, 5133, 5915 | Y |  |  | 0 | 73026 | 73025
50843 | Heron: Build 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | TSP/Company Contact Update | Heron |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2796 | 2024-11-22 |  | 138 | 0 | 0 | 90 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60447, 60448, 6610, 6611, 6614 | Y | N |  | 0 | 50844 | 50843
73050 | LCRATSC_JohnDumas_Substation_Addition | Substation addition to provide point interconnection for a new power plant. |  | John Dumas |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org (512) 578-4514 |  | 2024-11-25 |  | 345 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7041, 7047, 7050 | Y | N |  | 0 | 73051 | 73050
6216 | Bartlett Switch to Bartlett | Bartlett Switch to Bartlett |  | Bartlett Switch | Bartlett | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-11-28 12:00 |  | 69 | 0 | 2.7 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 114, 118 | Y |  |  |  | 13941 | 6216
6749 | Rosata: Build 138kV Substation | Build new Rosata 138kV POD Switch on Coleto Creek to Kenedy 138kV Line | In-Service Date Update | Rosata |  | Planned | 898 - 1076 | AEP TCC | James Lutz bcogan@aep.com 918-599-2857 | 3682 | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8153, 88153, 7241, 8162, 8186 | Y | Y |  |  | 14542 | 6749
50966 | Naismith: Build 345/138 kV Station | Build new 345/138 kV station with two autotransformers | In-Service Date and Estimated Cost Update | Naismith |  | Planned | 1063 - 1236 | AEP TCC | Thomas Reynolds mlforcum@aep.com 918-599-2674 | TP2017032 | 2024-11-30 |  | 345 | 0 | 0 | 1350 |  | San Patricio |  | Tier 1 | 19RPG0016 | 2019-10-07 | 2020-05-19 | 2020-06-15 | 8659, 8660, 8674 | Y | N |  | 0 | 69279 | 50966
57797 | Athey: Build 138 kV Station | Build new 138 kV Station on the Ft Stockton to Rio Pecos 138 kV line |  | Athey |  | Under Construction | 1109 - 1287 | AEP TNC | Shawn Ketcher twang1@aep.com 918-599-2635 | 1866 | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60792, 60718, 60798 | Y | N |  | 0 | 65578 | 57797
57906 | Laredo to University: Rebuild 138 kV Line | Reconductor Laredo to Del Mar 138 kV Line | Project Description, Schedule, Trans Circuit Miles Update | Laredo | University | Planned | 1119 - 1297 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3838 | 2024-11-30 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645, 8647 | Y | N |  | 0 | 65579 | 57906
63635 | Tribute: Build 138 kV Station | Build new 138 kV Station on the San Angelo Power to Red Creek 138 kV line | In-Service Date Update | Tribute |  | Planned | 1132 - 1310 | AEP TNC | Larry Brown twang1@aep.com 918-599-2635 | 1877 | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 60008, 6442, 6473 | Y | N |  | 0 | 63636 | 63635
69463 | Gulch: Construct new 345 kV Station | Arroyo Solar Interconnect | In-Service Date Update | Gulch |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-11-30 |  | 345 | 0.1 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8704, 8705, 8317, 8318 | Y |  |  | 0 | 70802 | 69463
70704 | LCRATSC_Florence_Substation_Addition | Add new three terminal ring bus substation to 138 kV line between Andice and Glasscock and install 46.7 MVA distribution transformer. The new substation will be located approximately 4.87 miles from Glasscock substation. |  | Andice | Glasscock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org (512) 578-4514 |  | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7521, 70522, 7523 | Y | N |  | 0 | 70705 | 70704
71011 | Solstice: CT Removal | Remove CTs from Solstice station located along the Solstice to Sand Lake ONCOR and the Solstice to Bakersfield LCRA 345 kV double circuit lines | Estimated Cost Update | Solstice |  | Planned |  | AEP TNC | Chris Caroll twang1@aep.com 918-599-2635 |  | 2024-11-30 |  | 345 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 11098, 60404, 76002 | Y | N |  | 0 | 71012 | 71011
72042 | Oasis 345kV Substation Expansion for SMT Ironman BESS (24INR0265) | Expand 345kV Oasis substation for SMT Ironman BESS (24INR0265) |  | Oasis |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-11-30 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | 0 | 72043 | 72042
72053 | Oasis 345kV Substation Expansion for SOHO BESS (23INR0419) | Expand 345kV Oasis substation for SOHO BESS (23INR0419). Reposition existing Ckts. 18B and 27B Oasis to Dow and Ckt.99E Meadow to Oasis. |  | Oasis |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-11-30 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | 0 | 72054 | 72053
72500 | Rio Lago - New 138kV Substation | Loop new 138kV substation into the existing 138kV Bandera to Verde Creek line and install 40MVA distribution transformer. The new substation will be located approximately 1.64 miles from Bandera substation (23INR0078) |  | Bandera | Verde Creek | Planned |  | BEC | Jhonatan Guerrero Rivera j.rivera@banderaelectric. 830-612-0048 |  | 2024-11-30 |  | 138 | 0.1 | 0 | 0 |  | Bandera | Bandera | Tier 4 |  |  |  |  | 7436, 7146, 7438 | Y | N |  | 0 | 72501 | 72500
75930 | Expand Highlands substation with addition of 3rd distribution transformer. Transformer expected at Ckt.66F Garth to Highlands tap to Haney. |  |  | Highlands | Garth/Haney | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40812 | Y | N |  | 0 | 75931 | 75930
76080 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild Mines Road to North Laredo SW 138 kV line | In-Service Date and Estimated Cost Update | Mines Road | North Laredo | Planned | 1116 - 1294 | AEP TCC/ETT TCC | William Lovelace mlforcum@aep.com 918-599-2674 | 3835 | 2024-11-30 |  | 138 | 0 | 5.85 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8643, 8909 | Y |  |  | 0 | 76081 | 76080
76145 | Matador: Station Build | Build a new Matador station five breaker ring bus | TSP/Company Contact and In-Service Date Update | Matador |  | Planned |  | AEP TNC | Tong Wang twang@aep.com 918-599-2635 | TA2020140 | 2024-11-30 |  | 69 | 0 | 0 | 0 |  | Motley |  | Tier 4 |  |  |  |  | 6074, 6039, 6140, 6141 | Y | N |  | 0 | 76146 | 76145
78455 | Oasis 345kV Substation / SOHO BESS II (25INR0162) | Install SOHO BESS II at Oasis 345kV substation… Connect at the same generator lead as SOHO BESS (SOHO BESS II - 25INR0162) |  | Oasis |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-11-30 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 78456 | 78455
1205 | Planned reconductor from Hasse to Gustine | Planned reconductor from Hasse to Gustine |  | HASSE | GUSTINE | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-12-01 |  | 69 | 0 | 7.34 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 273, 277 | Y |  |  | 0 | 54001 | 1205
4645 | Rebuild of Myra to Spring | Rebuild of Myra to Spring |  | Myra | Spring | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-12-01 |  | 138 | 0 | 13.9 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 684, 690, 691 | Y |  |  |  | 12221 | 4645
66366 | Rebuild Brazoria - Retrieve 138kV with bundled 795 ACSS |  |  | TNMP Brazoria (bus # 39600) | CenterPoint Retrieve (bus # 43170) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-12-01 |  | 138 | 0 | 6.17 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39600, 43170 | Y |  |  | 0 | 66367 | 66366
70371 | D'Hanis Capacitor addition | Add 9.6 MVAR capacitor step at D'Hanis |  | D'Hanis |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-12-01 |  | 69 | 0 | 0 | 0 | 0,9.6 |  |  | Tier 4 |  |  |  |  | 5814 | Y | N |  | 0 | 70372 | 70371
70884 | Rebuild Rio Colorado - Bay City | Rebuild Rio Colorado - Bay City 795 ACSR |  | Rio Colorado | Bay City | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-12-01 |  | 69 | 0 | 9.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5560, 5563 | Y |  |  | 0 | 70885 | 70884
71954 | Adds new Talitha substation and short line from Talitha to Orange Grove 138 | Adds new Talitha substation and short line from Talitha to Orange Grove 138 |  | Orange Grove | Talitha | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-12-01 |  | 138 | 0.73 | 0 | 0 |  | Jim Wells | Jim Wells | Tier 4 |  |  |  |  | 5661, 5660 | Y |  |  | 0 | 71955 | 71954
71982 | Upgrade Orange Grove station | Upgrade Orange Grove stationto ring bus |  | Orange Grove | Orange Grove |  |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  | 0 | 71983 | 71982
45155 | Ollin: Build 138 kV station | Construct new Ollin 138 kV station | TSP/ Companny Contact Update | Ollin |  | Planned | 939 - 1117 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 2752 | 2024-12-01 01:00 |  | 138 | 0.1 | 0 | 0 |  | Crane |  | Tier 4 | 19RPG013 |  |  |  | 6600, 6605, 6606, 6668, 6669, 60428, 60429, 60432, 60441, 6604, 6610, 6613, 6607, 6611, 60431, 76615 | Y | N |  | 0 | 45156 | 45155
70354 | LCRATSC_WolfLane_Substation_Upgrade | Upgrade Wolf Lane Substation to a 3000 A, 138-kV ring bus arrangement. Contingency Update |  | Wolf Lane |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-12-10 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 | [5 empty] | Y | Y |  | 0 | 70355 | 70354
70351 | LCRATSC_Rattler_Redwood_TL_Upgrade | Upgrade T262 Rattler - Redwood 138-kV transmission line to obtain a higher operational rating. |  | Rattler | Redwood | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-12-13 |  | 138 | 0 | 1.07 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7184, 7188 | Y | N |  | 0 | 70352 | 70351
45511 | Laredo to Del Mar: 138 kV Line Rebuild | Rebuild Laredo to Del Mar 138 kV Line | Estimated Cost Update | Laredo | Del Mar | Planned | 992 - 1170 | AEP TCC | William Lovelace mlforcum@aep.com 918-599-2674 | 3746 | 2024-12-14 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645 | Y | N |  | 0 | 65531 | 45511
5436 | Morgan Creek - McDonald 138 kV Line | Upgrade existing line | Project Deferral | Morgan Creek | McDonald Rd | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8360 | 2024-12-15 |  | 138 | 0 | 31.8 | 0 |  | Howard | Mitchell | Tier 3 | 23RPG011 | 2023-05-03 | 2023-05-26 |  | 1032, 11395, 1333 | Y |  |  | 0 | 73625 | 5436
5466 | Redland Switch 345/138 kV Autotransformer | Install new 345/138 kV Autotransformer at Redland Switch previously known as Herty North |  | Redland | Redland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6076 | 2024-12-15 |  | 345 | 0 | 0 | 600 |  | Angelina | Angelina | Tier 3 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3321, 3322, 3306 | Y | N |  |  | 13170 | 5466
5467 | Nacogdoches Southeast_Redland 345kV Line | Establish a new 345kV Line between Nacogdoches Southeast Switch and Redland Switch |  | Nacogdoches Southeast | Redland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6075 | 2024-12-15 |  | 345 | 13.4 | 0 | 0 |  | Nacogdoches | Angelina | Tier 2 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3119, 3321 | Y | N |  |  | 13171 | 5467
45640 | Spraberry - Polecat Creek 138 kV Line | Upgrade the existing 138 kV line |  | Spraberry | Polecat Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8645 | 2024-12-15 |  | 138 | 0 | 32.4 | 0 |  | Midland | Glasscock | Tier 3 |  |  |  |  | 1328, 1329, 1337, 11350, 11372, 10029, 11337, 11394 | Y |  |  | 0 | 73413 | 45640
50725 | Lean Clay 138 kV Switch | Construct a new 138 kV switch |  | Culberson | Sand Lake | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8658 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 11078, 1097, 11086 | Y |  |  | 0 | 82894 | 50725
52247 | Marrs - Handley 69 kV Line Conversion to 138 kV | Convert the existing Marrs-Handley 69 kV line to 138 kV operation |  | Marrs SW | Handley | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5222 | 2024-12-15 |  | 138 | 2.2 | 13 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1952, 1968, 2158, 2159, 2160, 2161, 2162, 11950, 11952, 1951, 1967, 1969, 11951, 11967 | Y |  |  | 0 | 69011 | 52247
52332 | Lamesa - Paul Davis Tap 138 kV Line Section | Upgrade the existing 138 kV line |  | Lamesa | Paul Davis Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8499, R8475 | 2024-12-15 |  | 138 | 0 | 17 | 0 |  | Dawson | Dawson | Tier 3 |  |  |  |  | 1163, 1170, 10008, 18880 | Y |  |  | 0 | 71169 | 52332
62666 | Upgrade and convert McGregor - Waco West Line | Upgrade and convert McGregor - Waco West Line |  | McGregor Phillips | Waco West | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6172 | 2024-12-15 |  | 138 | 0 | 24.3 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3441, 3584, 3585, 3586, 3596, 3589, 3370, 3372, 3437, 3446, 3440, 3594 | Y |  |  | 0 | 62667 | 62666
62693 | Courtney Creek - Yucca Drive 69 kV Line Conversion to 138 kV | Add Courtney Creek - Yucca Drive 69 kV Line Conversion to 138 kV |  | Courtney Creek | Yucca Drive | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8591 | 2024-12-15 |  | 69 | 0 | 44 | 0 |  | Pecos | Ward | Tier 3 | 22RPG025 | 2022-08-24 | 2022-09-16 |  | 1202, 1238, 1239, 11204, 11238, 11262, 1009, 1015, 1203, 1240, 1241, 1242, 11242, 1204, 11246, 11258, 60792 | Y |  |  | 0 | 64552 | 62693
66194B | Holliday - Navy Kickapoo 69 kV Line | Idle Holliday-Navy Kickapoo 69 kV line and Demolish Blackwell 69 kV Substation |  | Holliday | Navy Kickapoo | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4022 | 2024-12-15 |  | 69 | 0 | 0 | 0 |  | Archer | Archer | Tier 4 |  |  |  |  | 1525, 1526, 1528, 1473, 1527 | Y |  |  | 0 | 78353 | 66194
66567 | Add Wolf - Moss 138 kV Line Rebuild | Add Wolf - Moss 138 kV Line Rebuild |  | Wolf | Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8530 | 2024-12-15 |  | 138 | 0 | 34.5 | 0 |  | Ward | Ector | Tier 3 | 22RPG013 | 2022-05-11 | 2022-06-03 |  | 1013, 1019, 1292, 11292, 11293 | Y |  |  | 0 | 66568 | 66567
68955 | Meteor 345 kV Switch | Establish Meteor 345 kV Switch |  | Wolf | Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8619 | 2024-12-15 |  | 345 | 0 | 0 | 0 |  | Ward | Ector | Tier 4 |  |  |  |  | 10012, 1018, 11010 | Y |  |  | 0 | 68957 | 68955
70900B | Roanoke Area Upgrades | Establish Exchange 345 kV Switch and Exchange - Kingsridge 138 kV Double-Circuit Line |  | Exchange Switch | Kingsridge Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5281 M5144 M5146 M5148 | 2024-12-15 |  | 345 | 3.8 | 0 | 1500 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 1855, 12077, 12078, 12079, 12080, 12081, 559, 1845, 1851, 12036, 2081 | Y | N |  | 0 | 72014 | 70900
71908 | Install second 345/138 kV Auto at Temple Pecan Creek | Install second 345/138 kV Auto at Temple Pecan Creek and cut in the Temple - Lake Creek 345 kV Line |  | Temple Pecan Creek | Temple Pecan Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6239 | 2024-12-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 1 |  |  |  |  | 13412, 3404, 3412, 3414, 3420 | Y |  |  | 0 | 71909 | 71908
71960 | Upgrade Grady - Expanse 138 kV Line | Rebuild the existing 138 kV line |  | Grady | Expanse | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8639 | 2024-12-15 |  | 138 | 0 | 6.4 | 0 |  | Martin | Martin | Tier 4 |  |  |  |  | 11368, 23842 | Y |  |  | 0 | 71962 | 71960
71976 | Watermill 138 kV Switch | Rebuild the existing Watermill 138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3031 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 |  |  |  |  | 2429, 2430, 12433, 2126, 3068, 2427, 12430 | Y |  |  | 0 | 71977 | 71976
71989 | Big Spring West - Stanton East 138 kV Line | Rebuild the existing 138 kV line |  | Big Spring West | Stanton East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8303 | 2024-12-15 |  | 138 | 0 | 17.6 | 0 |  | Martin | Howard | Tier 4 |  |  |  |  | 1324, 10044, 11316, 1322, 1325, 1326, 11324, 11331 | Y |  |  | 0 | 73334 | 71989
71993 | Tributary - Vincent 138 kV Line Section | Rebuild the existing 138 kV line |  | Tributary | Vincent | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8667 | 2024-12-15 |  | 138 | 0 | 11.2 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 1394, 10047, 1397 | Y |  |  | 0 | 73300 | 71993
72596C | PEC_MarshallFord_Paleface_StormHardening | Upgrade to terminal equipment and update to final circuit rating. Terminal end equipment update to be completed Fall 2024 based on original project schedule. (Replaces ERCOT Project # 61274C) | 1/10/2023: Changes to description based on final design. | Paleface | Marshall Ford | Planned |  | PEC/LCRATSC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-12-15 |  | 138 | 0 | 11.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70477, 77356 | Y | N |  | 0 | 73445 | 72596
72649B | Add_Celina_Load |  |  |  |  | Planned |  | RYBRN | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 6793, 2350, 12351 | Y |  |  | 0 | 78609 | 72649
73043 | Peck - Driver 138 kV Line | Construct a new 138 kV line |  | Peck | Driver | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8603 | 2024-12-15 |  | 138 | 4.1 | 4 | 0 | 0,110.4 | Glasscock | Glasscock | Tier 2 | 22RPG047 | 2022-12-27 | 2023-01-20 |  | 1222, 1223, 11222, 11282, 11285, 1217, 1226, 1333, 11226, 11227, 11283, 1329, 1330, 18664, 23863 | Y |  |  | 0 | 76389 | 73043
73368 | Grey Well Draw - Buffalo 138 kV Second Circuit | Add Grey Well Draw - Buffalo 138 kV Second Circuit |  | Grey Well Draw | Buffalo | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8692 | 2024-12-15 |  | 138 | 6 | 26.2 | 0 |  | Midland | Midland | Tier 3 |  |  |  |  | 10061, 23858, 11390, 11396, 23837 | Y |  |  | 0 | 73370 | 73368
76682 | Add Capacitor Bank at Savanna 138 kV Substation | Add Capacitor Bank at Savanna 138 kV Substation |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8694 | 2024-12-15 |  | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 10025, 23867, 23870 | Y |  |  | 0 | 81462 | 76682
76686 | Add Hog Mountain 138 kV POD | Add Hog Mountain 138 kV POD |  | Quartz Sand | Hog Mountain POD | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8673 R8791 | 2024-12-15 |  | 138 | 5.4 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 18552, 1328 | Y |  |  | 0 | 76687 | 76686
76690 | Add Atchison POD | Add Atchison POD |  | Border Switch | Atchison | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8698 R8726 | 2024-12-15 |  | 138 | 7 | 0 | 0 |  | Loving | Loving | Tier 4 |  |  |  |  | 18670, 18672, 11089, 11189 | Y |  |  | 0 | 76691 | 76690
76719 | Establish Bull Moose 138 kV Switch | Establish 138 kV Switch | [5 empty] | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8702 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 18680, 1092, 11070, 11113, 11382 | Y |  |  | 0 | 81370 | 76719
77650 | Establish Steakley Dam 345 kV Switch for Blevins Solar | Establish Steakley Dam 345 kV Switch for Blevins Solar |  | Steakley Dam | Steakley Dam | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6282 | 2024-12-15 |  | 345 | 0 | 0 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3741, 3404, 3409 | Y |  |  | 0 | 77651 | 77650
80550 | Central Park 138 kV Switch | Establish Central Park 138 kV Switch for Graphic Packaging International, LLC |  | Central Park | Central Park | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6273 | 2024-12-15 |  | 138 | 1.2 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3474, 3446, 3544 | Y |  |  | 0 | 81382 | 80550
81148 | Lago Vista T3 addition | T3 addition with bus tie breakers | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-12-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70352 | Y |  |  | 0 | 81149 | 81148
81378 | Odessa EHV - Edwards Tap 138 kV Line Rebuild | Odessa EHV - Edwards Tap 138 kV Line Rebuild |  | Odessa EHV | Wolf | Planned | R8528 | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 |  | 2024-12-15 |  | 138 | 0 | 16.6 | 0 |  | Ector | Ward | Tier 3 |  |  |  |  | 1027, 1052, 1053, 1099, 1110 | Y |  |  | 0 | 81379 | 81378
81605 | Kolb Lake 138 kV POD | Establish Kolb Lake 138 kV POD |  | Kolb Lake POD | Kolb Lake POD | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6229 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  |  | 3346, 3747, 3307, 3340, 3347 | Y |  |  | 0 | 81606 | 81605
56350D | Burnett - Bowie 69 kV Line | Rebuild Old lake Switch - Smith Creek Line (FKA Ringgold Magnolia tap - Bellevue) |  | Burnett | Ringgold Magnolia Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4015 | 2024-12-16 |  | 69 | 0 | 9.8 | 100 |  | Wichita | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 11541, 17010, 33770 | Y | N |  | 0 | 73041 | 56350
77827 | Reconductor TNMP Cottonwood to Oncor Lean Clay | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-12-16 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 11078, 38099 | Y |  |  | 0 | 77828 | 77827
78374 | Rockhound 345/138 kV Switch | Construct a new 345/138 kV Switch |  | Falcon Seaboard | Midland East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8705 | 2024-12-16 |  | 345 | 0 | 0 | 1200 |  | Midland | Martin | Tier 3 | 24RPG002 | 2024-01-11 |  |  | 10062, 10063, 10064, 10065, 1021, 1025, 11390, 23837, 23843, 23858 | Y |  |  | 0 | 78375 | 78374
13TPIT0070 | Nash Creek Substation | Rebuild existing substation, and replace existing PWT with new 69kVx13.09 kV, new Control House, CSW, structures, containment foundations, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2024-12-20 |  | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7596 | Y | N |  | 0 | 78324 | 3322
78553 | [5 empty] | In-Service |  | RYBRN | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2024-12-25 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6791, 6807, 2626 | Y |  |  | 0 | 80747 | 78553
54521 | Hilltop_Weatherford_Rebuild |  |  | Weatherford (1589) | Hilltop (501) | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-12-26 |  | 138 | 0 | 13 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 501, 505, 512, 1589 | Y |  |  | 0 | 54522 | 54521
77041 | LCRATSC_LeonSwitch_Putnam_TL_Overhaul | LCRA TSC will perform an overhaul on the 8.9-mile Leon Switch – Putnam (T727) 138-kV transmission line between Leon Switch existing structure #1/1 and Putnam existing structure #9/10. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Leon Switch | Putnam | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org +151-257-84514 |  | 2024-12-26 |  | 138 | 0 | 8.95 | 0 |  | Eastland | Eastland | Tier 4 |  |  |  |  | 6310, 1624 | Y | Y |  | 0 | 77042 | 77041
5167 | Poesta to Tuleta: Build new double circuit 138/69 kV line | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. | Terminal From Location Update | Poesta |  | Under Construction | 742 - 0925 | AEP TCC | Dave Goetz mlforcum@aep.com 918-599-2674 | 2916 | 2024-12-30 |  | 138 | 23.5 | 23.5 | 0 |  | Bee | Bee | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8195, 8584, 8592, 8629, 88198, 8197, 8198, 8586, 85851, 8196, 8585, 8590, 8593 | Y | N |  | 0 | 61033 | 5167
52068 | Coy City Tap to Pleasanton: Convert to 138 kV | Convert Pleasanton to Three Rivers 69 kV line and Coy City Tap to Fashing 69 kV line to 138 kV, reterminate Pleasanton to Three Rivers into 138 kV yards at Pleasanton and Three Rivers, install new terminal for the Trumbo line at Pleasanton, and convert Fashing, Coy City Tap, and Schottky stations to 138 kV | Project Title, TSP/Company Contact, Estimated Cost, Trans Circuit Miles Rebuilt Update | Pleasanton | Three Rivers | Planned | 1077 - 1250 | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 | 3802 TP2020193 | 2024-12-30 |  | 138 | 0 | 8.46 | 0 |  | Atascosa | Live Oak | Tier 4 |  |  |  |  | 8406, 8507, 8599, 8600, 84061, 85071, 85991, 86001, 8142, 8199, 8200, 8203, 8400, 8403, 88507 | Y | N |  | 0 | 65610 | 52068
69902A | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. Loop Ckt.18E into Mission substation to create new Ckt.18 Gibbons Creek to Mission to Zenith. (Ckt.18 Gibbons Creek to Mission tie-line). Install generator lead from Mission (MSS) substation to Parliament/Parliament Solar |  | MISSION | Zenith | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-30 |  | 345 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  |  |  | 44920, 967, 44900 | Y | N |  | 0 | 78230 | 69902
59099 | Blessing to Celanese: Rebuild 138 kV line | Rebuild the Blessing to Celanese 138 kV line | In-Service Date Update | Blessing | Celanese Bay City | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2020227 | 2024-12-31 |  | 138 | 11.54 | 0 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 8116, 8121, 8191, 8558 | Y |  |  | 0 | 65587 | 59099
60522 | Rebuild Hidden Lakes-League City with 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  | 0 | 60523 | 60522
63579 | Roby to Rotan: Rebuild 69 kV Line | Rebuild the Roby to Rotan 69 kV Line |  | Roby | Rotan | Planned | 1130 - 1308 | AEP TNC | Christopher Carroll twang1@aep.com 918-599-2635 | 1875 | 2024-12-31 |  | 69 | 0 | 8 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 6194, 6195, 6196 | Y | N |  | 0 | 63580 | 63579
63956 | Clear Crossing: Build 345 kV terminal | Interconnect HODL Ranch II at Clear Crossing 345 kV station | In-Service Date Update | Clear Crossing | HODL Ranch II | Planned | 1139 - 1317 | ETT TNC | Adam Wells twang1@aep.com 918-599-2635 | 1884 | 2024-12-31 |  | 345 | 0 | 0 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  |  | 60017, 60515 | Y | N |  | 0 | 63957 | 63956
64063 | BRP Antlia BESS Interconnection | Connect BRP Antlia BESS to the Maxwell 138 kV station | In-Service Date Update | Maxwell | Antlia | Planned |  | AEP TCC | Joseph Isaac mlforcum@aep.com 918-599-2674 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 88999, 8998 | Y |  | TP2021260 | 0 | 64064 | 64063
64069 | Charger Solar Interconnection | Connect the Charger Interconnection to the Angstrom to STP 345 kV line | In-Service Date Update | Angstrom | STP | Planned |  | AEP TCC | Teresa Trotman mlforcum@aep.com 918-599-2674 | TP2021165 | 2024-12-31 |  | 345 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  |  | 8676, 8678, 5915, 8249 | Y |  |  | 0 | 64070 | 64069
66118 | Reconductor TI-Lakepointe with 959 ACSS/TW |  |  | Lakepoint (bus # 37010) | TI (bus # 37080) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-12-31 |  | 138 | 0 | 2.78 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 37010, 37080 | Y |  |  | 0 | 66119 | 66118
66221K | Galena Park Area Conversion Project | Rebuild GYPSUM customer substation for 138kV loop-tap service. Tap new GYPSUM substation (Spear Stone) from Ckt.94 between TANKER and new Galena Park tap to create new Ckt.94M CITFIL to Normandy tap to Galena Park tap to Spear Stone to TANKER |  | CITFIL | Tanker | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40731, 40739, 40590, 40612, 40630, 41172, 48130, 48402 | Y | N |  | 0 | 80627 | 66221
67422E | Greens Bayou to Clinton 138kV Conversion | Rebuild-Reconductor Ckt.10A Wallisville tap to TEXWAL |  | Wallisville | TEXWAL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 69 | 0 | 1.44 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41682, 41570 | Y | N |  | 0 | 72770 | 67422
68150 | Abilene South to Estes: Rebuild 138 kV Line | Rehab Abilene South to structure 33/7 | Project Title, Project Description, Terminal To Location, and Estimated Cost Update | Abilene South | Estes | Under Construction |  | AEP TNC | Michael Glueck twang1@aep.com 918-599-2635 |  | 2024-12-31 |  | 138 | 0 | 18.3 | 0 |  | Taylor | Callahan | Tier 4 |  | 2022-02-01 | 2022-03-01 | 2022-03-01 | 6313, 60063, 6260, 60365, 60336, 60355, 60773, 61015 | Y | N |  |  | 68151 | 68150
69892 | Deer Park Tap to NOBEL Ckt.21C Upgrades | Upgrade portions of Deer Park Tap to Underwood tap to NOBEL Ckt.21C as a Hardening upgrade |  | Underwood | NOBEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 1.1 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 48084, 48389 | Y | N |  |  | 69893 | 69892
70633A | Burke to Eagles Nest Ckt.02J Upgrades | Upgrade Ckt.02J Burke to Eagles Nest as a Hardening upgrade |  | Burke | Eagles Nest | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 4.59 | 0 |  | Brazoria | Brazoria | Tier 4 | 22RPG037 | 2022-10-31 | 2022-11-22 | 2022-11-22 | 42410, 42980, 42430 | Y | N |  | 0 | 72452 | 70633
70717 | LCRATSC_Yarrington_Substation_Addition | Add new three terminal ring bus substation to 138 kV line between Rohr and Goforth and install 46.7 MVA distribution transformer. The new substation will be located approximately 0.17 miles from Rohr substation. |  | Rohr | Goforth | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org (512) 578-4514 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7514, 7501, 7515 | Y | N |  | 0 | 70718 | 70717
71004A | Julia CNP-Owned Sub for Melaza Solar (21INR0220) | Install new Julia (JUL) CNP substation for generator interconnection to Maleza Solar. Loop Ckt.72 into Julia substation to create new Ckt.72 Hillje to Julia to Blue |  | Julia | Hillje/Blue | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44220, 44060, 44200 | Y | N |  | 0 | 75844 | 71004
71950 | Twin Buttes Load 138kV Circuit Breaker Addition | Provide a 138-kV point of interconnection at the Twin Buttes Substation to connect to a new Golden Spread Electric Cooperative Transmission line. Update contingencies |  | Twin Buttes |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 4 | [5 empty] | Y | N |  | 0 | 78299 | 71950
73448 | Roma: Build new 138 kV terminal | Bordertown BESS interconnection to Roma Station on Roma Switch to Rio Grande City | In-Service Date Update | Roma |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Starr | Nueces | Tier 4 |  |  |  |  | 87960, 8795, 8796 | Y |  |  | 0 | 73449 | 73448
73476 | TNMP_KERMIT_RECONDUCTOR |  |  | 37920 WINK T | 38250 KERMIT 2 | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-12-31 |  | 138 | 10.8 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 37920, 38250 | Y |  |  | 0 | 73477 | 73476
76176 | Transmission POI for Dogfish BESS |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38465, 38331, 38455 | Y |  |  | 0 | 76177 | 76176
77074 | Buda to Turnersville Storm Hardening | Rebuild single circuit section of Buda to Turnersville and reconductor with bundled 795 ACSR Conductor, 439 MVA. |  | Buda | Turnersville | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-12-31 |  | 138 | 0 | 3.8 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7500, 70498 | Y | N |  | 0 | 77075 | 77074
78420 | Baytown Distribution Transformer | Install third Baytown distribution transformer on Ckt.03B to create new Ckt.03B Kenny tap to Baytown tap to Baytown 138kV. |  | Baytown | KENNY | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40171, 40172, 40173, 40015, 40170, 44630, 48360 | Y | N |  | 0 | 81475 | 78420
78423 | Bellaire to WAP Ckt.50A Upgrade - WAP Switch 0505 | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits |  | Bellaire | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 | [5 empty] | Y | N |  | 0 | 78424 | 78423
82304 | PMCR for adding Blackjack new station |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-12-31 |  | 138 | 0.674 | 0 | 167 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 37682, 1646, 37650, 37680, 37681 | Y |  |  | 0 | 82850 | 82304
70633B | Burke to Eagles Nest Ckt.02J Upgrades | Upgrade Ckt.02K Eagles Nest to West Columbia as a Hardening upgrade |  | Eagles Nest | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:01 |  | 138 | 0 | 1.86 | 0 |  | Brazoria | Brazoria | Tier 4 | 22RPG037 | 2022-10-31 | 2022-11-22 | 2022-11-22 | 42430, 43380 | Y | N |  | 0 | 72451 | 70633
71004B | Julia CNP-Owned Sub for Melaza Solar (21INR0220) | Install generator lead from Julia (JUL) CNP substation to MALEZA/Maleza Solar |  | Julia | MALEZA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 75845 | 71004
73352B | PH Robinson Area 138kV Upgrades | Upgrade Ckt.79F PH Robinson to Seabrook to HANNAH to HUNTER to increase thermal limits |  | PH Robinson | Seabrook | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42780, 42852, 48282, 42830 | Y | N |  | 0 | 73354 | 73352
73371C | BP24 Sub Upgrades | Upgrade Crosby to Danek Ckt.08G to increase thermal limits |  | Crosby | Danek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40390, 40396 | Y | N |  | 0 | 73374 | 73371
49564 | Mantle: Construct New 345 kV Station | Mantle: Construct New 345 kV Station | TSP/Company Contact and In-Service Date Update | Mantle |  | Planned | 1035 - 1213 | AEP TCC | Tom Reynolds mlforcum@aep.com 918-599-2674 | 3774 TP2018166 | 2024-12-31 20:00 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8059, 80598, 8383, 8573 | Y | N |  | 0 | 49565 | 49564
70550 | Create_GP_Solar_POI_Bus | Created GP Solar POI bus. |  | Glen Pine | Explorer | Planned |  | RYBRN | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-01-01 |  | 138 | 0 | 0 | 0 |  | Van Zandt | Van Zandt | Tier 4 |  |  |  |  | 6802, 6829, 6833 | Y |  |  | 0 | 72028 | 70550
72647 | Add_Blue_Ridge_Load |  |  |  |  | Planned |  | RYBRN | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-01-01 |  | 69 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 6803, 37245, 37240, 37280 | Y |  |  | 0 | 78600 | 72647
75887 | Add_SteepHollow_Load |  |  | Steep Hollow |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-01-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32879 | Y |  |  | 0 | 80378 | 75887
75889 | Add_Wellborn_Load |  |  | Wellborn |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-01-01 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32895 | Y |  |  | 0 | 80379 | 75889
77172 | Add new carbon capture load at Alazan | Project will be modified after station engineering is completed. |  | Alazan |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-01-01 |  | 138 | 0 | 0 | 0 |  | Kleberg |  | Tier 4 |  |  |  |  | 8515 | Y |  |  | 0 | 77173 | 77172
68179 | North Edinburg Red Gate | North Edinburg: Install 3 - 138 kV breakers. Re-terminate Falfurrias 138 kV Line. Terminate Redgate (STEC) 138 kV Line. | Schedule Update | North Edinburg | Redgate (STEC) | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-01-17 |  | 138 | 0.08 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8380, 88380 | Y |  |  | 0 | 68180 | 68179
70223 | LCRATSC_Mont_PilotGrove_TL_Overhaul | LCRA TSC will perform an overhaul on the 8-mile Mont ¿ Pilot Grove (T140) 138-kV transmission line. |  | Mont | Pilot Grove | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-01-24 |  | 138 | 0 | 8 | 0 |  | Lavaca | Lavaca | Tier 4 |  |  |  |  | 7234, 7235, 7249 | Y | Y |  | 0 | 70224 | 70223
68252 | Lobo: Line settings | Interconnect Guajillo to the Lobo 345 kV station | Transmission Status Update | Lobo |  | Under Construction |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2025-01-30 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80219, 163223 | Y |  |  | 0 | 68253 | 68252
6934B | Elm Creek - New 345 kV Reactor | Install new 345 kV 60 Mvar Reactor at Elm Creek Substation. | [5 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0873, S-0893 | 2025-01-31 |  | 345 | 0 | 0 | 0 | 60,0 | Guadalupe |  | Tier 4 |  |  |  |  | 5133 | Y |  |  |  | 14754 | 6934
61090 | Southeast138kV substation | Establish 138kV Southeast substation with (2) 40MVA transformers and will cut into existing Ckt 1026 (Stoney Ridge to Hi-Cross |  | Stoney Ridge | Hi-Cross |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-01-31 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9240, 9237, 9251 | Y |  |  | 0 | 61091 | 61090
61224 | AEN_Decker_SH_ckt_1008__reconductor | Upgrade the 7.04 mile Decker to Sand Hill 138 kV transmission line (Ckt 1008) with bundled 795 ACSS Drake conductor rated for 3000 amps |  | Decker [9187] | Sandhill [9216] | Planned |  | AEN | Shirley Mathew shirley.mathew@austinener (512) 322-6103 |  | 2025-01-31 |  | 138 | 0 | 7.04 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9187, 9216 | Y |  |  | 0 | 61225 | 61224
81345 | Adding McFarland |  |  |  |  | Planned |  | TSP |  |  | 2025-01-31 |  | 138 | 0 | 0 | 0 |  | Parker |  | Tier 4 |  |  |  |  | 79700 | Y |  |  | 0 | 81346 | 81345
47541 | Crane Circuit Breaker Addition | Provide transmission service to American Electric Power at Crane Substation. Adding one (1) breaker and associated equipment needed to connect the AEP-owned Crane to Kinnison 138-kV transmission line. |  | Crane Substation | Crane Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2025-01-31 02:00 |  | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 76615 | Y | N |  | 0 | 78402 | 47541
71935 | Upgrade Hondo Creek to Castroville to 138kV | Upgrade Castroville sub to 138kV and line from Hondo creek to Castroville |  |  |  |  | 71917 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-02-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | 22RPG022 |  |  |  | 5804, 5807, 5808, 5810, 5819, 5821 | Y |  |  | 0 | 73097 | 71935
82829 | New Furhman Substation | Adds New Furhman switching station on Rayburn - Vanderbilt line for generator interconnect |  | Rayburn | Vanderbilt | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-02-01 |  | 138 | 0.84 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5506, 5502, 5584 | Y | N |  | 0 | 82830 | 82829
50845 | Kinnison: Expand 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | TSP/Company Contact, In-Service Date Update | Kinnison |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2797 | 2025-02-28 |  | 138 | 0 | 0 | 130 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60431, 6604, 6607, 6611, 60432 | Y | N |  | 0 | 65545 | 50845
50847 | Sage: Expand 69 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | TSP/Company Contact, In-Service Date Update | Sage |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2799 | 2025-02-28 |  | 69 | 0 | 0 | 0 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-06-21 |  | 6604 | Y | N |  | 0 | 50848 | 50847
70282 | New 138kV Brushy Creek Substation |  |  | Thompsons Creek | Snook | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-02-28 |  | 138 | 2.81 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32867, 32857, 32863 | Y |  |  | 0 | 70301 | 70282
72029A | Ashville (ASH) 138kV CEHE Station for SUNLIT/Dori BQ BESS (23INR0040) | Loop new CEHE 138kV substation Ashville (ASH) into Ckt.06F Garden Villas to Holmes to create new Ckt.06 Garden Villas to Ashville to Holmes |  | Ashville | Garden Villas | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42770, 42680, 47210 | Y | N |  | 0 | 73344 | 72029
76076 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild Las Cruces to Milo 138 kV line | In-Service Date and Estimated Cost Update | Las Cruces | Milo | Planned | 1116 - 1294 | AEP TCC/ETT TCC | William Lovelace mlforcum@aep.com 918-599-2674 | 3835 | 2025-02-28 |  | 138 | 0 | 2.4 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8112, 8918 | Y |  |  | 0 | 76077 | 76076
78459 | Peters 138kV Substation Expansion for Walstrom BESS (22INR0540) | Expand Peters 138kV substation for generator lead to WALSTR (WAL) / Walstrom BESS (22INR0540). |  | Peters |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-02-28 |  | 138 | 0 | 0 | 0 |  | Austin | Austin | Tier 4 | [5 empty] | Y | N |  | 0 | 78460 | 78459
72029B | Ashville (ASH) 138kV CEHE Station for SUNLIT/Dori BQ BESS (23INR0040) | Install one generator lead from CEHE 138kV substation Ashville (ASH) to SUNLIT/Dori BQ BESS |  | Ashville | SUNLIT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-02-28 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | 0 | 73343 | 72029
45501 | Eldorado Live Oak to Sonora: Rebuild 69 kV line | Rehab Eldorado Live Oak to Sonora 69 kV line | TSP/ Company Contact, In-Service Date Update | Eldorado Live Oak | Sonora | Planned | 982 - 1160 | AEP TNC | Dave Baker twang1@aep.com 918-599-2635 | 2769 | 2025-02-28 01:00 |  | 69 | 0 | 23.92 | 0 |  | Schleicher | Sutton | Tier 3 | 18RPG012 | 2018-12-18 | 2019-01-17 |  | 6054, 6509, 6498, 6503, 6505, 6510, 6513 | Y | N |  | 0 | 65530 | 45501
51012 | Kinnison to Sage: Rebuild 69 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | TSP/ Company Contact, In-Service Date Update | Kinnison | Sage | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2823 | 2025-02-28 01:00 |  | 69 | 0 | 0.25 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-17 |  | 60431, 6604 | Y | N |  | 0 | 65555 | 51012
72651 | Add_Josephine_Load | [6 empty] | RYBRN | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-03-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6991, 991 | Y |  |  | 0 | 76031 | 72651
76918 | Primavera 138 kV: Construct new station | New station to serve Tesla load |  | Primavera |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023059 | 2025-03-01 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8003, 88747, 8749, 8518, 8921 | Y |  |  | 0 | 76919 | 76918
71937 | Caterpillar Substation | Add T6, 40 MVA. 138-26.08 kV PWT to Caterpillar Substation |  | Caterpillar |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-03-18 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 | [5 empty] | Y | N |  | 0 | 71938 | 71937
80464 | McKenize Road 138 kV: Build a new station | Add Bootstrap Loads |  | Nueces | Nueces | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-03-30 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8520, 8545, 8858, 78569, 78568 | Y |  |  | 0 | 80465 | 80464
70536 | New 138 kV Verde Circle Substation | New 138 kV Verde Circle Substation looping into existing 138 kV Westover Hills and VLSI line. |  |  |  | Planned | T-0316 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0971 | 2025-03-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5466, 5467, 5488 | Y |  |  | 0 | 70537 | 70536
76078 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild Mines Road to Milo 138 kV line | In-Service Date and Estimated Cost Update | Mines Road | Milo | Planned | 1116 - 1294 | AEP TCC/ETT TCC | William Lovelace mlforcum@aep.com 918-599-2674 | 3835 | 2025-03-31 |  | 138 | 0 | 2.95 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8643, 8918 | Y |  |  | 0 | 76079 | 76078
80956 | Holly: 138 kV Breaker Replacement | Upgrade 138 kV bus tie breaker at the Holly 138 kV station | NEW | Holly |  | Planned | TP2023629 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-03-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8486 | Y | N |  | 0 | 80957 | 80956
70886 | Rebuild TinTop - Rio Colorado | Rebuild TinTop- Rio Colorado 795ACSR |  | Tin Top | Rio Colorado | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-04-01 |  | 69 | 0 | 15.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5563, 5569 | Y |  |  | 0 | 70887 | 70886
81354 | GSEC_9452_Add_Snodgrass_Sub | Adding new Snodgrass sub to connect to AEP's Juncus Station. | Add New Load and Sub |  |  | Planned |  | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2025-04-01 |  | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 9452, 60002 | Y | Y |  | 0 | 81355 | 81354
73661 | New transformer (T2) at BPUB Palo Alto Substation | Adding load (T2) on bus 5965 Palo Alto. |  | BPUB Palo Alto 5965 |  | Planned |  | BPUB/Brownsville PUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2025-04-02 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 5965 | Y | N |  | 0 | 80506 | 73661
73663 | New transformer (T1) at BPUB Waterport Substation | BPUB new load T1 at bus 59450 |  | Waterport Substation (59450) |  | Planned |  | BPUB/Brownsville PUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2025-04-02 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 59450 | Y | N |  | 0 | 80507 | 73663
61404 | Boerne Split-Welfare Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T228 Boerne to Welfare 138-kV and T656 Bergheim to Kendall 345-kV 7.3-mile double-circuit transmission line by replacing the aging conductor. |  | Boerne, Bergheim | Welfare, Kendall | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61402 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-04-03 |  | 345 | 0 | 7.3 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7046, 7153, 7168, 7770 | Y | N |  | 0 | 78327 | 61404
72576A | Lago Vista to Nameless Transmission Line Upgrade | Rebuild and upgrade Nameless to Lago Vista with double-circuit capable structures. Install 1 ckt with bundled 795 kcmil conductor (440 MVA). Final span of conductor and terminal equipment at Nameless will be upgraded to 440 MVA with ERCOT project #72576B. (Replaces ERCOT Project # 61277A) | 1/10/2023: Added information to clarify timing for final circuit rating upgrade. | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2025-04-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70352, 70526 | Y | N |  | 0 | 72577 | 72576
78183 |  |  |  | Henry | Henry | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-04-15 |  | 69 | 0 | 0 | 0 | 0,12 | Childress | Childress | Tier 4 |  |  |  |  | 740 | Y |  |  | 0 | 78184 | 78183
61234 | Antler-Bergheim Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the T493 Antler to Bergheim 138-kV and T389 Bergheim to Hays Energy 345-kV 7.2-mile double-circuit transmission line by replacing the aging conductors from Antler to Bergheim substations. |  | Antler | Bergheim | Planned | 61406, 61358, 61392, 61350, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-04-16 |  | 345 | 0 | 7.2 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7171, 7770, 7043, 7170 | Y | N |  | 0 | 78331 | 61234
70922 | LCRATSC_ChiefBrady_Georgetown_TL_Upgrade | LCRA TSC will upgrade T355 Chief Brady - Georgetown 138-kV transmission line to achieve a higher operational rating. |  | Chief Brady | Georgetown | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-04-17 |  | 138 | 0 | 3 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7343, 7366 | Y | N |  | 0 | 70923 | 70922
1275 | Hawkins to Gainesville | Hawkins to Gainesville |  | Hawkins | Gainesville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-04-28 |  | 69 | 0 | 6.72 | 80 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 705, 706, 33705, 33726, 707, 726 | Y |  |  | 0 | 67891 | 1275
45136 | CPSE_New Midtown Substation | New Mid Town substation looped into Comal St to Olmos transmission line. |  |  |  |  | S-0910 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0283 | 2025-04-29 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5311, 5096, 5325 | Y |  |  | 0 | 45137 | 45136
50900 | Mason to North Brady: Rebuild 69 kV line | Rehab Mason to North Brady 69 kV line | In-Service Date Update | Mason | North Brady | Planned | 1046 - 1219 | AEP TNC | David Baker twang1@aep.com 918-599-2635 | 2794 | 2025-04-30 |  | 69 | 0 | 30.24 | 0 |  | Mason | McCulloch | Tier 3 | 19RPG019 | 2019-10-01 | 2019-11-01 |  | 6006, 6381, 6393, 6406, 60386 | Y | N |  | 0 | 65550 | 50900
73059 | Barrera: Build new 138 kV distribution station | Build new distribution station on the Reveille to North Laredo SW 138 kV line | In-Service Date Update | Barrera |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-04-30 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8717, 8108, 8612, 8619, 8627, 8909 | Y |  |  | 0 | 73060 | 73059
80858 | Sterling City: Upgrade 69 kV Relays | Upgrade relays at the Sterling City 69 kV station on the Angora 69 kV terminal | NEW | Sterling City |  | Planned | TP2023887 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-04-30 |  | 69 | 0 | 0 | 0 |  | Sterling |  | Tier 4 |  |  |  |  | 6435, 6484 | Y | N |  | 0 | 80859 | 80858
81347 | Adding Crucis Substation | [6 empty] | TSP |  |  | 2025-04-30 |  | 138 | 0 | 0 | 0 |  | Hood |  | Tier 4 |  |  |  |  | 79701 | Y |  |  | 0 | 81348 | 81347
45174 | Ollin to LCRA Crane: Partial Build, Partial Rebuild, and Conversion | Build new Ollin 138 kV station; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage | Project Description, TSP Company Contact, and In-Service Date Update | Ollin | LCRA Crane | Planned | 939 - 1117 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 2767 | 2025-04-30 01:00 |  | 138 | 0.52 | 0 | 0 |  | Crane | Crane | Tier 4 | 19RPG013 |  |  |  | 6600, 6605, 6606, 6669, 60428, 60429, 60431, 60432, 60441, 6610, 6613, 6668, 76615 | Y | N |  | 0 | 65527 | 45174
45421 | McElroy to Sage: Rebuild 69 kV line | Build new Ollin 138 kV station with a 138/69 kV auto; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage | In-Service Date Update | McElroy | Sage | Planned | 939 - 1117 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2768 | 2025-04-30 01:00 |  | 69 | 0 | 1.99 | 0 |  | Crane | Crane | Tier 4 | 19RPG013 |  |  |  | 6604, 6607 | Y | N |  | 0 | 65529 | 45421
65661 | Rebuild Wickett-Pyote 138 kV line |  |  | Wickett (but # 37981) | Pyote (bus # 38001) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-01 |  | 138 | 0 | 12.88 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 37981, 38001 | Y |  |  | 0 | 65662 | 65661
69471 | Villa Cavazos: Station Work | Eval BESS Interconnect |  | Villa Cavazos |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2025-05-01 |  | 138 | 0.35 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 80229 | Y |  |  | 0 | 69472 | 69471
71879 | Update Ratings |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0939b | 2025-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5133, 5371 | Y |  |  | 0 | 71880 | 71879
71917 | Upgrade STEC castroville to Pearson to 138kV | Upgrade STEC Bader station to 138kV. Upgrade STEC Castroville to bader and bader to pearson to 138kV |  | 5808 | 5813 | Planned | 71935 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-05-01 |  | 138 | 0 | 10.51 | 0 |  | Medina | Medina | Tier 2 | 22RPG022 | 2022-08-08 | 2022-12-06 |  | 5802, 5810, 5804, 5811, 5813 | Y |  |  | 0 | 71918 | 71917
71930 | Upgrade RIOHONDO to BURNS line | Upgrade RIOHONDO to BURNS line to be 478MVA capable |  | Rio Hondo | Burns | Planned | 7192671928 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-05-01 |  | 138 | 0 | 12.2 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5763, 8319 | Y |  |  | 0 | 71931 | 71930
76194 | Angstrom: Build new 345 kV terminal | Pintail Pass BESS interconnection to Angstrom station |  | Angstrom |  | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2023132 | 2025-05-01 |  | 345 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8249, 8956 | Y |  |  | 0 | 76195 | 76194
80753 | LST_Claytonville to Camp Springs 138 kV line additions | LST_Claytonville to Camp Springs 138 kV line additions |  | Claytonville 138 |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68012, 68009 | Y |  |  | 0 | 80754 | 80753
81544 | GSEC_9466_Add_CampSprings_Sub | Add Big Country's Camp Springs Sub 9MW | ISD exceeds NMMS model load date |  |  | Planned |  | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2025-05-01 |  | 138 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 9466, 68012 | Y |  |  | 0 | 81545 | 81544
72588 | Trading Post to Cedar Valley Storm Hardening | Rebuild single circuit section of Trading Post to Cedar Valley and reconductor with bundled 795 ACSR Conductor, 440 MVA. (Replaces ERCOT Project # 61266) |  | Trading Post | Cedar Valley | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2025-05-05 |  | 138 | 0 | 6.8 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70505, 70506 | Y | N |  | 0 | 72589 | 72588
45125 | Quintana Rd to South San Rebuild | Rebuild 1.3 miles of 138 kV transmission line form Quintana Rd substation to South San substation. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0271 | 2025-05-14 |  | 138 | 0 | 1.29 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-15 |  |  | 5350, 5385 | Y |  |  | 0 | 45126 | 45125
62068 | Lakeway-Marble Falls Transmission Line Storm Hardening | Increase the reliability of transmission facilities on the T497 Lakeway ¿ Marble Falls 23-mile 138-kV transmission line. |  | Lakeway | Marble Falls | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Burnet | Tier 4 | 22RPG031 |  | 2022-11-03 |  | 7348, 7349, 7351, 7356, 7476, 7538, 7474, 7540 | Y | N | 22RPG031 reclassified as Tier 4 neutral by RPG review on 11/03/2022 | 0 | 62069 | 62068
62434 | Sargent Road - Industrial Blvd 138 kV DCKT Line | Upgrade existing 138 kV Line |  | Sargent Road Switch | Industrial Blvd Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4128 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2940, 2947, 2972, 2973, 2974, 2975 | Y |  |  | 0 | 62435 | 62434
62448 | Rebuild Marlin 69 kV Switch | Rebuild Marlin 69 kV Switch |  | Marlin | Marlin | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1752 | 2025-05-15 |  | 69 | 0 | 0 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 13639, 3418, 3638 | Y |  |  |  | 62658 | 62448
63948 | Establish Fallstown 138 kV Switch | Establish Fallstown 138 kV Switch |  | Fallstown | Fallstown | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3018 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | 1488, 1483, 17005 | Y |  |  | 0 | 63949 | 63948
66188 | Cedar Crest - Dealey - West Levee 138 kV Line | Upgrade the existing 138 kV Line |  | Ceadr Crest | West Levee | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4212 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2493, 2842, 2400 | Y |  |  | 0 | 66189 | 66188
66569 | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch |  | Mulberry Creek | Mulberry Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9022 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Jones | Jones | Tier 3 | 21RPG021 | 2021-12-17 | 2022-01-12 |  | 1459, 1435, 6235, 11420 | Y |  |  | 0 | 81422 | 66569
69345 | LCRATSC_Limmer_Substation_Addition | Construct a new LCRA TSC-owned Limmer Substation in the Hutto to Zorn 345 kV line approximately 3 miles east of Hutto. Limmer Substation will be installed initially as a five-breaker 345 kV breaker-and-a-half arrangement. |  | Zorn, Hutto | Limmer | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org +151-257-84514 |  | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Williamson | Travis | Tier 3 | 22RPG027 | 2022-08-29 |  |  | 7341, 3696, 7042, 7340 | Y | Y |  | 0 | 78338 | 69345
69552B | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 345 kV Switch, Autotransformers, and 345 kV Tie Lines to Limmer (LCRA) |  | Teal | Teal | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6165 | 2025-05-15 |  | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3363, 3364, 13364, 7341, 3362 | Y |  |  | 0 | 81584 | 69552
70534 | LCRATSC_Hueco_Springs_Sub_Add | NBU is constructing a new 138-kV substation to serve a new residential development. LCRA TSC will provide transmission service to the new load serving substation on the T235 Henne to Comal. |  | Henne | Comal | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7179, 7174, 7176 | Y | N |  | 0 | 70535 | 70534
70538 | LCRATSC_PilotGrove_YoakumGartner_TL_Overhaul | Perform an overhaul on the 7.8 mile T614 Pilot Grove (structure #8/2) - Yoakum Gartner Road 138-kV transmission line. Structure #8/2 and the remaining portion of T614 will be overhauled as part of the FY23 Mont - Pilot Grove Transmission Line Overhaul project. |  | Pilot Grove | Yoakum Gartner | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Lavaca | DeWitt | Tier 4 |  |  |  |  | 7234, 7242 | Y | N |  | 0 | 70539 | 70538
71136 | Waxahachie-Waxahachie OCF 69 kV Line Rebuild | Rebuild the existing Waxahachie-Waxahachie OCF 69 kV Line |  | Wilmer | Waxahachie | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4339 | 2025-05-15 |  | 69 | 0 | 0 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  |  | 2335, 2343 | Y |  |  | 0 | 71137 | 71136
71199 | Yucca Drive - Moss 138 kV Line | Rebuild existing 138 kV line |  | Yucca Drive | Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9047 | 2025-05-15 |  | 138 | 0 | 35.2 | 0 |  | Ector | Winkler | Tier 4 |  |  |  |  | 11015, 1009, 1019, 11128, 18663 | Y |  |  | 0 | 76384 | 71199
71956 | LCRATSC_ElginSwitch_Substation_Addition | LCRATSC will install a new three-breaker ring bus substation at Elgin Switch. Oncor will relocate its facilities from Elgin Switch to Brushy Creek. Install a temporary shoo-fly between T668 and T260 to maintain through-path during construction. |  | Elgin Switch |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 3650, 7321, 3541, 7324, 7338 | Y | N |  | 0 | 73564 | 71956
71980 | Watermill 345 kV Switch | Rebuild the existing Watermill 345 kV Switch |  | Watermill |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4012 | 2025-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 3 |  |  |  |  | 2428, 2435, 2997, 12429, 2398, 2427, 2432, 2466, 2847, 3159, 2429 | Y |  |  | 0 | 76731 | 71980
72004 | Cat Claw 138 kV Dynamic Reactive Device (formerly Midkiff) | Install a new Dynamic Reactive Device at Cat Claw (formerly Midkiff) |  | Cat Claw | Cat Claw | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8675 R8680 R8695 | 2025-05-15 |  | 138 | 0 | 0 | 0 | -250250 | Upton | Upton | Tier 3 |  |  |  |  | 10058, 10059, 10060, 23871, 1210, 1217, 11345, 23870, 11218 | Y |  |  | 0 | 73345 | 72004
73417 | LCRATSC_Schumansville_SheriffsPosse_StormHardening | Perform storm hardening on the 5.6 mile Schumansville - Sheriff's Posse (T307) transmission line. T307 shares ROW with de-energized T409 Comal - Sheriff's Posse between structure #5 and Sheriff's Posse. Design of T307 should allow for the future addition of circuit T409 on double-circuit structures between Sheriff's Posse and structure #5. |  | Schumansville | Sheriff's Posse | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 6 | 0 |  | Guadalupe | Comal | Tier 4 |  |  |  |  | 7460, 7609 | Y | N |  | 0 | 73418 | 73417
73793 | LCRATSC_McCartyLaneEast_Zorn_TL_Storm_Hardening | Perform storm hardening on the 4.2 mile McCarty Lane - Zorn (T202) 138-kV transmission line. T202 is double-circuited with McCarty Lane - Beback - Zorn (T201) 138-kV transmission line. |  | McCarty Lane East | Zorn | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 8.58 | 0 |  | Hays | Guadalupe | Tier 4 |  |  |  |  | 7180, 7182, 7187 | Y | N |  | 0 | 73794 | 73793
76578 | Upgrade the Temple Pecan - Temple Elm 138 kV Double-Circuit Line | Upgrade the 5-mile Temple Pecan - Temple Elm 138 kV Double-Circuit Line |  | Temple Pecan Creek | Temple Elm Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6234 | 2025-05-15 |  | 138 | 0 | 10 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3420, 13662 | Y |  |  | 0 | 76579 | 76578
76650 | Establish Walleye Creek 345/138 kV Switch | Establish Walleye Creek 345/138 kV Switch |  | Walleye Creek | Walleye Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6243 | 2025-05-15 |  | 345 |  | 4.5 | 600 | 0,110.4 | Milam | Milam | Tier 3 |  |  |  |  | 3712, 3713, 3714, 3715, 3716, 3717, 116, 3541, 3742, 7040, 13429, 13430 | Y |  |  | 0 | 76651 | 76650
76705 | Prairieland 345/138 kV Switch and 138 kV Line | Establish Prairieland 345/138 kV Switch and Prairieland – Quartz Sand 138 kV Line |  | Prairieland | Quartz Sand | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8632 | 2025-05-15 |  | 138 | 6 | 0 | 0 |  | Glasscock | Glasscock | Tier 2 |  |  |  |  | 18548, 18549, 18550, 18551, 1058, 1328, 11387, 1030, 18552 | Y |  |  | 0 | 81372 | 76705
78365 | Boggy Creek 138/69 kV Switch | Construct the new Boggy Creek 138/69 kV Switch |  | Boggy Creek | Boggy Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6295 | 2025-05-15 |  | 138 | 5 | 0 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3493, 3496, 3643, 132, 3415, 3644, 3607, 3645, 3689 | Y |  |  | 0 | 81558 | 78365
78371 | Richardson East Switch – Richardson Spring Creek 138 kV Line Section | Upgrade Richardson East Switch – Richardson Spring Creek 138 kV Line Section |  | Richardson East | Richardson Spring Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4402 | 2025-05-15 |  | 138 | 0 | 2.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2689, 2690 | Y |  |  | 0 | 78372 | 78371
78382 | Adds Capacitor Bank at White Dune | Adds Capacitor Bank at White Dune |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8669 | 2025-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Winkler | Winkler | Tier 4 |  |  |  |  | 18692 | Y |  |  | 0 | 80906 | 78382
78395 | LCRATSC Thompsonville switching structure replacement | Replace switching structure and load-serving power transformer at Thompsonville station. |  | Thompsonville |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | 1026926 | 2025-05-15 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 | [5 empty] | Y |  |  | 0 | 78396 | 78395
80546A | Upgrade the Hutto Switch - Gabriel Switch 138 kV Line | Rebuild the Round Rock Westinghouse Tap - Gabriel Line Section and upgrade the Hutto - Round Rock Line |  | Hutto Switch | Gabriel Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6203, R6202 | 2025-05-15 |  | 138 | 0 | 20.2 | 0 |  | Williamson | Williamson | Tier 3 |  |  |  |  | 3664, 3666, 3669, 3677, 7346, 3667, 3668, 7528, 7532 | Y |  |  | 0 | 81498 | 80546
80913 | Sloan 138 kV Switch | Establish Sloan 138 kV Switch. |  | Midland Airport, Midland East | Midessa South | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8659 | 2025-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Midland | Midland | Tier 4 |  |  |  |  | 11137, 11138, 11165, 1059, 1124, 1138, 11143 | Y |  |  | 0 | 80955 | 80913
81146 | Southmayd 138 kV Switch | Establish Southmayd 138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4338 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Grayson |  | Tier 4 |  |  |  |  | 2790, 1744, 11704 | Y |  |  | 0 | 81147 | 81146
81358 | Grindstone 138 kV Switch | Establish Grindstone 138 kV Switch |  | Grindstone Switch | Grindstone Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1754 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Palo Pinto | Palo Pinto | Tier 4 |  |  |  |  | 1569, 1571, 1575, 1592, 1599 | Y |  |  | 0 | 81359 | 81358
81383 | Edwards Tap - Sandhills Tap 138 kV Line Rebuild | Edwards Tap - Sandhills Tap 138 kV Line Rebuild |  | Odessa EHV | Wolf | Planned | R8528 | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 |  | 2025-05-15 |  | 138 | 0 | 11.71 | 0 |  | Ector | Ward | Tier 3 |  |  |  |  | 1102, 1103, 1110 | Y |  |  | 0 | 81384 | 81383
82806 | Establish Long Hollow 345 kV Switch (POI for Pinnington Solar) | Establish Long Hollow 345 kV Switch (POI for Pinnington Solar) |  | Graham Plant Switch | Parker Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3509 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Young | Parker | Tier 4 |  |  |  |  | 1506, 1430, 1436 | Y |  |  | 0 | 82807 | 82806
82808 | Stranger 345 kV Switch | Establish Stranger 345 kV Switch |  | Stranger Switch | Stranger Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6320 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 3721, 3390, 3711 | Y |  |  |  | 82809 | 82808
82810 | Olympus 138 kV Switch | Establish Olympus 138 kV Switch |  | Olympus Switch | Olympus Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6330 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3723, 3125, 3127, 3454, 3466 | Y |  |  | 0 | 82811 | 82810
82826 | Sunflower 138 kV Switch | Establish Sunflower 138 kV Switch |  | Sunflower Switch | Sunflower Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6322 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3722, 170, 3592 | Y |  |  | 0 | 82827 | 82826
67622 | LCRATSC_Caldwell_Substation_Addition | LCRA TSC will build a new substation, Caldwell Substation, to manage 12 MW of load in Summer of 2024. This substation will be on the Cooks Point ¿ Lyle Wolz 138-kV transmission line. It is about 5 miles south of Cooks Point Substation. LCRA will install circuit breakers in a ring bus formation. |  | Caldwell | Caldwell | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2025-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Burleson | Burleson | Tier 4 |  |  |  |  | 7566, 7567, 7569 | Y | N |  | 0 | 67623 | 67622
76274 | Hamilton Road: Build new 138 kV terminal | Interconnect Tierra Seca to the Hamilton Road 138 kV station | Contact Update | Hamilton Road |  | Planned | TP2023133 | ETT TCC/AEP TCC |  |  | 2025-05-18 |  | 138 | 0.1 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  |  | 8255, 8688, 8690, 8684 | Y |  |  | 0 | 76275 | 76274
48816 | Mulberry Creek: Rebuild 345 kV station | Rebuild Mulberry Creek 345 kV station and replace both autotransformers | Transmission Status Update | Mulberry Creek |  | Under Construction | 1015 - 1193 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 | 2776 | 2025-05-28 01:00 |  | 345 | 0 | 0 | 900 |  | Jones |  | Tier 4 | 21RPG021 | 2021-12-15 | 2022-01-13 |  | 6230, 60788, 60789, 1435, 1459, 6235, 11420, 60040, 6231, 6232 | Y | N |  | 0 | 65536 | 48816
67992A | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade,CPSE_Medina_to_36th_Street_Upgrade | Shepherd Rd to Valley Rd 138kV line Reconfiguration. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-29 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5230, 5378, 5465 | Y |  |  | 0 | 72403 | 67992
67992C | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade,CPSE_Medina_to_36th_Street_Upgrade | Looping of 345KV Howard Rd switching station into existing Cagnon to AVR and Cagnon to Spruce 34KV lies. The switching station will have 2 600MVA 345KV/138KV autotransformers. |  | 5056 | 5400 and 5475 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-29 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5231, 5056, 5400, 5475, 5230 | Y |  |  | 0 | 67993 | 67992
72037A | Seabreeze 345kV Substation for Tanglewood Solar (23INR0054) | New 345kV Seabreeze (SEB) substation for generator interconnection to Tanglewood Solar (23INR0054). Loop Ckt.27B into Seabreeze substation to create new Ckt.27 DOW to Seabreeze to Oasis. |  | Seabreeze | DOW/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-29 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43020, 42500, 43035 | Y | N |  | 0 | 73696 | 72037
72037B | Seabreeze 345kV Substation for Tanglewood Solar (23INR0054) | Install generator lead from Seabreeze (SEB) substation to TANGLE (TNG) customer substation (23INR0054). |  | Seabreeze | TANGLE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-29 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | Cost included in main phase | 73695 | 72037
6719 | Twelvemile Substation Addition | Construct a new substation named Twelvemile off the Bakersfield to Schneeman Draw transmission line to support a generation interconnection request (16INR0104) |  | Bakersfield | Schneeman Draw | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018769 | 2025-05-30 |  | 345 | 0 | 0 | 0 |  | Pecos | Crockett | Tier 4 |  |  |  |  | 76008, 7053, 76015 | Y | N |  | 0 | 58408 | 6719
69467 | Dupont to Resnik:Rebuild138 kV line | Rebuild Dupont to Resnik 138 kV Line |  | Dupont | Resnik | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2025-05-30 |  | 138 |  | 0.83 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8422, 8580 | Y |  |  | 0 | 69468 | 69467
70779 | Tortuga: Install Cap Bank | Tortuga Capacitor | Schedule Update | Tortuga |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022188 | 2025-05-30 |  | 138 | 0 | 0 | 0 | 0,23 | Nueces |  | Tier 4 |  |  |  |  | 8697 | Y |  |  | 0 | 70780 | 70779
73098 | Castroville Cut-in 138 kV | Cut the AEP line from Quihi to CPS Castroville into the newly converted to 138 kV STEC Castroville station. |  | Quihi | Castroville (CPS) | Planned | TP2022982 | ETT TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2025-05-30 |  | 138 | 0.4 | 0 | 0 |  | Medina |  | Tier 2 | 22RPG022 | 2023-08-22 | 2023-11-22 |  | 5083, 5804, 8248 | Y |  |  | 0 | 73099 | 73098
73408 | Odysseus: Build new 345 kV station | Interconnect Ulysses Solar to the Odysseus 345 kV Station on the Bluff Creek to SA Red Creek 345 kV line | In-Service Date Update | Odysseus |  | Planned |  | AEP TNC | Zach Lachiusa twang1@aep.com 918-599-2635 |  | 2025-05-30 |  | 345 | 0 | 0 | 0 |  | Coke |  | Tier 4 |  |  |  |  | 60072, 6444, 60040 | Y | N |  | 0 | 73409 | 73408
75830A | New 345kV Savannah (SAV) substation for generator interconnection to Cascade Solar (23INR0091). | Loop Ckt.27 into Savannah substation to create new Ckt.27 Seabreeze to Savannah to Oasis. |  | Savannah | Seabreeze/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-30 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43180, 42500, 43020, 43035 | Y | N |  | 0 | 75833 | 75830
76574 | TexasAg Wind Interconnection | Interconnect TexasAg to the Brisita 345 kV station |  | Brisita |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023129 | 2025-05-30 |  | 345 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8693, 88693, 8574, 8383 | Y |  |  | 0 | 76575 | 76574
75830B | New 345kV Savannah (SAV) substation for generator interconnection to Cascade Solar (23INR0091). | Install generator lead from Savannah (SAV) substation to CASCAD (CSC) customer substation (23INR0091). |  | Savannah | CASCAD | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-30 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 75834 | 75830
50868 | Rosata - Structure 31/8: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild | In-Service Date Update | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3780 | 2025-05-31 |  | 138 | 0 | 15.5 | 0 |  | Goliad | Karnes | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8186, 8153 | Y | N |  | 0 | 50869 | 50868
55572 | Burma to Sterling City: Rebuild 69 kV Line | Rehab the Burma to Sterling City 69 kV Line | In-Service Date Update | Burma | Sterling City | Under Construction | 1096 - 1274 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 | 1864 | 2025-05-31 |  | 69 | 0 | 32 | 0 |  | Tom Green | Sterling | Tier 3 | 20RPG021 | 2020-10-01 | 2020-11-01 |  | 6439, 6445, 6460, 61016, 61017, 6435, 6446, 6461, 60411 | Y | N |  | 0 | 55573 | 55572
60526 | Rebuild West Columbia Local-Angleton with 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39530, 39560 | Y |  |  | 0 | 60527 | 60526
63922 | Tiki Island Distribution Upgrades | Install double-tap distribution service to Tiki Island. Existing tap will remain on Ckt.63E La Marque to Stewart. Tap Ckt.93C La Marque to West Galveston for the new tap section to Tiki Island. |  | Tiki Island | LaMarque/West Galveston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  |  | 43351, 43352, 43355, 48851, 48852, 48855, 42860, 43290, 43400, 43401 | Y | N |  | 0 | 63923 | 63922
67921 | Sisseton: Build 69 kV tap | Build new 69 kV tap on the Aspermont to Hamlin 69 kV line | Project Description and In-Service Date Update | Sisseton |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-05-31 |  | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6073, 60068, 6156, 6184, 6186, 6185, 6187 | Y |  |  | 0 | 67922 | 67921
70349 | Belknap to Fort Griffin: Rebuild 69 kV Line | Rehab Belknap to Fort Griffin 69 kV line | Planning Tier Update | Belknap | Fort Griffin | Planned |  | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 |  | 2025-05-31 |  | 69 | 0 | 23.6 | 0 |  | Jones | Shackelford | Tier 4 | 22RPG020 | 2022-06-27 | 2022-07-22 |  | 6178, 6210, 6214, 60466, 60471, 60398, 60409, 60445 | Y | N |  | 0 | 70350 | 70349
72065 | Lake Jackson Distribution Substation Conversion to Low-Profile | Rebuild Lake Jackson 138/12kV distribution substation to low-profile |  | Lake Jackson |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42880, 43172 | Y | N |  | 0 | 72066 | 72065
72880 | Sisseton: Build 69 kV station | Build 69 kV switch station on the Aspermont to Hamlin 69 kV line | Transmission Owner Project Number and In-Service Date Update | Sisseton |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TP2022059 | 2025-05-31 |  | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6073, 60068, 6156, 6184, 6186, 6185, 6187 | Y |  |  | 0 | 72881 | 72880
72935 | Saragosa: Install 2nd Bay | Install 2nd Bay at Saragosa Substation | In-Service Date Update | Saragosa |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60716 | Y | N |  | 0 | 72936 | 72935
73621A | Hawkinsville (HAW) CNP-Owned 345kV Substation for Lavaca Bay Solar (23INR0084) | New 345kV Hawkinsville (HAW) substation for generator interconnection to Lavaca Bay Solar. Loop Ckt.27D into substation to create new Ckt.27 Jones Creek to Hawkinsville to Refuge. |  | Refuge | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 1.4 | 0 | 0 |  | Matagorda | Brazoria | Tier 4 |  |  |  |  | 42440, 42400, 42530 | Y | N |  | 0 | 73622 | 73621
75776A | Samaritan 138kV Switching Station | In terms of completed Clute substation: Reconfigure Ckt.26 Angleton to Clute and loop into new CNP-owned 138kV Samaritan switching station to create new Ckt.26 Angleton to Samaritan to Clute. |  | Samaritan | Angleton/STRATT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42030, 42110, 43300 | Y | N |  | 0 | 75778 | 75776
75856A | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. Loop into Ckt.06E to create new Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. |  | ETHYL | South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 69 | 1.33 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41240, 41370 | Y | N |  | 0 | 76648 | 75856
75856B | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. Loop into Ckt.06E to create new Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. | Convert ETHYL customer 69kV substation to 138kV. Loop into Ckt.06E to create new Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. |  | ETHYL | South Channel/Jefferson | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40550, 41270, 41381, 41382, 41240, 41370 | Y | N |  | 0 | 76649 | 75856
75938 | Expand Zenith substation with addition of 35kV Distribution Facilities. Tap TR1 on Ckt.09J to create new Ckt.09J Zenith to Zenith TR1 tap to Fry Road tap. Tap TR2 on Ckt.76A to create new Ckt.76A Zenith to Zenith TR2 tap to Fry Road tap. | Expand Zenith substation with addition of 35kV Distribution Facilities. Tap TR1 on Ckt.09J to create new Ckt.09J Zenith to Zenith TR1 tap to Fry Road tap. Tap TR2 on Ckt.76A to create new Ckt.76A Zenith to Zenith TR2 tap to Fry Road tap. |  | Zenith | Fry Road | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44910 | Y | N |  | 0 | 75939 | 75938
76234 | Wormser Road: Build new 138 kV termial | Seven Flags BESS interconnection to Wormser Road Station | In-Service Date Update | Wormser Road |  | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2023311 | 2025-05-31 |  | 138 |  |  |  |  | Webb |  | Tier 4 |  |  |  |  | 8295 | Y |  |  | 0 | 76235 | 76234
76622 | Expand Peters 138kV substation for Walstrom BESS (22INR0540). | Expand Peters 138kV substation for Walstrom BESS (22INR0540). |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Austin | Austin | Tier 4 | [5 empty] | Y | N |  | 0 | 76623 | 76622
78485D | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade portions of Ckt.05E Bellaire to Sharpstown to Hillcroft to increase thermal limits. |  | Bellaire | Hillcroft | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 6.41 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 47014, 48146, 48378 | Y | N |  | 0 | 78487 | 78485
78490A | Jeanetta Auto Upgrades | Replace existing 600 MVA Jeanetta Auto A1 with 800 MVA autotransformer |  | Jeanetta |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 0 | 0 | 200 |  | Harris | Harris | Tier 3 |  |  |  |  | 47300, 47310, 49024 | Y | N |  | 0 | 79425 | 78490
78495 | Hillje 345kV Substation Expansion for Space City Solar - Generator Interconnection (21INR0341) | Expand Hillje 345kV substation and install one generator lead for new interconnection to MIDANE customer substation for Space City Solar |  | Hillje | MIDANE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 | [5 empty] | Y | N |  | 0 | 78496 | 78495
80850 | Lon Hill to Sinton: Bypass Waterworks 69 kV station | Relocate portion of 69 kV line between Odem and Stevens Tap to bypass Waterworks 69 kV station | NEW | Odem | Stevens Tap | Planned | TA2022133 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-05-31 |  | 69 | 0 | 0.45 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8867, 8865, 8810 | Y | N |  | 0 | 80851 | 80850
82321 | PMCR for 2nd TX in Coachwhip | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38170 | Y |  |  | 0 | 82322 | 82321
78485B | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.09A Britmoore to Hayes to Alief to increase thermal limits. |  | Britmoore | Alief | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 2 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 44020, 44120, 44310 | Y | N |  | 0 | 78488 | 78485
78490B | Jeanetta Auto Upgrades | Replace existing 600 MVA Jeanetta Auto A3 with 800 MVA autotransformer |  | Jeanetta |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 0 | 0 | 200 |  | Harris | Harris | Tier 3 |  |  |  |  | 47300, 47310, 49082 | Y | N |  | 0 | 79426 | 78490
78490C | Jeanetta Auto Upgrades | Upgrade Ckt.25B Roark equipment and reconductor near Roark substation to increase thermal limits |  | Clodine | Roark | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 0 | 0.04 | 0 |  | Harris | Harris | Tier 3 | [5 empty] | Y | N |  | 0 | 79427 | 78490
73621B | Hawkinsville (HAW) CNP-Owned 345kV Substation for Lavaca Bay Solar (23INR0084) | Install generator lead from Hawkinsville (HAW) substation to LAVACA / Lavaca Bay Solar. |  | Hawkinsville |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:01 |  | 345 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 | [5 empty] | Y | N |  | 0 | 73623 | 73621
75776B | Samaritan 138kV Switching Station | Connect Samaritan CNP substation with two leads to TNMP_White Oak distribution substation. |  | Samaritan | Angleton/Clute | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42030, 39580 | Y | N |  | 0 | 75779 | 75776
73371E | BP24 Sub Upgrades | Upgrade Whaley to WA Parish Ckt.72F to increase thermal limits |  | Whaley | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:04 |  | 345 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44005, 44070 | Y | N |  | 0 | 73376 | 73371
70943 | Double circuit 138kV tie between Pyote and Coyanosa |  |  | Pyote (bus # 38001) | Coyanosa (bus # 38380) | Conceptual |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-06-01 |  | 138 | 15 | 0 | 0 |  | Ward | Reeves | Tier 2 |  |  |  |  | 38001, 38380 | N |  |  | 0 | 70944 | 70943
80422 | Add_Triangle_Park_Load |  |  | Triangle Park |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-06-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32854 | Y |  |  | 0 | 80423 | 80422
81315 | add 19.2 MVAR Capacitor at Rossville | add 19.2 MVAR Capacitor at Rossville. 2023 RTP |  | Rossville |  |  |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-06-01 |  | 69 | 0 | 0 | 0 | 0,19.2 |  |  | Tier 4 |  |  |  |  | 5718 | Y |  |  | 0 | 81316 | 81315
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 3000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | NEW | 2025-06-10 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 9723 | 2443
44946 | CPSE_New_Scenic_Loop_138kV_Load_Serving_Station | The new Scenic Loop 138 kV load serving station will be looped into existing Ranchtown to LCRA (Menger Creek) 138 kV transmission line. The substation should be located south west of the existing Fair Oaks Ranch and north east of the existing Ranchtown substation. |  |  |  | Planned | S-0885 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0275 | 2025-06-13 20:00 |  | 138 | 9 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5363, 5358, 7665 | Y |  |  | 0 | 44947 | 44946
76133 | West Childress: Station Rehab | Rehab West Childress station |  | West Childress |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2020223 | 2025-06-20 |  | 138 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 6030, 6135 | Y | N |  | 0 | 76134 | 76133
73364 | CPSE_New_Omicron_Substation | [6 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-06-23 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5326, 5055, 5355 | Y |  |  | 0 | 73365 | 73364
22TPIT0000 | Parkway Substation | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10680 | 3324
70019 | Add 138kV Locust-Hickory line 700MVA |  |  | Locust | Hickory | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2025-06-30 |  | 138 | 0 | 1.85 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 922, 924 | Y | N |  | 0 | 70020 | 70019
70196 | LCRATSC_Kingsland1_SandyCreek_TL_Overhaul | LCRA TSC will perform an overhaul on the 7.3-mile Kingsland 1 ¿ Sandy Creek (T400) 69-kV transmission line. |  | Kingsland 1 | Sandy Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-06-30 |  | 69 | 0 | 7.3 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7121, 7400, 7404 | Y | Y |  | 0 | 70197 | 70196
72882 | LCRATSC_Lockhart_Luling_69kV_TL_Overhaul | LCRA TSC will perform an overhaul on the 15.8-mile Lockhart – Luling (T157) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Lockhart | Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-06-30 |  | 69 | 0 | 15.83 | 0 |  | Caldwell | Caldwell | Tier 4 | 23RPG004 | 2023-02-24 | 2023-03-20 |  | 7215, 7218, 7220, 7223 | Y | N |  | 0 | 72883 | 72882
76350 | Install new TARGA 138kV customer substation as Ckt.86 Jordan to TARGA to CITIES. | Install new TARGA 138kV customer substation as Ckt.86 Jordan to TARGA to CITIES. |  | TARGA | Jordan/CITIES | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-06-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40950, 40340, 40855 | Y | N |  | 0 | 76351 | 76350
5430K | Conversion to 138kV | Construct new 138kV Hickory substation and terminate the existing Bonnie Brae - Hickory (which is already insulated for 138kV) at the new 138kV Hickory substation. |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2025-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 931 | Y | N | N/A | 0 | 55205 | 5430
5430O | Conversion to 138kV | Reconnect the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2025-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 930 | Y | N | N/A | 0 | 55209 | 5430
64776 | Upgrade 138kV DentonWest-RDWells line to 700MVA (SUM2024) |  |  | RD Wells | Denton West | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2025-07-01 |  | 138 | 0 | 4.47 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 930, 986 | Y | N |  | 0 | 64777 | 64776
65723 | Riedel: Build New Distribution Station | Construct new distribution station on the Magnolia Tap to Nixon 138 kV line |  | Riedel |  | Planned | 1032 - 1210 | AEP TCC/LCRA | Michael Forcum mlforcum@aep.com 918-599-2674 | 3771 | 2025-07-01 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  |  | 8583 | Y | Y |  | 0 | 65724 | 65723
78414 | Replacing existing 1200 Amp switch and 1800 Amp bypass jumper with new 3000 Amp switch. |  |  |  |  | Planned |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2025-07-01 |  | 138 | 0 | 0 | 0 |  | Comal |  | Tier 4 | [5 empty] | Y |  |  | 0 | 78417 | 78414
61392 | Bergheim-Fair Oaks Ranch Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T238 Bergheim to Fair Oaks 138-kV and T656 Bergheim to Kendall 345-kV 4.1-mile double-circuit transmission line by replacing the aging conductor. |  | Bergheim | Fair Oaks Ranch/Kendall | Planned | 61406, 61358, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-07-18 |  | 345 | 0 | 4.1 | 0 |  | Comal | Kendall | Tier 4 | 22RPG005 | 2022-03-04 |  |  | 7046, 7170, 7169, 7770 | Y | N |  | 0 | 61393 | 61392
69473 | Jaguar: Construct New Distribution Station | Jaguar: Construct New Distribution Station | In-Service Date Update | Jaguar |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2025-07-31 |  | 138 | 0 | 0 | 40 |  | Victoria |  | Tier 4 |  |  |  |  | 8724, 8183, 8194 | Y |  |  | 0 | 69474 | 69473
72942 | Bluff Creek: 138 kV Station Work | Replace fourteen (14) 138 kV Breakers and one (1) Circuit Switcher | In-Service Date Update | Bluff Creek |  | Planned |  | AEP TNC | Alex Perkins twang1@aep.com 918-599-2635 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 66216, 66217, 6216, 6260, 6351, 180455, 180463, 60040, 60043 | Y | N |  | 0 | 72943 | 72942
61406 | Kendall-Welfare Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T584 Kendall to Welfare 138-kV and T656 Bergheim to Kendall 345-kV 10.2-mile double-circuit transmission line by replacing the aging conductor. |  | Kendall | Welfare | Planned | 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-08-25 |  | 138 | 0 | 10.2 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7046, 7152, 7153, 7770 | Y | N |  | 0 | 78330 | 61406
49550 | Port Isabel: Rebuild As GIS Station | Rebuild Port Isabel as a GIS | In-Service Date Update | Port Isabel |  | Planned | 958 - 1136 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3716 | 2025-08-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8338, 8744 | Y | N |  | 0 | 49551 | 49550
76624 | WA Parish 345kV Substation Expansion for Crowned Heron Storage (24INR0405) | Expand 345kV WA Parish substation for Crowned Heron Storage (24INR0405) |  | WA Parish | HERON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-08-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  | 0 | 76625 | 76624
75958 | add 19.2 MVAR Capacitor at Rio Colorado | Adds 2 9.6 MVAR step caps at Rio Colorado |  | Rio Colorado |  |  |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-09-01 |  | 69 | 0 | 0 | 0 | 0,19.2 |  |  | Tier 4 |  |  |  |  | 5563 | Y |  |  | 0 | 75959 | 75958
66200C | Upgrade Taylor - Holland 69 kV Line | Rebuild the Bartlett - Granger 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6173 | 2025-09-15 |  | 69 | 0 | 6.9 | 0 |  | Williamson | Williamson | Tier 4 | 22RPG036 |  |  |  | 3647, 3648 | Y |  |  | 0 | 71896 | 66200
66202A | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Palestine - Elkhart 69 kV Line |  | Palestine | Elkhart | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6182 | 2025-09-15 |  | 69 | 0 | 9.8 | 0 |  | Anderson | Anderson | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3273, 3285 | Y |  |  | 0 | 66203 | 66202
66210 | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV. Relocate the Lake Creek 138/69 kV Auto to Marlin. |  | Lake Creek | Marlin | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1743 | 2025-09-15 |  | 138 | 0 | 13.7 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3411, 3416, 3418, 3694, 3695, 3410, 13639 | Y |  |  | 0 | 66211 | 66210
73063 | Big Foot to Lytle: Convert to 138 kV | Convert the Big Foot to Lytle 69 kV line to 138 kV and interconnect Rowan Digital to the Lytle 138 kV station | Project Title, Project Description, Company Contact, Cost, Trans Circuit Miles New, Reactive Capability Added Update | Big Foot | Lytle | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022155 | 2025-09-20 |  | 138 | 0 | 12 | 0 | 23,0 | Medina | Frio | Tier 4 |  |  |  |  | 8223, 8622, 8732, 8208, 8216, 8962, 8218, 8221, 58280 | Y |  |  | 0 | 73064 | 73063
76242 | Lytle: Build new 138 kV terminal | Convert the Big Foot to Lytle 69 kV line to 138 kV and interconnect Rowan Digital to the Lytle 138 kV station |  | Lytle |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022155 | 2025-09-20 |  | 138 | 0.1 | 0 | 0 | 0,23 | Medina |  | Tier 4 |  |  |  |  | 8962 | Y |  |  | 0 | 76243 | 76242
50878 | North Edinburg: 345 kV Reconfigure | North Edinburg: 345 kV Reconfigure |  | North Edinburg |  | Planned | 1056 - 1229 | AEP TCC | Rich Haley mlforcum@aep.com 918-599-2674 | 3786 | 2025-09-30 |  | 345 | 0 | 0 | 0 | -100,0 | Hidalgo |  | Tier 4 |  |  |  |  | 8341, 8383 | Y | N |  | 0 | 50879 | 50878
59197 | Mason to Mason Switch: Rebuild 69 kV Line | Rehab the Mason to Mason Switch 69 kV Line | In-Service Date Update | Mason | Mason Swicth | Planned | 1126 - 1304 | AEP TNC | Brian Oyster twang1@aep.com 918-599-2635 | 1871 | 2025-09-30 |  | 69 | 0 | 10.3 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6394, 60458, 6393, 6396, 6407 | Y | N |  | 0 | 59198 | 59197
69890 | Bailey 345kV Substation Expansion for Ray Gulf Wind (22INR0517) | Expand 345kV Bailey substation for Ray Gulf Wind generator interconnection (22INR0517) |  | Bailey |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-09-30 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 | [5 empty] | Y | N |  |  | 69891 | 69890
73067 | Marina: Construct New Station | Construct new network station on the Highway 9 to Morris St and Nueces Bay 138 kV Line |  | Marina |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-09-30 |  | 138 | 0 | 8 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8733, 8064, 8441, 8470, 8474, 8623, 8620 | Y |  |  | 0 | 73068 | 73067
76139 | Juncus Interconnection | Build an interconnection for a 13 MW load on the Abilene South to Steamboat 69 kV Circuit. | Transmission Owner and In-Service Date Update | Juncus |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2023074 | 2025-09-30 |  | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 60002, 6326, 6328 | Y | Y |  | 0 | 76140 | 76139
76214 | North Edinburg: 345 kV Reconfigure | Reconfigure North Edinburg 345 kV station: 2nd reactor | In-Service Date Update | North Edinburg |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2019168 | 2025-09-30 |  | 345 | 0 | 0 | 0 | -50,0 | Hidalgo |  | Tier 4 |  |  |  |  | 5660, 8383, 8455, 8901, 8452, 8905, 8341 | Y |  |  | 0 | 76215 | 76214
77144 | Pompano: New 138 kV Station | New station for Next Decade/ Rio Grande LNG | In-Service Date Update | Pompano |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2015151 | 2025-09-30 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8535, 8337, 79601 | Y |  |  | 0 | 77145 | 77144
78427A | Bohemian (BOH) 138kV CEHE Substation for Destiny Storage (24INR0397) | Install new CEHE 138kV Bohemian (BOH) substation for generator interconnection to Destiny Storage. Loop Ckt.66K into substation to create new Ckt.66 Crosby to Bohemian to Eastgate. |  | Bohemian | Crosby/ Eastgate | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-09-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40970, 40390, 40690 | Y | N |  | 0 | 78428 | 78427
78471 | WA Parish 345kV Substation Expansion for Bypass Storage (23INR0336) | Expand 345kV WA Parish substation for Bypass Storage (23INR0336) |  | WA Parish | BYPASS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-09-30 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  | 0 | 78472 | 78471
80466 | Oleander: Construct New 138 kV Terminal | Interconnect Citrus Flatts BESS to the Oleander 138 kV station |  | Oleander |  | Planned |  | AEP | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-09-30 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 | [5 empty] | Y |  |  | 0 | 80467 | 80466
78427B | Bohemian (BOH) 138kV CEHE Substation for Destiny Storage (24INR0397) | Install generator lead from Bohemian (BOH) substation to Rhapsody / RHAPSO (RHA) / Destiny Storage |  | Rhapsody | Bohemian | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-09-30 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | 0 | 78429 | 78427
70714 | LCRATSC_La_Cima_Substation_Addition | Add new substation to 138 kV line between Ranch Road 12 and Hill Top and install 46.7 MVA distribution transformer. The new substation will be located approximately 0.30 miles from Ranch Road 12 substation. |  | Ranch Road 12 | La Cima | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org (512) 578-4514 |  | 2025-10-01 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7185, 7186, 7190 | Y | N |  | 0 | 70715 | 70714
78627 | RCEC_SherwoodShores_AddCap |  |  |  |  | Planned |  | RYBRN | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6806 | Y |  |  | 0 | 78628 | 78627
70012 | West Weatherford to Oran Voltage Conversion | West Weatherford to Oran Voltage Conversion |  | West Weatherford | Oran | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-10-03 |  | 138 | 0 | 0.1 | 0 |  | Palo Pinto | Parker | Tier 4 |  |  |  |  | 515, 518, 519, 785, 1578, 1585, 1589 | Y |  |  | 0 | 70013 | 70012
80484 | Closner: Construct New 138 kV Terminal | Interconnect Gunnar BESS to the Closner 138 kV station. | NEW | Closner |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-10-18 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8029 | Y |  |  | 0 | 80485 | 80484
80486 | Loxley: Construct New 138kV Station | Interconnect the Loxley load to the new Loxley 138kV station on the Pleasanton to Trumbo 138kV Line. | New Project | Loxley |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-10-18 |  | 138 | 0.1 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  |  | 80491, 5429, 8203 | Y |  |  | 0 | 80487 | 80486
72344 | PALMETTO_CUTIN |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-10-23 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39510, 39500, 110505 | Y |  |  | 0 | 72345 | 72344
59959 | CPSE_New_Old_Hickory_Switchyard | Build a new Old Hickory 345 switchyard to connect Old Hickory Solar plant. |  | 5133 | 5915 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0303; S-0940 | 2025-10-24 20:00 |  | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5323, 5133, 5915 | Y |  |  | 0 | 59960 | 59959
80852 | Lolita: Construct New 138 kV Terminal | Interconnect Third Coast BESS to the Lolita 138 kV station | NEW | Lolita |  | Planned | TP2023138 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-10-30 |  | 138 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 8125 | Y | N |  | 0 | 80853 | 80852
64581A | New 138kV Waterfowl substation | Reconfigure existing Ckt.02F (move Seadoc/Seaway onto other circuit) resulting in Ckt.36 COPPER to Booster tap to Jones Creek. |  | COPPER | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 43212, 43221, 48006, 48333, 48334, 5568, 42195, 42199, 42540, 43211, 48007, 48039, 42215 | Y | N |  | 0 | 82981 | 64581
66122 | Tiempo: Build new 345 kV terminal | Interconnect Redonda Solar to the Tiempo 345 kV station | In-Service Date Update | Tiempo |  | Planned |  | ETT TCC | Adam Wells mlforcum@aep.com 918-599-2674 | TP2022009 | 2025-10-31 |  | 345 | 0.1 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 80224, 80232 | Y |  |  | 0 | 66511 | 66122
72059 | Hillje 345kV Substation Expansion for Ramsey Storage - Generator Interconnection to FLATLA (FLA) (21INR0505) | Expand Hillje 345kV substation and install one generator lead for new interconnection to FLATLA (FLA) customer substation for Ramsey Storage |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 72060 | 72059
75810A | Install new 345kV Speedway substation for interconnection to Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. Install generator lead from Speedway to CRADLE solar | Install new 345kV Speedway (SPD) substation for generator interconnection to CRADLE/ Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. |  | Speedway | DOW/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43060, 42500, 43035 | Y | N |  | 0 | 75812 | 75810
75810B | Install new 345kV Speedway substation for interconnection to Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. Install generator lead from Speedway to CRADLE solar | Install generator lead from Speedway (SPD) substation to CRADLE (CDL) customer substation (23INR0150). |  | Speedway | CRADLE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 75813 | 75810
78480A | Weinbrenner (WEI) 138kV CEHE Station for LONGPO (LNP) / Long Point Solar 19INR0042 | Loop new CEHE 138kV substation Weinbrenner (WEI) into Ckt.02J Burke to Eagle Nest to create new Ckt.02 Burke to Weinbrenner to Eagle Nest. |  | Weinbrenner | Burke/ Eagle Nest | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42990, 42410, 42430 | Y | N |  | 0 | 82803 | 78480
64581B | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Reconfigure existing Ckt.02F and install new conductor to create new Ckt.02 Jones Creek to Waterfowl |  | Jones Creek | Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 43470, 42540 | Y | N |  | Cost included in main entry | 82982 | 64581
78480B | Weinbrenner (WEI) 138kV CEHE Station for LONGPO (LNP) / Long Point Solar 19INR0042 | Install one generator lead from CEHE 138kV substation Weinbrenner (WEI) to LONGPO (LNP) / Long Point Solar (19INR0042) |  | Weinbrenner | LONGPO | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 82804 | 78480
64581C | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Convert customer-owned Seadoc and Seaway substations to loop service. Reconfigure existing Ckt.02F and reconnect Seadoc/Seaway to create new Ckt.02x Jones creek to Seadoc to Seaway to Waterfowl. |  | Jones Creek | Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 43211, 43222, 48007, 42540, 43470 | Y | N |  | Cost included in main entry | 82983 | 64581
64581D | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Remove existing Seaway Switchrack. Reconfigure existing Ckt.02F to create new Ckt.02y Waterfowl to Franklins Camp. |  | Waterfowl | Franklins Camp | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 5568, 43470 | Y | N |  | Cost included in main entry | 82984 | 64581
80508 | Kilby: Construct New 345 kV Station | Interconnect Quantum Solar to the new Kilby 345 kV station on the Clear Crossing to Pendulo 345 kV line | NEW | Kilby |  | Planned | TP2023844 | ETT TNC | Michael Glueck twang1@aep.com 918-599-2635 |  | 2025-11-01 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60089, 60507, 60514 | Y | N |  | 0 | 80509 | 80508
78167 | Add 2nd autotransformer at Trumbull | Add 2nd autotransformer at Trumbull |  | Trumbull | Trumbull | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-11-15 |  | 69 | 0 | 0 | 40 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 222, 221 | Y |  |  | 0 | 78168 | 78167
6572 | Ballinger to Eden 69 kV line: Rebuild taps | Rebuild Taps on the Ballinger to Eden 69 kV line | Contact, Schedule Update | Ballinger | Eden | Planned | 890 - 1068 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 2814 | 2025-11-30 |  | 69 | 0 | 2.8 | 0 |  | Runnels | Concho | Tier 4 |  |  |  |  | 6338, 6369, 6370, 6372, 6376 | Y | N |  | 0 | 65513 | 6572
61394 | Portilla: Construct New Distribution Station | Construct New Distribution Station on the Lon Hill to Warburton 138 kV Line | In-Service Date Update | Portilla |  | Planned |  | AEP TCC | Damian Raab mlforcum@aep.com 918-599-2674 | DP21X0008 | 2025-11-30 |  | 138 | 1.5 | 0 | 0 | 0,14.4 | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8020, 8046, 8924, 8027, 8920 | Y |  |  | 0 | 61395 | 61394
63924 | Quasar: Build New 345 kV Station | Interconnect Brass Fork Solar to the Clear Crossing to Coulomb 345 kV Line | In-Service Date and Estimated Cost Update | Quasar |  | Planned | 1138 - 1316 | ETT TNC | Zach Lachiusa twang1@aep.com 918-599-2635 | 1883 | 2025-11-30 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60712, 60514, 60703 | Y | N |  | 0 | 63925 | 63924
72566 | Cedar Valley to Friendship Storm Hardening | Rebuild single circuit section of Cedar Valley to Friendship and reconductor with bundled 795 ACSR Conductor, 440 MVA. Replaces Project ID 61268 |  | Cedar Valley | Friendship | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-11-30 |  | 138 | 0 | 4.3 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70506, 70507 | Y | N |  | 0 | 72567 | 72566
72579A | PEC_MountainTop_Blanco_DevilsHill_VoltageUpgrade | Rebuild and upgrade Mountain Top to Blanco 69 kV circuit to 138 kV with bundled 795 kcmil conductor (440 MVA). (Replaces ERCOT Project # 70367A) |  | Mountain Top | Blanco | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-11-30 |  | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 | 22RPG033 |  | 2022-11-14 |  | 70480, 70482, 7148, 70484 | Y | Y |  | 0 | 72580 | 72579
73359 | Vertrees: Construct New Distribution Station | Construct new distribution station on the Stewart Rd to Weslaco Unit 138 kV Line | In-Service Date Update | Vertrees |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-11-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8662, 8737, 8348, 8951 | Y |  |  | 0 | 73360 | 73359
80482 | North McAllen: Construct New 138 kV Terminal | Interconnect Carambola BESS to the North McAllen 138 kV station | New Project | North McAllen |  | Planned | TP2023631 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-11-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8632 | Y |  |  | 0 | 80483 | 80482
48818 | Ballinger: Rebuild 138 kV Station | Rehab the 138/69 kV autotransformer at Ballinger | Contact, Schedule Update | Ballinger |  | Planned | 1016 - 1194 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 2777 | 2025-11-30 01:00 |  | 138 | 0 | 0 | 130 |  | Runnels |  | Tier 4 |  |  |  |  | 6338, 6340 | Y | N |  | 0 | 65537 | 48818
70299 | New Holleman Substation | [6 empty] | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 32892, 32005, 32893 | Y |  |  | 0 | 78212 | 70299
70880 | Rebuild Carancahua -TinTop | Rebuild Carancahua to TinTop with 795ACSR |  | Carancahua | Tin Top | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 69 | 0 | 12.93 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5569, 5570, 5571, 5573 | Y |  |  | 0 | 70881 | 70880
71926 | Upgrade BURNS to Heidelberg line | Upgrade BURNS to Heidelberg line to be 478MVA capable |  | Burns | Heidelberg | Planned | 7192871930 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 138 | 0 | 10 | 0 |  | Cameron | Hidalgo | Tier 4 |  |  |  |  | 5763, 5765 | Y |  |  | 0 | 71927 | 71926
76768 | Upgrade Pearson -Pearsall | Upgrade the Pearson-Natalia-Devine-Moore-Pearsall to 795 ACSR |  | Pearson | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 69 | 0 | 22.24 | 0 |  | Frio | Medina | Tier 4 |  |  |  |  | 5811, 5828, 5830, 5858, 58570, 5857, 5893 | Y |  |  | 0 | 76769 | 76768
76788 | Upgrade Victoria-Rayburn | Upgrade Victoria- Loop 463- Rayburn to 403 MVA |  | Rayburn | Victoria | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 138 | 0 | 11.57 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5502, 5680, 8172 | Y |  |  | 0 | 76789 | 76788
76816 | Upgrade Loyola Auto | Upgrade Loyola Auto |  | Loyola | Loyola | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5648, 5650 | Y |  |  | 0 | 76817 | 76816
78478 | Rebuild Oaks to Poteet to Pearsall 69 kV line | Rebuild Oaks to Poteet to Pearsall 69 kV line from 4/0 to 795. 2023 RTP |  | Oaks | Pleasanton | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 69 | 0 | 18.5 | 0 |  |  |  | Tier 2 |  |  | 2020-05-21 |  | 5710, 5712, 5893 | Y | N |  |  | 78479 | 78478
78483 | Rebuild Nada to El Campo 69 kV line | Rebuild Nada to El Campo 69 kV line from 4/0 to 795. 2023 RTP |  | Nada | El Campo | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 69 | 0 | 15.44 | 0 |  | Colorado | Wharton | Tier 4 |  |  |  |  | 5536, 5538 | Y | N |  |  | 78484 | 78483
82851 | Adds TNMP White Oak Substation |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-12-01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39580 | Y |  |  | 0 | 82852 | 82851
80630 | Angstrom - STP LOCs | Angstrom - STP LOCs |  |  |  | Planned | TA2024200 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2025-12-02 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5915, 8249, 8676 | Y |  |  | 0 | 80631 | 80630
5475 | Lufkin Switch - Redland Switch 345 kV Line | Construct a new 345 kV Line from Lufkin Switch to Redland Switch |  | Lufkin Switch | Redland Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6077 | 2025-12-15 |  | 345 | 8.1 | 0 | 0 |  | Angelina | Angelina | Tier 2 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3117, 3321 | Y | N |  |  | 13180 | 5475
5526 | Forney 345/138 kV Switch | Rebuild existing 345/138 kV switching |  | Forney |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4114 | 2025-12-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 3 |  |  |  |  | 22438, 2437, 2438 | Y | N |  | 0 | 78356 | 5526
62445 | Base Camp (FKA Eagle Mountain) 138kV Switch Rebuild | Rebuild existing 138 kV Switch |  | Eagle Mountain |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5261 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 1859, 1860, 11859, 11860, 11861, 11864, 11865, 11866, 568, 1864, 1865, 12065 | Y |  |  | 0 | 70920 | 62445
66190 | East Levee - Industrial Blvd 138 kV DCKT Line | Rebuild East Levee - Industrial Blvd 138 kV DCKT Line |  | East Levee | Industrial | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4213 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2481, 2482, 2875, 2974, 2874, 2876, 2976 | Y |  |  | 0 | 66191 | 66190
66214 | Upgrade and convert Brownwood - Firerock 69 kV Line to 138 kV | Upgrade and convert Brownwood - Firerock 69 kV Line to 138 kV |  | Brownwood | Firerock | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6164 | 2025-12-15 |  | 138 | 0 | 15.5 | 0 |  | Brown | Brown | Tier 4 |  |  |  |  | 1671, 1661, 1670, 1662, 6359, 6408 | Y |  |  | 0 | 66215 | 66214
66218B | Hillsboro - Italy 69 kV Line | Rebuild the Milford-Italy 69 kV Line |  | Milford | Italy | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4326 | 2025-12-15 |  | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  | 2021-04-23 | 2021-05-18 |  | 2337, 2338 | Y |  |  | 0 | 73690 | 66218
66289A | Upgrade and convert Tyler - Athens 69 kV Line | Rebuild the Chandler West - Structure 29/2 69 kV Line |  | Chandler West | Murchison | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6094 | 2025-12-15 |  | 69 | 0 | 21.3 | 0 |  | Henderson | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3236, 3238, 3239, 3108, 3801, 13235 | Y |  |  | 0 | 77176 | 66289
66473 | Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line | Upgrade the Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line |  | Mesquite East | Oates | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4137 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 831, 2742, 2747, 2756, 2764, 2765, 2766, 2767 | Y |  |  | 0 | 66475 | 66473
66492A | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Jacksboro Amoco - Jacksboro Sinclair 69 kV Line |  | Jacksboro Sinclair | Jacksboro Amoco | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3006 | 2025-12-15 |  | 69 | 0 | 14 | 0 |  | Jack | Jack | Tier 4 |  |  |  |  | 1542, 1555, 1556, 1557, 1558, 11556 | Y |  |  | 0 | 72962 | 66492
68681 | Lamar Blossom Switch - Clarksville 69 kV Line Rebuild | Rebuild the existing 69 kV Line |  | Lamar | River Crest | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5325 | 2025-12-15 |  | 69 | 0 | 0 | 0 |  | Lamar | Red River | Tier 4 |  |  |  |  | 1772, 1785, 11784 | Y |  |  | 0 | 68682 | 68681
70900C | Roanoke Area Upgrades | Establish Dunham 345 kV Switch |  | Dunham Switch | Dunham Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5281 M5144 M5146 M5148 | 2025-12-15 |  | 345 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 21851, 646, 1730, 1849, 33646 | Y | N |  | 0 | 72015 | 70900
70900D | Roanoke Area Upgrades | Establish Ramhorn Hill 345 kV Switch and Ramhorn Hill – Dunham 345 kV Double-Circuit Line |  | Dunham Switch | Ramhorn Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5281 M5144 M5146 M5148 | 2025-12-15 |  | 345 | 36.8 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 31875, 1421, 2081, 21851 | Y | N |  | 0 | 72016 | 70900
71178 | Seagoville-Watermill 138 kV Line | Rebuild Seagoville-Watermill 138 kV Line |  | Seagoville | Watermill | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4081 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 2429, 2434, 3076, 3077, 3079, 3083 | Y |  |  | 0 | 71179 | 71178
71903 | Establish Launch Pad 138 kV Switch | Establish Launch Pad 138 kV Switch |  | Launch Pad | Launch Pad | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6156 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3594, 3709, 3372, 3593, 3601 | Y |  |  | 0 | 71904 | 71903
72007 | Ranger Camp 345/138 kV Switch | Construct a new 345/138 kV Switch to replace existing Morgan Creek Switch |  | Ranger Camp 345/138 kV Switch | Ranger Camp 345/138 kV Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3024 | 2025-12-15 |  | 345 | 0 | 0 | 1200 |  | Mitchell | Mitchell | Tier 1 |  |  |  |  | 10049, 10050, 10051, 10052, 11004, 1025, 1030, 1032, 1033, 1064, 1189, 1378, 1190, 1348, 11048, 11332, 11342, 11393, 11032, 11033, 11034, 11035 | Y |  |  | 0 | 81363 | 72007
72009 | Cattleman 345/138 kV Switch | Construct a new 345/138 kV Switch to replace existing Morgan Creek Switch |  | Cattleman | Cattleman | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8647 | 2025-12-15 |  | 345 | 0 | 0 | 1200 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10053, 10054, 10055, 10056, 1030, 1058, 18548, 11395 | Y |  |  | 0 | 81376 | 72009
75255F | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-12-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5260, 5385 | Y |  |  | 0 | 75960 | 75255
76135 | Hackberry Switch – DFW D-East 2 138 kV DCKT Line Section | Rebuild Hackberry Switch – DFW D-East 2 138 kV DCKT Line Section |  | Dallas | Dallas | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4347 M4357 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 | 23RPG020 |  |  |  | 1996, 1997, 2001, 2010, 15020, 15021, 2388, 15025, 15026, 15045, 15046 | Y |  |  | 0 | 76136 | 76135
76572 | Temple - Temple Pecan 138 kV 2nd Circuit | Temple - Temple Pecan 138 kV 2nd Circuit |  | Temple | Temple Pecan Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6235 | 2025-12-15 |  | 138 | 0 | 4.4 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3415, 3420 | Y |  |  | 0 | 76573 | 76572
76660 | Rebuild Temple Switch and install auto #2 | Rebuild Temple Switch and install auto #2 |  | Temple | Temple | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6197 | 2025-12-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 1 |  |  |  |  | 3718, 3415, 13415, 3414 | Y |  |  | 0 | 76661 | 76660
78363 | Gunter 345/138 kV Switch | Establish Gunter 345/138 kV Switch |  | Gunter |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3301 | 2025-12-15 |  | 345 | 0 | 0 | 600 | 75,0 | Collin |  | Tier 3 |  |  |  |  | 2235, 2236, 12235, 1730, 2373, 11757, 11735, 12468 | Y |  |  | 0 | 78364 | 78363
78367 | Montfort Switch-Shankle Switch 138 kV Line | Rebuild Montfort Switch - Shankle Switch 138 kV Line |  | Montfort | Shankle | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4002 | 2025-12-15 |  | 138 | 0 | 18 | 0 |  | Navarro | Ellis | Tier 3 |  |  |  |  | 192, 2330, 2331, 3454, 12329 | Y |  |  | 0 | 78368 | 78367
78369 | Rebuild Sam Switch - Venus Switch 345 kV DCKT | Rebuild Sam Switch - Venus Switch 345 kV DCKT |  | Venus | Sam | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6293 | 2025-12-15 |  | 345 | 0 | 76 | 0 |  | Ellis | Hill | Tier 1 |  |  |  |  | 1906, 1907, 3374, 3389, 68090 | Y |  |  | 0 | 78370 | 78369
81060 | Riverton-Border-Quarry Field 138 kV Second Circuit | Riverton-Border-Quarry Field 138 kV Second Circuit |  | Riverton | Quarry Field | Planned | R8733 | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 |  | 2025-12-15 |  | 138 | 29.7 | 0 | 0 |  | Reeves | Loving | Tier 4 |  |  |  |  | 11083, 11089, 11356, 11189, 18672 | Y |  |  | 0 | 81062 | 81060
81063 | Progress Park 138 kV Switch | Establish Progress Park 138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3067 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Grayson |  | Tier 4 |  |  |  |  | 12678, 12677, 1699 | Y |  |  | 0 | 81065 | 81063
81175 | Salt Flat Road 138 kV Switch and Salt Flat Road - Barr Ranch - Reiter 138 kV Second Circuit | Add Salt Flat Road 138 kV Switch and Salt Flat Road - Barr Ranch - Reiter 138 kV Second Circuit |  | Reiter | Salt Flat Road | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8704 | 2025-12-15 |  | 138 | 44 | 4.4 | 0 |  | Ector | Midland | Tier 3 |  |  |  |  | 1276, 18545, 18701, 1027, 1111, 1193, 1197, 1234, 11111, 11217, 11235, 11344, 10001, 23859 | Y |  |  | 0 | 81176 | 81175
81223 | Morgan Creek CT Yard 138 kV Switch | Construct a new 138 kV switch replacing existing Morgan Creek 138 kV Switch. |  | Morgan Creek CT Yard 138 kV Switch | Morgan Creek CT Yard 138 kV Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3024 | 2025-12-15 |  | 345 | 0 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1032 | Y |  |  | 0 | 81367 | 81223
81389 | Sandhills Tap - Wolf 138 kV Line Rebuild | Sandhills Tap - Wolf 138 kV Line Rebuild |  | Odessa EHV | Wolf | Planned | R8528 | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 |  | 2025-12-15 |  | 138 | 0 | 14.2 | 0 |  | Ector | Ward | Tier 3 |  |  |  |  | 11018, 1013, 1103 | Y |  |  | 0 | 81390 | 81389
81551 | Dos Rios 138 kV Switch | Establish Dos Rios 138 kV Switch |  | Dos Rios Switch | Dos Rios Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6231 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3725, 32, 3707 | Y |  |  | 0 | 81552 | 81551
71985 | Cypress Water 138 kV Switch | Rebuild the existing Northlake(Cypress Waters) 138 kV Switch |  | Northlake |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4353 | 2025-12-16 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 |  |  |  |  | 2367, 2385, 2362, 2363, 2386, 2390, 2395, 2587 | Y |  |  | 0 | 73110 | 71985
76652 | Line Termination at Cypress Waters | Vineyard Switch – Hackberry Switch 138 kV Line Termination at Cypress Waters 138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5344 | 2025-12-16 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2017, 2386, 2392 | Y |  |  | 0 | 76653 | 76652
81274 | Ranger Camp – Cattleman 345 kV Double-Circuit Line | Construct a new 345 kV double-circuit line from Ranger Camp to Cattleman |  | Ranger Camp | Cattleman | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3024 | 2025-12-16 |  | 345 | 6.8 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10049, 10053 | Y |  |  | 0 | 81275 | 81274
61449 | Clark Church (Ottine New) Substation | Build New 69/138 Substation by Birdhouse to Replace existing Ottine station, add 20MVA; demo existing Ottine substation |  | Ottine | Ottine | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-12-19 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7594 | Y | N |  | 0 | 61450 | 61449
72574 | topo_update | Upgrade Junction from tap station to a three terminal ring bus. Replaces Project ID 63916. | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-12-25 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70600 | Y |  |  | 0 | 80916 | 72574
70305 | Camp Elizabeth: Build new 69 kV station | Construct new 69 kV box bay station with capacitor bank on the College Hills West to Sterling City 69 kV line | Schedule Update | Camp Elizabeth |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-12-30 |  | 69 | 0 | 0 | 0 | 0,7.7 | Sterling |  | Tier 4 |  |  |  |  | 6436, 6641, 6417, 6435, 11352 | Y | N |  | 0 | 70306 | 70305
76196 | Lobo: 138 kV Breaker Replacement | Replace Lobo 138 kV CBs | Schedule Update | Lobo |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2023015 | 2025-12-30 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80221 | Y |  |  | 0 | 76197 | 76196
81270 | Construct the new Prong Moss 345 kV switch | Construct a new 345 kV switch |  | Prong Moss | Prong Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3025 | 2025-12-30 |  | 345 | 0 | 0 | 0 |  | Howard | Howard | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10057, 1025, 10049, 10062, 6561025 | Y |  |  | 0 | 81271 | 81270
65683 | To add Open Sky Station | To interconnect GINR 20INR0241 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68014, 68001, 68004 | Y | N |  | 0 | 65684 | 65683
68183 | Estes to Putnam: Rebuild 138 kV line | Rehab the Abilene South to Putnam 138 kV line | In-Service Date and Estimated Cost Update | Estes | Putnam | Under Construction | 68150 | AEP TNC | Michael Glueck twang1@aep.com 918-599-2635 |  | 2025-12-31 |  | 138 | 0 | 15 | 0 |  | Callahan | Callahan | Tier 4 |  | 2022-02-01 | 2022-03-01 | 2022-03-01 | 6309, 60365, 61015 | Y | N |  |  | 68184 | 68183
70307 | BRYN_Standard_PMCR_Dansby_Rebuild_fix | Reference Project 4577 Dansby Rebuild. Project 4577 was added to convert Dansby 69kV bus to Breaker and a Half configuration. |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-12-31 |  | 69 | 0 | 0 | 200 |  | Brazos |  | Tier 4 |  |  |  |  | 32875, 32897 | Y |  |  | 0 | 75508 | 70307
72040 | Blueridge to WA Parish Ckt.02A Upgrades (22RPG041) | Upgrade portions of Ckt.02A Blueridge tap to WA Parish as a Hardening upgrade |  | HO Clarke | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 138 | 0 | 9.08 | 0 |  | Harris | Harris | Tier 4 | 22RPG041 | 2022-11-21 | 2022-12-15 | 2022-12-15 | 44180, 48163, 48302, 48335 | Y | N |  | 0 | 72473 | 72040
72063 | Moody to Stewart Ckt.63 Upgrades P1041 | Reconductor portions of Ckt.63 Stewart to West Galveston as a Hardening project |  | Stewart | West Galveston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 345 | 0 | 4.03 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42950, 42951, 43400 | Y | N |  | 0 | 72064 | 72063
72268 | CPSE_New Ingram Rd Substation | [6 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Bexar |  | Tier 4 |  |  |  |  | 5241, 5102, 5346 | Y |  |  | 0 | 72269 | 72268
72868 | LCRATSC_Benedum_CB_Addition | This project provides a point of interconnection for a new 307.46 MW Battery Energy Storage at the 138-kV Benedum Substation by adding a connection to the ring bus to accommodate the new interconnection. Update contingencies |  | Benedum |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-12-31 |  | 138 | 0.1 | 0 | 0 |  | Upton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 78297 | 72868
73065 | Magana Hein: Build new 138 kV distribution station | Build new distribution station on the Molina to Wormser Road 138 kV line | In-Service Date Update | Magana Hein |  | Planned |  | AEP TCC | Travis Coody mlforcum@aep.com 918-599-2674 |  | 2025-12-31 |  | 138 | 2.6 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8801, 8295, 8641, 8646, 80230 | Y |  |  | 0 | 73066 | 73065
73123 | LCRATSC_SimGideon_Swiftex_TL_Upgrade | LCRA TSC will upgrade T608 Sim Gideon - Swiftex 138-kV transmission line to achieve a higher operational rating. |  | Sim Gideon | Swiftex | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org (512) 578-4514 |  | 2025-12-31 |  | 138 | 0 | 10 | 0 |  | Bastrop | Bastrop | Tier 3 |  |  |  |  | 7310, 7319, 7326 | Y | N |  | 0 | 73124 | 73123
73332 | Install Hermann (HER) Distribution Substation | Install Hermann (HER) Distribution Substation. Loop on Ckt.08I to create new Ckt.08 Plaza to Hermann to Grant. |  | Hermann | Plaza/Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45120, 47110, 47350 | Y | N |  | 0 | 73333 | 73332
73352A | PH Robinson Area 138kV Upgrades | Reposition existing PH Robinson to BACLIF generator lead from the PHR_South bus to the PHR_North bus. |  | PH Robinson | BACLIF | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42010, 42015, 111131 | Y | N |  | 0 | 73353 | 73352
73578A | Heights 138kV Loop Conversion | Rebuild/Reconductor Dead Ckt.40Z Str #14606-26374 to prepare for 138kV Conversion. De-energize Ckt.31C Dunlavy to Heights and repurpose as Ckt.09D tap to Dunlavy TR1 load. |  | Dunlavy | Heights | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47581, 47580, 47682 | Y | N |  | 0 | 82606 | 73578
73838 | LCRATSC_Redwood_SanMarcos_TL_Upgrade | LCRA TSC will upgrade T200 Redwood - San Marcos 138-kV transmission line to obtain a higher operational rating. |  | Redwood | San Marcos | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org +151-257-84514 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7188, 7192 | Y | N |  | 0 | 73839 | 73838
75788 | This project will intercept the second circuit of a common tower at Reata station. | This project will intercept the second circuit of a common tower at Reata station. | [5 empty] | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  | Eastland | Eastland | Tier 4 |  |  |  |  | 68008, 68011, 68051 | Y |  |  | 0 | 75789 | 75788
75792 | New substation for generation interconnection project for 21INR0359 | New substation for generation interconnection project for 21INR0359 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 68035, 68040, 68091 | Y |  |  | 0 | 75793 | 75792
82250 | PMCR for PILOT POINT NEW STATION | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37365, 2236 | Y |  |  | 0 | 82251 | 82250
73578B | Heights 138kV Loop Conversion | Repurpose/retire existing 69kV Ckts 34A/34B. Unbundle parallel-bundled portions of Ckt.40A HOC to Dunlavy and reconfigure as unbundled Ckt.40A HOC to Dunlavy and new Ckt.34 HOC to Dunlavy |  | Dunlavy | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 00:01 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47160, 47580 | Y | N |  | 0 | 82607 | 73578
73352C | PH Robinson Area 138kV Upgrades | Upgrade Ckt.79C BIGBAY to BAYOU to increase thermal limits. Request customers to approve 110% Emergency rating of in-series equipment at BBP/BYU. |  | BIGBAY | BAYOU | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42160, 42180 | Y | N |  | 0 | 73355 | 73352
73578C | Heights 138kV Loop Conversion | Reconfigure Eureka to double tap Ckts 09D/73E. Tap Ckt.73E to create new Wirt to Eureka TR1 tap to White Oak. |  | Wirt | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45751, 45750, 44657, 46615 | Y | N |  | 0 | 82608 | 73578
73352D | PH Robinson Area 138kV Upgrades | Upgrade PH Robinson 'North' Bus fault duty to 80KA |  | PH Robinson |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 00:03 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  | 0 | 73356 | 73352
73578D | Heights 138kV Loop Conversion | Repurpose/retire existing 69kV Ckts 34A/34B and convert Heights substation to 138kV service. Reconfigure Ckt.09D to create new Ckt.09D San Felipe to Eureka TR2/TR3 tap to Heights tap to Heights loop to White Oak. Remove existing Heights 7.2 MVAR cap bank from Heights TR1. |  | Heights | San Felipe/White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 00:03 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45750, 45752, 47582, 47680, 47682, 47685, 46615, 46620, 47160, 47581, 47382, 747680 | Y | N |  | 0 | 82609 | 73578
73578E | Heights 138kV Loop Conversion | Remove White Oak auto A2/A4 and remaining 69kV facilities |  | White Oak |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 00:04 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46620, 49021, 49042, 47680, 46615 | Y | N |  | 0 | 82610 | 73578
73578F | Heights 138kV Loop Conversion | Install 7.2MVAR cap bank at Hyde Park TR2. Install 7.2MVAR cap bank at Hyde Park TR3. Install 7.2MVAR cap bank at Dunlavy TR2. |  | Hyde Park/Dunlavy |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 00:05 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47580, 47690 | Y | N |  | 0 | 82611 | 73578
72576B | Lago Vista to Nameless Transmission Line Upgrade | Upgrade final span into Nameless, upgrade terminal equipment, and achieve circuit rating of 440 MVA. (Replaces ERCOT Project #61277B) | 1/10/2023: Added information to clarify circuit rating. | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2026-01-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70352, 70526 | Y | N |  | 0 | 72578 | 72576
72582C | Nameless to Leander Transmission Line Upgrade | Upgrade final span into Nameless, upgrade terminal equipment, and achieve circuit rating of 440 MVA. (Replaces ERCOT Project # 61279C) | 1/10/2023: Added information to clarify circuit rating. | Hero Way | Nameless | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-01-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70526, 70536 | Y | N |  | 0 | 72585 | 72582
81895 | BPUB Branch Changes | Removing branch Price to Loma, adding Price to Stillman, adding another branch Loma Alta to Stillman. |  | 59410, 5962 | 79601, 79601 | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2026-01-01 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5962, 59410, 79601 | Y |  |  | 0 | 81896 | 81895
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0196 | 2026-01-31 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 9559 | 2308
67992D | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade,CPSE_Medina_to_36th_Street_Upgrade | Upgrade Hamilton to Medical Center 138KV Line to 469MVA |  | 5187 | 5300 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5187, 5300 | Y |  |  | 0 | 67994 | 67992
78473A | Odin (ODI) 138kV CEHE Substation | (In terms of completed Waterfowl substation) Loop new CEHE 138kV substation Odin (ODI) into Ckt.36 to create new Ckt.36 COPPER to Odin to Booster tap to Jones Creek. |  | Odin | Brazosport/ Booster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 |  |  |  |  | 42280, 42199, 42215 | Y | N |  | 0 | 78474 | 78473
78473B | Odin (ODI) 138kV CEHE Substation | Install one generator lead from CEHE 138kV substation Odin (ODI) to VALHAL (VAL) / Valhalla Solar (26INR0042) |  | Odin | VALHAL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | [5 empty] | Y | N |  | 0 | 78475 | 78473
50866 | Structure 31/8 - Kenedy SS: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild | In-Service Date Update | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3779 | 2026-01-31 01:00 |  | 138 | 0 | 14.3 | 0 |  | Karnes | Karnes | Tier 3 | 20RPG014 | 2020-08-15 | 2020-09-15 |  | 8186, 8153 | Y | N |  | 0 | 50867 | 50866
79990 | Add new Yellow Wolf station for 21INR0428 |  |  | Limestone | Gibbons Creek | Under Construction |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2026-02-01 |  | 345 | 0 | 0 | 0 |  | Leon |  | Tier 4 |  |  |  |  | 79007, 967, 46020 | Y | N |  | 0 | 79991 | 79990
69479 | Radiant: Build new 345 kV Station | Lunis Creek Solar Interconnect | In-Service Date Update | Radiant |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2026-02-28 |  | 345 | 0.2 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 8715, 5915, 8676 | Y |  |  | 0 | 69480 | 69479
69489 | Shepley: Construct New Distribution Station | Shepley: Construct New Distribution Station | In-Service Date Update | Shepley |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2026-02-28 |  | 138 | 0 | 0 | 50 |  | Victoria |  | Tier 4 |  |  |  |  | 8719, 8143, 8172 | Y |  |  | 0 | 69490 | 69489
80824 | Zenaida: Construct New 138 kV Station | Interconnect Dove Run Solar to the new Zenaida 138 kV station on the Crestonio to Falfurrias 138 kV line | NEW | Zenaida |  | Planned | TP2023843 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-02-28 |  | 138 | 0 | 0 | 0 |  | Duval |  | Tier 4 |  |  |  |  | 80043, 8510, 8695 | Y | N |  | 0 | 80825 | 80824
70882 | Rebuild Olivia - Carancahua | rebuild Olivia sw to Carancahua 795 ACSR |  | Olivia SW | Carancahua | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-03-01 |  | 69 | 0 | 8.71 | 0 |  | Jackson | Matagorda | Tier 4 |  |  |  |  | 5573, 5574 | Y |  |  | 0 | 70883 | 70882
82714 | Rebuild of Airport of Substation | Atlas Substation will be replacing Airport Substation. |  | Filter Plant (BPUB), South Plant (BPUB), and Southmost (STEC) | Atlas (BPUB) | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2026-03-02 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 59440, 5789, 59420, 59500 | Y | N |  |  | 82715 | 82714
73762 | LCRATSC_Peppergrass_Substation_addition | American Electric Power (AEP) is building a new load serving substation and needs transmission service from the LCRA TSC owned 138-kV T470 Abilene South to McElmurray transmission line. LCRA TSC will install a new 138-kV bus and provide transmission service to the new AEP substation. |  | Peppergrass |  | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org (512) 578-451 |  | 2026-03-03 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 76316, 6260, 76317 | Y | N |  | 0 | 73763 | 73762
78169 | Lewisville Switch to Highland | Lewisville Switch to Highland |  | Lewisville Switch | Highland | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-03-15 |  | 138 | 0 | 2.8 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 645, 664 | Y |  |  | 0 | 78170 | 78169
80376 |  |  |  | WEST WEATHERFORD | SHADY GROVE | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-03-15 |  | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 513, 477, 512, 515, 1589 | Y |  |  | 0 | 80377 | 80376
75780A | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy Solar (23INR0057) | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. |  | Elmaton | STP/WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-03-30 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43990, 5915, 44000 | Y | N |  | 0 | 81058 | 75780
80572 | Miel: Construct New 138 kV Station | Interconnect Nightfall Solar to the new Miel 138 kV station on the Razorback to Uvalde 138 kV line | NEW | Miel |  | Planned | TP2023841 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-03-30 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 4 |  |  |  |  | 8747, 8234, 8707 | Y | N |  | 0 | 80573 | 80572
75780B | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy Solar (23INR0057) | Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy Solar (23INR0057) |  | Elmaton | DUFFY | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-03-30 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 81059 | 75780
80830 | Zenaida: Construct New 138 kV Station | Interconnect Sun Cactus Solar to the new Zenaida 138 kV station on the Crestonio to Falfurrias 138 kV line | NEW | Zenaida |  | Planned | TP2023851 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-03-31 |  | 138 | 0 | 0 | 0 |  | Duval |  | Tier 4 |  |  |  |  | 80043 | Y | N |  | 0 | 80831 | 80830
80468 | Conoco: Construct New 138 kV Terminal | Interconnect Isaac Solar to the Conoco 138 kV station |  | Conoco |  | Planned |  | AEP | Glen Reed gareed@aep.com 918-599-2664 |  | 2026-03-31 12:00 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8114, 113651 | Y |  |  | 0 | 80469 | 80468
61444 | Add a new load serving substation about 4.35 miles south of La Vernia along FM 775 | Add a new load serving substation about 4.35 miles south of La Vernia along FM 775, w/40 MVA PWT |  | Wilson South |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-04-30 |  | 138 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 7629, 5418, 7615 | Y | N |  | 0 | 78418 | 61444
64858 | La Palma Expansion | Construct 3 Breaker Ring Bus. Construct 345 kV Line from La Palma 345 kV station to Kingfisher 345 kV (Sharyland) station. |  | La Palma | Kingfisher | Planned |  | AEP TCC/SLU | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2021588 | 2026-04-30 |  | 345 | 6.5 | 0 | 0 |  | Cameron | Cameron | Tier 2 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 79501, 8317, 8383, 79500, 80137 | Y |  |  | 0 | 65264 | 64858
71002 | Tidehaven: Construct New Distribution Station | Tidehaven: Construct New Distribution Station | In-Service Date Update | Tidehaven |  | Planned | 1028 - 1206 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3767 DP21X0007 | 2026-04-30 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8044, 8666, 8119, 8131, 8132, 8121, 8133, 8555 | Y | N |  | 0 | 71003 | 71002
73032 | Mulberry Creek: Rebuild 138 kV Station | Rebuild Mulberry Creek 138 kV station | Projected In-Service Date Update | Mulberry Creek |  | Planned |  | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 |  | 2026-04-30 |  | 138 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6232, 6231, 6288, 6235 | Y | N |  |  | 73033 | 73032
77122 | Mulberry Creek: Construct New 345 kV Terminal | Interconnect the Lancium load to the Mulberry Creek 345 kV station | NEW | Mulberry Creek |  | Planned | TP2023636 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-04-30 |  | 345 | 2.25 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6235 | Y | N |  | 0 | 77123 | 77122
70373 | Driscoll Capacitor addition | adds 3 9.6 MVAR capacitor steps at Driscoll |  | Driscoll |  |  |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 0 | 0 | 0,28.8 |  |  | Tier 4 |  |  |  |  | 5640 | Y |  |  | 0 | 70374 | 70373
71928 | Upgrade Heidelberg to AEP Weslaco line | Upgrade Heidelberg to STEC WESLACO and STEC WESLACO to AEP Weslaco lines to be 478MVA capable |  | Heidelberg | Weslaco | Planned | 7193071926 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 138 | 0 | 8.6 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5765, 5768, 8354 | Y |  |  | 0 | 71929 | 71928
76786 | Upgrade Calallen- Loyola | Upgrade Calallen- Robstown - CC Sw- Driscol-Ricardo-Riviera-Loyola to 959.6 ACSS |  | Calallen | Loyola | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 46.57 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 5626, 5634, 5636, 5640, 5645, 5646, 5650 | Y |  |  | 0 | 76787 | 76786
80907 | Fort Stockton Plant: Rebuild 138/69 kV Station | Rebuild the Fort Stockton Plant 138/69 kV station | NEW | Fort Stockton Plant |  | Planned | TP2023319 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-05-01 |  | 138 | 0 | 0 | 90 |  | Pecos |  | Tier 4 |  |  |  |  | 6630 | Y | N |  | 0 | 80908 | 80907
82840 |  |  |  | HYDRA | Hydroponic | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-05-02 |  | 115 | 3 | 0 | 0 |  | Lubbock | Lubbock | Tier 4 |  |  |  |  | 700, 59122 | Y |  |  | 0 | 82841 | 82840
73366 | CPSE_New_Wiseman_Substation | Loop new 138 kV substation into existing 138kV Cagnon to Helotes Transmission Line. | [5 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-05-08 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5487, 5055, 5200 | Y |  |  | 0 | 73367 | 73366
17TPIT0031 | Elkton 345/138 kV autotransformer | Replace existing autotransformer |  | Elkton | Elkton | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6032-E | 2026-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  |  | 3105, 3106, 29150 | Y | N |  |  | 10501 | 3155
5479 | Trinidad - Tri Corner 345 kV Double-Circuit Line | Upgrade existing DCKT line |  | Trinidad Sw. Sta | TriCorner/Watermill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4045 | 2026-05-15 |  | 345 | 0 | 92.1 | 0 |  | Henderson | Dallas | Tier 3 |  |  |  |  | 2432, 3123, 3124 | Y | N |  |  | 13184 | 5479
5981 | Shamburger North 345/138 kV Sw. Sta. | Establish Shamburger North 345/138 kV Sw. Sta. | Project Deferral | Shamburger North | Shamburger North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6083 | 2026-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  |  | 3217, 3223, 3226, 2485, 3103, 3201, 3206 | Y | N |  |  | 13696 | 5981
5982 | Shamburger North - Shamburger 138 kV Line | Upgrade Shamburger North - Shamburger 138 kV Line | Project Deferral | Shamburger North | Shamburger | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6084 | 2026-05-15 |  | 138 | 10 | 0 | 0 |  | Smith | Smith | Tier 4 |  |  |  |  | 3104, 3206, 3226 | Y | N |  |  | 13697 | 5982
61601 | Add Coody Crossing 345 kV Switch | Add Coody Crossing 345 kV Switch |  | Clear Crossing | Tecumseh Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8560 | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Throckmorton | Throckmorton | Tier 4 |  |  |  |  | 11419, 11418, 60514 | Y |  |  | 0 | 64014 | 61601
66200D | Upgrade Taylor - Holland 69 kV Line | Rebuild the Granger - Taylor 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6173 | 2026-05-15 |  | 69 | 0 | 5.9 | 0 |  | Williamson | Williamson | Tier 4 | 22RPG036 |  |  |  | 3644, 3645, 3646, 3648, 3649, 13646 | Y |  |  | 0 | 71897 | 66200
70900E | Roanoke Area Upgrades | Establish Roanoke_Exchange 138 kV Line |  | Roanoke Switch | Exchange Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5281 M5144 M5146 M5148 | 2026-05-15 |  | 138 | 11.4 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 1854, 12077 | Y | N |  | 0 | 72017 | 70900
71130 | Centerville Switch - Lake Hubbard Switch 138 kV Double-Circuit Line | Upgrade the existing 138 kV Double-Circuit Line |  | Lake Hubbard | Centerville | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4126 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2439, 2450, 2401, 2402 | Y |  |  | 0 | 71131 | 71130
71912A | Rebuild the Killeen Fort Hood - Killeen Taft 138 kV Line | Rebuild the Killeen Fort Hood - Killeen Park Street Tap 138 kV Line |  | Killeen Fort Hood | Killeen Park Street Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6245 | 2026-05-15 |  | 138 | 0 | 3.9 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3626, 3627 | Y |  |  | 0 | 71913 | 71912
73106 | LCRATSC_Lockhart_SanMarcos_TL_Conversion_Updated | The five LCRA TSC-owned transmission line sections from Lockhart to San Marcos will be converted to 138-kV (T220 San Marcos to Camp Gary to Robert Brown Jr., T519 Robert Brown Jr. to Clear Fork, and T601 Clear Fork to Lockhart). |  | Lockhart | San Marcos | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org (512) 578-4514 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Hays | Tier 4 |  |  |  |  | 7191, 7194, 7195, 7196, 7188, 7192, 7215, 7216 | Y | N |  | 0 | 78513 | 73106
76654 | Establish Voss Lake 345/138 kV Switch | Establish Voss Lake 345/138 kV Switch |  | Voss Lake | Voss Lake | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6278 | 2026-05-15 |  | 345 | 0 | 5.6 | 600 | 0,110.4 | Milam | Milam | Tier 3 |  |  |  |  | 3750, 3751, 3752, 3753, 3675, 3678, 3687, 3712, 3717, 13429, 13430 | Y |  |  | 0 | 76655 | 76654
76728 | Skyview 345/138 kV Switch | Establish Skyview 345/138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4350 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 |  |  |  |  | 2119, 2120, 2123, 2127, 2129, 2130, 2131, 2132, 2231, 11938, 1922, 1924, 1927, 2124, 2125, 2128, 2134, 2243, 2244 | Y |  |  | 0 | 76831 | 76728
77174 | Rebuild Old Lake Sw - Ringgold Magnolia 69 kV line | Rebuild Old Lake Sw - Ringgold Magnolia 69 kV line |  | Old Lake Switch | Ringgold Magnolia | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3508 | 2026-05-15 |  | 69 | 0 | 13 | 0 |  | Clay | Montague | Tier 4 |  |  |  |  | 1524, 11541, 11545 | Y |  |  | 0 | 77175 | 77174
78357 | Wilmer 345/138 kV Switch | Establish Wilmer 345/138 kV Switch |  | Wilmer |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4369 M4371 M4372 | 2026-05-15 |  | 345 | 0 | 0 | 1200 | 0,220.8 | Dallas |  | Tier 1 |  |  |  |  | 2344, 3084, 3085, 13082, 23082, 3083, 60017, 2261, 2342, 2427, 2967, 2429, 2432 | Y |  |  | 0 | 78373 | 78357
78408 | LCRA TSC Henne Substation Bus Upgrade | LCRA TSC intends to build a new 138 kV line from Henne to Kohlenberg. LCRA TSC will have to accommodate this line at Henne. Henne substation can be converted to a breaker and half to improve reliability and support the project. |  | Henne | Henne | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7172, 7174, 7173, 7176, 7182 | Y | N |  | 0 | 78411 | 78408
80546B | Upgrade the Hutto Switch - Gabriel Switch 138 kV Line | Rebuild the Gabriel - Salado Line Section Establish Salado Switch and the Salado - Round Rock Line |  | Round Rock Switch | Salado Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6203, R6202 | 2026-05-15 |  | 138 | 0 | 61 | 0 |  | Bell | Williamson | Tier 3 |  |  |  |  | 3764, 3777, 13641, 3677, 13640, 121, 3640, 3664, 3668, 3688, 7346 | Y |  |  | 0 | 81499 | 80546
80921 | Downtown Kyle Substation Addition | [6 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70503, 70198, 70502 | Y |  |  | 0 | 80922 | 80921
81067 | Balch Springs Tap – Balch Springs 138 kV Line Section | Rebuild Balch Springs Tap – Balch Springs 138 kV Line Section |  | Balch Springs Tap | Balch Springs | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4194 | 2026-05-15 |  | 138 | 0 | 3.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2776, 2775, 2777, 2778 | Y |  |  | 0 | 81068 | 81067
81305 | Oncor_FW_Expanse – Tredway 138 kV Line | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Expanse | Tredway | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8681 | 2026-05-15 |  | 345 | 0 | 27.7 | 0 |  | Martin | Martin | Tier 3 |  | 2023-09-29 |  |  | 10090, 10097, 10098, 10110, 10112, 10113, 23835, 23847, 23848, 23880, 11348, 11349, 23838, 1355, 10032, 11338, 11368, 11383, 23829, 11006, 23849 | Y |  |  | 0 | 82491 | 81305
6777 | Establish Division Sub Cedar Hill - Liggett 138 kV Line | Establish Division Sub and Loop Cedar Hill - Liggett 138 kV line in to Great Southwest / General Motors | Project Deferral | Grand Prairie West | Mayfield Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5280 | 2026-05-15 02:01 |  | 138 | 6 | 0 | 0 |  | Dallas | Tarrant | Tier 2 |  |  |  |  | 2143, 12265, 1919, 2137, 2138, 2140, 2265, 2274 | Y | N |  | 0 | 72912 | 6777
6304 | Shamburger North - Shamburger 345 kV Line | Upgrade existing 345 kV Line | Project Deferral | Shamburger North | Shamburger | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6085 | 2026-05-28 |  | 345 | 10 | 10 | 0 |  | Smith | Smith | Tier 3 |  |  |  |  | 3103, 3223 | Y | N |  |  | 14033 | 6304
72568 | Friendship to Rutherford Storm Hardening | Rebuild single circuit section of Friendship to Rutherford and reconductor with bundled 795 ACSR Conductor, 440 MVA. Replaces Project ID 61270. |  | Friendship | Rutherford | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-05-30 |  | 138 | 0 | 4.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70507, 70509 | Y | N |  | 0 | 72569 | 72568
73423 | Buddy Owens: Build new 138 kV Substation | Build new 138 kV substation on Key Switch to North McAllen 138 kV line | Schedule Update | Buddy Owens |  | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-05-30 |  | 138 | 0 | 0 | 80 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8973, 8632, 8773 | Y |  |  | 0 | 73424 | 73423
81006 | Add load at Diabox and thermally uprate Ckt 21 MOMENT-SOLMER-SRB |  |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 40480, 41090, 41400, 41480 | Y | N |  | 0 | 81007 | 81006
76580 | Poblano: Build new 138 kV station | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | Estimated Cost Update | Poblano |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-05-30 02:00 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 8009, 8008, 8234, 8236 | Y |  |  | 0 | 76581 | 76580
44399 | South Padre Island: Rebuild as GIS station | Rebuild South Padre Island as a GIS | In-Service Date Update | South Padre Island | - | Planned | 948 - 1126 | AEP TCC | James Nivens bcogan@aep.com 918-599-2857 | 3712 | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8335, 8917 | Y | N |  | 0 | 44400 | 44399
50890 | Port Lavaca: Station Rebuild (Cangrejo) | Rebuild Port Lavaca (Cangrejo) Station | In-Service Date Update | Port Lavaca |  | Planned | 1057 - 1230 | AEP TCC | Lorraine Timmerman bcogan@aep.com 918-599-2857 | 3787 TA2019045 | 2026-05-31 |  | 69 | 0 | 37.81 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | 8135 | Y | N |  | 0 | 50891 | 50890
58010 | North McAllen: Rebuild 138 kV Station | North McAllen Station Rebuild | In-Service Date and Estimated Cost Update | McAllen |  | Planned | 1118 - 1296 | AEP TCC | Thomas Neils mlforcum@aep.com 918-599-2674 | 3837 | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8368, 8631, 8632 | Y |  |  | 0 | 65583 | 58010
64042 | Barrilla Junction: 69 kV Loop Rebuild | Rebuild Barrilla Junction to Saragosa to Cherry Creek to Verhalen to Hoefs Road stations, convert to 138 kV | TSP/Company Contact and In-Service Date Update | Barrilla Junction | Hoefs Road Station | Planned | 1141 - 1319 | AEP TNC | Glen Reed twang1@aep.com 918-599-2635 | 1886 | 2026-05-31 |  | 69 | 0 |  | 0 |  | Pecos | Reeves | Tier 3 | 21RPG023 | 2021-12-17 | 2022-01-14 |  | 6649, 6650, 6651, 6652, 6654, 60206, 60207, 60208, 60808, 6653, 60385, 60716, 69023, 69047 | Y | N |  | 0 | 64043 | 64042
66077 | Reconductor both Pecos-Cedarvale 138 kV ckts |  |  | Pecos (bus # 38091) | Cedarvale (bus # 38145) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 15.34 | 0 |  | Reeves | Ward | Tier 4 |  |  |  |  | 38091, 38145 | Y |  |  | 0 | 66078 | 66077
66101 | Del Sol to Frontera: Build New 345 kV Double Circuit Line | Build new 345 kV double circuit line from Del Sol to Frontera. Expand Frontera Station and install two (2) autotransformers | Project Title, Project Description, Transmission Owner, and Estimated Cost Update | Del Sol | Frontera | Planned |  | ETT TCC/AEP TCC | Brent Harris mlforcum@aep.com 918-599-2674 | TP2020838 | 2026-05-31 |  | 345 | 36 | 0 | 1350 |  | Starr | Hidalgo | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8992, 80119, 8355, 80355, 8980 | Y |  |  | 0 | 66102 | 66101
66204 | Rebuild Hidden Lakes-PH Robinson with bundled 795 ACSS |  |  | TNMP Hidden Lakes (bus # 38900) | CenterPoint PH Robinson (bus # 42015) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 3.15 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 42015 | Y |  |  | 0 | 66205 | 66204
66208 | Rebuild League City-Hidden Lakes with bundled 795 ACSS |  |  | Hidden Lakes (bus # 38900) | League City (bus # 38920) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 3.21 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  | 0 | 66209 | 66208
69253 | Rebuild 138 kV Line from Cangrejo to Dacosta | Rebuild 138 kV Line from Cangrejo to Dacosta | In-Service Date and RPG Dates Update | Cangrejo | Dacosta | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2026-05-31 |  | 138 | 0 | 17.97 | 0 |  |  |  | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8135, 8136, 8721, 8722, 8723, 8133, 8140, 8141, 8143, 80064, 8169, 8536 | Y |  |  | 0 | 69254 | 69253
71106 | Dunlavy to HO Clarke Ckt.40A Partial Reconductor | Reconductor portions of Ckt.40A Dunlavy to HO Clarke ahead of future 138kV conversions |  | Dunlavy | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 69 | 0 | 4.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47015, 47160, 48150, 47320, 47580, 48363 | Y | N |  | 0 | 71107 | 71106
72044A | Clute 138kV Switching Station | Reconfigure existing Ckt.82F RIWOOD to CAVERN to BIPORT and loop into new CEHE-owned 138kV Clute switching station to create new Ckt.82 RIWOOD to Clute to CAVERN to BIPORT. |  | Clute | RIWOOD/CAVERN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 | 42050, 43150, 43330 | Y | N |  | 0 | 81651 | 72044
76232 | Reconductor Mivida-Coachwhip-Fishhook 2045 ACCC |  |  | Mivida PSSE Bus# 38152 | Fishhook PSSE Bus# 38180 | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 14.39 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38152, 38170, 38180 | Y |  |  | 0 | 76233 | 76232
76291 | Upgraded Cedarvale–BoneSpringsTap–Fishhook |  |  | Cedarvale to Bone Springs Tap | Bone Springs Tap to Fishhook | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 12.59 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38145, 38165, 38180 | Y |  |  | 0 | 76292 | 76291
76293 | Upgraded Cedvale-MiDiva138KV |  |  | Cerdarvale | Midiva | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 0.15 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38145, 38152 | Y |  |  | 0 | 76294 | 76293
76348 | Reconductor Foxtail-PIGCreek-1926ACSS-138KV |  |  | Foxtail | PIG Creek | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 0.68 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38294, 60393 | Y |  |  | 0 | 76349 | 76348
76576 | Asherton to Uvalde: Convert to 138 kV | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | Estimated Cost and RPG Number Update | Asherton | Uvalde | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-05-31 |  | 138 | 0 | 59.74 | 0 |  | Dimmit | Uvalde | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 7867, 8005, 8006, 8007, 8008, 8242, 8244, 8284, 8672, 8280, 8283, 8231, 8243 | Y | N |  | 0 | 78243 | 76576
78485A | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.24B Westchase to Hayes to Britmoore to increase thermal limits. Upgrade Ckt.24 Bellaire equipment and relay limits. |  | Westchase | Britmoore | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 6.21 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 44120, 48159, 48420 | Y | N |  | 0 | 78486 | 78485
78490D | Jeanetta Auto Upgrades | Reconductor Ckt.25B Clodine to Roark TR8 tap to increase thermal limits. |  | Clodine | Roark | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 3.67 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 44140, 44592 | Y | N |  | 0 | 79428 | 78490
80632 | Install Kilgore 35kV Distribution Substation. Loop on Ckt.86B to create new Ckt.86 CHEVRON to Kilgore to LANGSTON | Install Kilgore 35kV Distribution Substation. Loop on Ckt.86B to create new Ckt.86 CHEVRON to Kilgore to LANGSTON |  | CHEVRON/LANGSTON | Kilgore | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 5.12 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 44830, 40300, 40775 | Y | N |  | 0 | 80633 | 80632
81215 | Oklaunion: Reconfigure 138 kV Station | Reconfigure the Oklaunion 138 kV station from a straight bus to a ring bus | NEW | Oklaunion |  | Planned | TP2023876 | ETT TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6098, 6066, 6097, 6100 | Y | N |  | 0 | 81216 | 81215
78485C | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade portions of Ckt.05E Bellaire to Sharpstown to Hillcroft to increase thermal limits. |  | Bellaire | Hillcroft | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 3.09 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 47015, 48145, 48343 | Y | N |  | 0 | 78489 | 78485
72044B | Clute 138kV Switching Station | [6 empty] | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  | 0 | 81652 | 72044
72044C | Clute 138kV Switching Station | Reconfigure existing Ckt.26D STRATT to SINTEK and loop into new CEHE-owned 138kV Clute switching station to create new Ckt.26 STRATT to Clute to SINTEK. |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 | 42030, 42050, 43300, 42110, 42111, 43240 | Y | N |  | 0 | 81653 | 72044
72044D | Clute 138kV Switching Station | [6 empty] | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  | 0 | 81654 | 72044
76569 | Asherton: Rebuild 138 kV station | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | Estimated Cost and RPG Number Update | Asherton |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-05-31 02:00 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 8280, 8244, 8005, 8242, 8283 | Y |  |  | 0 | 76570 | 76569
45029 | Grandview Highland Hills Rebuild | CPSE_Rebuild of 138 kV double circuit line Line between Grandview to Highland Hills. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0273 | 2026-06-01 |  | 138 | 0 | 11.6 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-11 |  |  | 5030, 5175, 5095, 5205 | Y |  |  | 0 | 45030 | 45029
65663 | Double Ckt Line M138-K | Project Delayed Indefinitely. |  | Pecos (bus # 38091) | Faulkner (bus # 38124) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-06-01 |  | 138 | 0 | 26.2 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38091, 38124 | N |  |  | 0 | 65664 | 65663
71408 | Upgrade CKT943 to 3000 amperes | Replace existing 2-795ACSR conductors with 2-795 ACSS conductors and the upgrade the terminal equipment to 3000 amperes. |  | Lytton Springs | Pilot Knob | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-01 |  | 138 | 0 | 11.13 | 0 |  | Caldwell | Travis | Tier 4 |  |  |  |  | 9075, 9259 | Y |  |  | 0 | 71409 | 71408
76082 | Union Carbide: Rebuild 138 kV Station | Rebuild Union Carbide as new AIS station Chalybe | Project Description, Cost, Tier Update | Union Carbide |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8337, 8735, 5767, 5963, 8338, 5965, 8535, 79601 | Y |  |  | 0 | 76083 | 76082
76286 | Hecker to Resnik: Rebuild 138kV Line | Rebuild the Hecker to Resnik 138kV Line |  | Hecker | Resnik | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023506 | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8565, 8580 | Y |  |  | 0 | 76287 | 76286
77320 | Add CapBANK in COYANOSA |  |  | COYANOSA |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38380 | Y |  |  | 0 | 77321 | 77320
80384 |  | Reconductor Gibbons Creek to Greens Prairie Line |  | Gibbons Creek | Greens Pairie | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-06-01 |  | 138 | 0 | 12.9 | 0 |  | Grimes | Brazos | Tier 4 |  |  |  |  | 964, 32878 | Y |  |  | 0 | 80385 | 80384
80404 |  | Reroute East to Rodgers 69kV line to create East to Rayburn 69kV line to accommodate the TXDOT SH6 project. |  | BRYN EAST | RAYBURN | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-06-01 |  | 69 | 1 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32849, 32874, 32861 | Y |  |  | 0 | 80405 | 80404
80424 |  | Rebuild / Reconductor Dansby to Business Park 69kV for Rail Spur |  | Dansby | Bryn Business Park | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-06-01 |  | 69 | 0 | 3.3 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32871, 32875 | Y |  |  | 0 | 80425 | 80424
81573 | Oklaunion: Build new 345 kV Terminal to interconnect Alpha | Interconnect Alpha at the Oklaunion 345 kV station | NEW | Oklaunion |  | Conceptual |  | ETT TNC/AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-06-01 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6100 | Y |  |  | 0 | 81574 | 81573
81581 | Riley: Build new 345 kV Terminal to interconnect Gamma | Interconnect Gamma at the 345 kV Riley station | NEW | Riley |  | Conceptual |  | ETT TNC/AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-06-01 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6111 | Y |  |  | 0 | 81582 | 81581
81647 | Sardinia: Build 138 kV Station to interconnect Epsilon | Build new 138 kV Station to interconnect Epsilon | NEW | Dupont Switch | Sardinia | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-06-01 |  | 138 | 2 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 81433, 8143 | Y |  |  | 0 | 81648 | 81647
20TPIT0000 | Parkway Substation T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-06-26 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10679 | 3323
69709 | LCRATSC_Bearkat_NorthMcCamey_SandLake_TransmsissionLineAddition | LCRA TSC, Oncor , and WETT joint project to add the Bearkat-North McCamey 345-kV double-circuit transmission line and North McCamey-Sand Lake 345-kV double-circuit transmission line. 22RPG010 |  | Bearkat | Sand Lake | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG +151-257-84514 |  | 2026-06-26 |  | 345 | 165 | 0 | 0 |  | Glasscock | Ward | Tier 1 | 22RPG010 |  | 2022-04-12 |  | 11098, 59903, 76000 | Y | Y |  | 0 | 78333 | 69709
70186 | LCRATSC_BuchananCTEC_Kingsland1_TL_Overhaul | LCRA TSC will perform an overhaul on the 6.2-mile Buchanan to Kingsland 2 to Kingsland 1 (T291) 69-kV transmission line. |  | Buchanan CTEC | Kingsland 1 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG +151-257-84514 |  | 2026-06-30 |  | 69 | 0 | 6.2 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7101, 7402, 7404 | Y | Y |  | 0 | 78419 | 70186
70673 | Clairmont Sun Oil Tap: Rebuild 69 kV Line | Rehab Clairmont Sun Oil Tap 69 kV Line | In-Service Date Update | Clairmont | Sun Clairmont | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2021233 | 2026-06-30 |  | 69 | 0 | 0 | 0 |  | Kent | Kent | Tier 4 |  |  |  |  | 6197, 6198 | Y |  |  | 0 | 70674 | 70673
70675 | Aransas Pass- Rincon 138 kV: Line Upgrade | Upgrade 69 kV line between Aransas Pass and Rincon to 138 kV capable line. | Schedule Update | Aransas Pass | Rincon | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022132 | 2026-06-30 |  | 69 | 0 | 16 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8416, 8421, 8427 | Y |  |  | 0 | 70676 | 70675
71952 | LCRA TSC Bluffton to Buchanan Transmission Line Overhaul | Overhaul circuit and replace conductor with single-Drake conductor (117 MVA) from Bluffton to Buchanan. Replacement structures should be 138-kV double-circuit capable of supporting a single-Suwannee conductor. Install OPGW. |  | Bluffton | Buchanan | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 69 | 0 | 7 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7101, 7406 | Y | N |  | 0 | 72467 | 71952
72479 | Cobia: Build new 138 kV Station | Build new 138 kV station along the Carbide to Joslin 138 kV line | In-Service Date Update | Cobia |  | Planned |  | AEP | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-06-30 |  | 138 | 0.1 | 0 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | 8133, 8685, 88742, 8132, 8140, 8155, 8720, 708133, 8742 | Y |  |  | 0 | 72482 | 72479
73401 | LCRATSC_Fredonia_Mason_TL_Upgrade | Perform an overhaul on the 11 mile T289 Fredonia (CTEC) - Mason (CTEC) 69-kV transmission line. Per LCRA TSC Transmission System Planning procedure, replacement structures will be capable of operating at 138-kV. |  | Fredonia | Mason | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-06-30 |  | 69 | 0 | 11 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 7395, 76391 | Y | N |  | 0 | 73402 | 73401
73496 | Nelson Sharpe III: New 345 kV terminal | Noria Hondo Solar & BESS interconnection to Nelson Sharpe III on Lon Hill to Ajo 345 kV line | In-Service Date Update | Nelson Sharpe III |  | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-06-30 |  | 345 | 1 | 0 | 0 |  | Nueces |  | Tier 4 | [5 empty] | Y |  |  | 0 | 73497 | 73496
72579B | PEC_MountainTop_Blanco_DevilsHill_VoltageUpgrade | Rebuild and upgrade Blanco to Devil's Hill 69 kV circuits to 138 kV with bundled 795 kcmil conductor (440 MVA). (Replaces ERCOT Project # 70367B) |  | Blanco | Devil's Hill | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-07-01 |  | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 | 22RPG033 |  | 2022-11-14 |  | 70484, 70482, 70493 | Y | Y |  | 0 | 72581 | 72579
55217 | Putnam to Leon: Rebuild 138 kV line | Rehab the Putnam to Leon (Oncor) 138 kV line | Project Description and In-Service Date Update | Putnam | Leon | Planned | 1042 - 1269 | AEP TNC | LaRissa Lundry twang1@aep.com 918-599-2635 | 1859 | 2026-07-31 |  | 138 | 0 | 20.81 | 0 |  | Callahan | Eastland | Tier 4 |  |  |  |  | 1624, 6310 | Y | N |  | 0 | 55218 | 55217
66023 | T340 T-Line Upgrade | Upgrading the Marion to Sheriff's Posse Transmission Line T340 from 795 ACSR to 959 ACSS conductor. Upgrades to conductor and structures are included. Structures designed for ultimate build-out of double-circuit bundled 959 ACSS in preparation for additional future capacity. |  | Marion | Sheriff's Posse | Planned |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2026-07-31 |  | 138 | 0 | 3.4 | 0 |  | Guadalupe | Comal | Tier 4 |  |  |  |  | 7178, 7460 | Y | N |  | 0 | 78403 | 66023
70800 | Triada: Build New 345 kV Station | Build new 345 kV station on lobo to Avanzada line for Siete Wind interconnection | In-Service Date Update | Triada |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022749 | 2026-07-31 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8718, 80219, 80235 | Y |  |  | 0 | 70801 | 70800
79462 | Expand HO Clarke substation for Callisto II (22INR0558) | Expand HO Clarke substation for Callisto II (22INR0558) |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | 0 | 79463 | 79462
75790 | Placeholder Station for Erath Solar POI | Placeholder Station for Erath Solar POI |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-08-27 |  | 345 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 68025, 68020, 68030 | Y |  |  | 0 | 75791 | 75790
82298 | PMCR for Adding TNMP Woodhouse New Station | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-08-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  | 2024-02-27 | 38308, 38295, 38355, 60717 | Y |  |  | 0 | 82299 | 82298
66206A | Upgrade Temple - Minerva 69 kV Line | Upgrade Temple - Marak 69 kV Line |  | Temple | Marak | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6186 | 2026-09-15 |  | 69 | 20.5 | 0 | 0 |  | Bell | Milam | Tier 3 | 22RPG034 | 2022-10-01 | 2022-11-01 |  | 3643, 3689 | Y |  |  | 0 | 68923 | 66206
66289B | Upgrade and convert Tyler - Athens 69 kV Line | Convert Athens - Tyler 69 kV Line to 138 kV operation |  | Tyler | Athens | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6094 | 2026-09-15 |  | 138 | 5.8 | 0 | 0 |  | Smith | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3108, 3142, 3233, 3236, 3239, 3288, 13235, 3126, 3197, 3232, 3238, 3256, 3269, 13142, 3248, 3801 | Y |  |  | 0 | 77177 | 66289
66492B | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Grindstone - Jacksboro Sinclair 69 kV Line |  | Jacksboro Sinclair | Grindstone | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3006 | 2026-09-15 |  | 69 | 0 | 15 | 0 |  | Jack | Palo Pinto | Tier 4 |  |  |  |  | 1557, 1572 | Y |  |  | 0 | 72964 | 66492
80315 | Big Foot to Pearsall: Convert to 138 kV | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch | NEW | Big Foot | Pearsall | Planned | 1104 - 1282 | AEP TCC | Will Simmons mlforcum@aep.com 918-599-2674 | 3821 | 2026-09-30 |  | 138 | 0 | 14.79 | 0 |  | Frio | Frio | Tier 4 | 23RPG024 | 2024-08-23 | 2024-09-23 |  | 8216, 8218, 8752, 8753, 8221 | Y |  |  | 0 | 80316 | 80315
80317 | Dilley Switch to Pearsall: Convert to 138 kV, Reroute from Dilley to Dilley Switch, Rebuild Dilley to Dilley Switch 69 kV, and Double Circuit Dilley Switch to Pearsall with Dilley to Dilley Switch | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch | NEW | Dilley Switch | Pearsall | Planned | 1104 - 1282 | AEP | Will Simmons mlforcum@aep.com 918-599-2674 | 3822 | 2026-09-30 |  | 138 | 0 | 19.8 | 0 |  | Frio | Frio | Tier 4 | 23RPG024 | 2024-08-23 | 2024-09-23 |  | 8752, 8753, 8208, 8210, 8212, 8216 | Y |  |  | 0 | 80318 | 80317
80319 | Devine: Install Cap Bank | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch | NEW | Devine |  | Planned |  | AEP | Will Simmons mlforcum@aep.com 918-599-2674 |  | 2026-09-30 |  | 138 | 0 | 0 | 0 | 0,23 | Medina |  | Tier 4 | 23RPG024 | 2024-08-23 | 2024-09-23 |  | 8732 | Y |  |  | 0 | 80322 | 80319
73895 | LCRATSC_Sunglow_Substation_addition | This project provides a point of interconnection for a new battery energy storage resource at a new 138-kV Sunglow Substation between LCRA TSC T627 and LCRA Rosita Creek Substation. |  | Sunglow |  | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org +151-257-84514 |  | 2026-10-15 |  | 138 | 0 | 0 | 0 |  | Maverick |  | Tier 4 |  |  |  |  | 78016, 8260, 78015 | Y | N |  | 0 | 73896 | 73895
78175 |  |  |  | Franklin | Franklin | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-15 |  | 138 | 0 | 0 | 0 | 0,9 | Robertson | Robertson | Tier 4 |  |  |  |  | 57 | Y |  |  | 0 | 78176 | 78175
78177 |  |  |  | Pleasant Grove | Pleasant Grove | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-15 |  | 69 | 0 | 0 | 0 | 0,7.2 | Falls | Falls | Tier 4 |  |  |  |  | 81 | Y |  |  | 0 | 78178 | 78177
78181 |  |  |  | Midway | Midway | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-15 |  | 69 | 0 | 0 | 0 | 0,7.2 | Falls | Falls | Tier 4 |  |  |  |  | 185 | Y |  |  | 0 | 78182 | 78181
6072 | Eldorado to Ft. McKavitt: Rebuild 69 kV Line | Rehab Eldorado to Ft. McKavitt 69 kV line | Project Title, TSP/Company Contact, In-Service Date Update | Eldorado Tap | Ft. McKavitt | Planned | 786 - 0971 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 2677 | 2026-10-31 |  | 69 | 0 | 19.41 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  |  | 6505, 6506, 6507, 6508 | Y | N |  |  | 13794 | 6072
55550 | Brushline: Construct New Distribution Station | Construct new 138/13 kV station Brushline | In-Service Date Update | Brushline |  | Planned | 1106 - 1284 | AEP TCC | Rick Garcia mlforcum@aep.com 918-599-2674 | 3826 | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8972, 5754, 8963 | Y |  |  | 0 | 55551 | 55550
73362 | Uribe: Construct New Distribution Station | Construct new distribution station on the Molina to Zapata 138 kV Line | Terminal From Location and In-Service Date Update | Uribe |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 8985, 8993, 8299, 8646, 80230 | Y | N |  | 0 | 73363 | 73362
75835A | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits |  | Stone Lake | Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 8.29 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 44840, 46510, 46511 | Y | N |  | 0 | 75836 | 75835
76131 | Pendulo: Build New 345 kV terminal | Interconnect Inertia Solar and BESS 2 to the Pendulo 345 kV Station on the Clear Crossing to Smoky Hill line | TSP/Company Contact and In-Service Date Update | Pendulo |  | Planned |  | ETT TNC | Craig Tabor twang1@aep.com 918-599-2635 |  | 2026-10-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60507 | Y | N |  | 0 | 76132 | 76131
79451A | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. |  | Ancla | Angleton/West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 46630, 42110, 43380 | Y | N |  | 0 | 79454 | 79451
79451B | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. | Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. |  | Ancla | ROYAL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 79455 | 79451
45397 | Lion: 138 kV Station & Transmission Line | Lion: 138 kV Station with new line to Stewart Road | In-Service Date Update | Lion | Stewart Road | Planned | 885 - 1063 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3672 TP2018218 | 2026-11-30 |  | 138 | 2.71 | 0 | 40 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8969, 8758, 8951 | Y | N |  | 0 | 65528 | 45397
61396 | Hamilton - Maxwell: Line Rebuild | Hamilton - Maxwell: Line Rebuild | In-Service Date Update | Hamilton Road | Maxwell | Planned |  | AEP TCC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | TA2019800 | 2026-11-30 |  | 138 | 0 | 29 | 0 |  | Val Verde | Val Verde | Tier 3 | 20RPG022 | 2020-11-02 | 2021-01-19 |  | 8257, 8998 | Y |  |  | 0 | 65593 | 61396
66447 | Reforzar: Construct New 345 kV Station | Construct a new 345 kV station on the Lon Hill to North Edinburg 345 kV line | Project Title, Project Description, Estimated Cost, RPG Number, and RPG Dates Update | Reforzar |  | Planned |  | AEP TCC | Joseph C Isaac mlforcum@aep.com 918-599-2674 | TP2022035 | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Brooks |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80078, 8455, 8905 | Y |  |  | 0 | 67317 | 66447
67318 | Cruce: Construct New 345 kV Station | Construct a new 345 kV station on the Cenizo to Reforzar 345 kV line and the Del Sol to San Miguel 345 kV line | Project Title, Project Description, TSP/Company Contact, RPG Number, and RPG Dates Update | Cruce |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022034 | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Duval |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80079 | Y |  |  | 0 | 67319 | 67318
67320 | Cruce to Reforzar: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cruce to Reforzar | Project Title, Project Description, TSP/Company Contact, RPG Number, and RPG Dates Update | Cruce | Reforzar | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022033 | 2026-11-30 |  | 345 | 48 | 0 | 0 |  | Duval | Brooks | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80078, 80079 | Y |  |  | 0 | 67339 | 67320
67322 | Cenizo to Cruce: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cenizo to Cruce | Project Title, Project Description, Owner, Ending County, RPG Number, and RPG Dates Update | Cenizo | Cruce | Planned |  | AEP TCC/ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022031 | 2026-11-30 |  | 345 | 69 | 0 | 0 |  | Webb | Jim Hogg | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80079, 80220 | Y |  |  | 0 | 67323 | 67322
67324 | Cruce to Del Sol: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cruce to Del Sol | Project Title, Project Description, Owner, RPG Number, and RPG Dates Update | Cruce | Del Sol | Planned |  | AEP TCC/ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022032 | 2026-11-30 |  | 345 | 54.2 | 0 | 0 |  | Duval | Starr | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80079, 80355 | Y |  |  | 0 | 67325 | 67324
67326 | Ajo to Reforzar: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Ajo to Reforzar | Project Title, Project Description, Owner, TSP/Company Contact, RPG Number, and RPG Dates Update | Ajo | Reforzar | Planned |  | AEP TCC/ETT | Curtis Brown mlforcum@aep.com 918-599-2674 | TP2022030 | 2026-11-30 |  | 345 | 11 | 0 | 0 |  | Kenedy | Brooks | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80076, 80078 | Y |  |  | 0 | 67327 | 67326
69469 | Equinox Solar Project | Equinox Solar Project | CANCELLED | Cenizo | Del Sol | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  |  | 88355, 80355 | Y |  |  | 0 | 69470 | 69469
70712 | SAPS to Red Creek: Rebuild 138 kV Line | Rehab SAPS to Red Creek 138 kV Line | In-Service Date Update | SAPS | Red Creek | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2020210 | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  |  | 6442, 6473, 6480, 60008 | Y |  |  | 0 | 70713 | 70712
72884 | Gonzales: Build 69 kV STATCOM | Build new 69 kV STATCOM at the Gonzales 69 kV station | Transmission Owner Project Number and In-Service Date Update | Gonzales |  | Planned |  | ETT TNC | Tong Wang twang1@aep.com 918-599-2635 | TP2022130 | 2026-11-30 |  | 69 | 0 | 0 | 0 | -25,25 | Presidio |  | Tier 4 |  |  |  |  | 60203, 6675 | Y | N |  | 0 | 72885 | 72884
73055 | Hamlin to Roby: Rebuild 69 kV line | Rehab Hamlin to Roby 69 kV line | TSP/Company Contact, In-Service Date, Planning Tier, RPG Number, and RPG Dates Update | Hamlin | Roby | Planned |  | AEP TNC | Damian Rabb mlforcum@aep.com 918-599-2674 |  | 2026-11-30 |  | 69 | 0 | 25.23 | 0 |  | Fisher | Jones | Tier 4 | 23RPG002 | 2023-02-01 | 2023-02-28 |  | 6194, 6638, 6185, 6192, 6193, 6195 | Y | N |  | 0 | 73056 | 73055
73061 | Falfurrias to King Ranch: 138 kV Line Rebuild | Rehab Falfurrias to King Ranch 138 kV line. | Schedule Update | Falfurrias | King Ranch | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2026-11-30 |  | 138 | 0 | 20.5 | 0 |  | Brooks | Kleberg | Tier 4 |  | 2023-01-24 | 2023-02-24 |  | 8510, 80228 | Y | N |  | 0 | 73062 | 73061
79988 | Lucero: Construct New 345 kV Station | Interconnect SanPat Solar I and SanPat Solar II to the new Lucero 345 kV station on the Angstrom to Naismith 345 kV line | NEW | Lucero |  | Planned | TP2023838 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-11-30 |  | 345 | 0.2 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 80039, 8249, 8659 | Y | N |  | 0 | 79989 | 79988
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  |  | 5705 | Y | N |  |  | 9835 | 2554
67329 | San Miguel to Cruce 345 kV lines | New San Miguel to Cruce 345 kV double circuit lines |  | San Miguel | Cruce | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 345 | 231.12 | 0 | 0 |  | Atascosa | Duval | Tier 1 | 21RPG017 | 2021-09-23 | 2021-12-23 |  | 5901, 80079 | Y |  |  | 0 | 67330 | 67329
75524 | This converts Bell County to Gabriel to 138 KV |  |  | Bell County | Gabriel | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-12-12 |  | 138 | 0 | 0 | 0 |  | Bell | Williamson | Tier 4 |  |  |  |  | 114, 118, 122, 132, 133, 7345, 7346 | Y |  |  | 0 | 75525 | 75524
64239 | Vineyard Switch-Cypress Waters Switch 138 kV Line | Construct a new 138 kV circuit from Vineyard to Cypress Waters |  | North Lake Switch | Vineyard Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5320 | 2026-12-15 |  | 138 | 7.4 | 0 | 0 |  | Dallas | Tarrant | Tier 3 |  |  |  |  | 2022, 2386, 12012, 12013, 15030, 15035, 15040 | Y |  |  | 0 | 70741 | 64239
68700 | Bonham - Toco Switch 69 kV Line Rebuild | Rebuild the existing 69 kV Line |  | Bonham | Toco | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3016 | 2026-12-15 |  | 69 | 0 | 35 | 0 |  | Fannin | Lamar | Tier 4 |  |  |  |  | 1703, 1761, 1788, 1789, 1790, 11789 | Y |  |  | 0 | 68701 | 68700
68706 | Edgewood Switch – Royse Switch 138 kV Line | Rebuild and convert the Edgewood-Iron Bridge 69 kV to 138 kV operation |  | Edgewood | Able Springs | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3227 | 2026-12-15 |  | 69 | 0 | 0 | 0 |  | Van Zandt | Kaufman | Tier 4 |  |  |  |  | 3182, 3185, 3188, 3189, 3191, 3192, 3193, 6920, 6922, 13191, 3163, 12467, 2471, 2721, 3165, 3167, 12470, 3168, 3169, 3181, 12469, 12472 | Y |  |  | 0 | 68707 | 68706
71156 | Ennis West Switch-Waxahachie Switch 138 kV Line Rebuild | Rebuild the Ennis West-Waxahachie 138 kV Line |  | Ennis West | Waxahachie | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4200 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2241, 2321, 12320 | Y |  |  | 0 | 71160 | 71156
72958 | Graham to Cottonwood 69 kV Line Rebuild | Graham to Cottonwood 69 kV Line Rebuild |  | Graham | Graham | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3001 | 2026-12-15 |  | 69 | 0 | 0 | 0 |  | Young | Young | Tier 4 |  |  |  |  | 1597, 1602, 1603 | Y |  |  | 0 | 72959 | 72958
73567 | LCRATSC_BerryCreek_Substation_Addition | Substation addition to provide Point of Interconnection for Oncor Andice substation addition. |  | Berry Creek |  | Conceptual |  | LCRATSC | Dylan PReas dylan.preas@lcra.org (512) 578-4514 |  | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7361, 7521, 70522 | Y | N |  | 0 | 78401 | 73567
76669 | Rebuild Elbow to Redberry to Bulldog 138 kV Line | Rebuild Elbow to Redberry to Bulldog 138 kV Line |  | Elbow | Bulldog | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8666 | 2026-12-15 |  | 138 | 0 | 18.5 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 10080, 23833, 23834 | Y |  |  | 0 | 77043 | 76669
76696 | Construct a new Border – Shifting Sands 138 kV Line | Construct a new Border – Shifting Sands 138 kV Line |  | Atchison | Shifting Sands | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8628 | 2026-12-15 |  | 138 | 22.3 | 0 | 0 |  | Loving | Winkler | Tier 2 |  |  |  |  | 11392, 18670 | Y |  |  | 0 | 76697 | 76696
78044 | ROCK DRAW 345 kV Switch | Adding Oncor's portion of TNMP Silverleaf and Cowpen 345/138-kV Stations Project (23RPG013) |  | Sand Lake | North McCamey | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8716 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Ward | Upton | Tier 1 | 23RPG013 | 2023-05-18 | 2023-06-09 |  | 18668, 11098, 76000 | Y |  |  | 0 | 78048 | 78044
78046 | TOYAH CREEK 345 kV Switch | Adding Oncor's portion of TNMP Silverleaf and Cowpen 345/138-kV Stations Project (23RPG013) |  | Sand Lake | Solstice | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8715 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Ward | Pecos | Tier 1 | 23RPG013 | 2023-05-18 | 2023-06-09 |  | 18669, 11098, 60404 | Y |  |  | 0 | 78049 | 78046
78361 | Lake Creek - Rattlesnake Road 345 kV Line | Rebuild the Lake Creek - Rattlesnake Road 345 kV Line (McLennan Area Project) |  | Lake Creek | Rattlesnake Road | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6276 | 2026-12-15 |  | 345 | 0 | 5.1 | 0 |  | McLennan | McLennan | Tier 3 |  |  |  |  | 3384, 3399, 3409 | Y |  |  | 0 | 81575 | 78361
81227 | Cattleman – Gascondades 345 kV Reroute | Terminate Morgan Creek – Gascondades 345 kV Line into Cattleman 345 kV Switch |  | Cattleman | Gascondades | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8647 | 2026-12-15 |  | 345 | 0 | 2.5 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 10053, 76030 | Y |  |  | 0 | 81664 | 81227
81299 | Ranger Camp – Prong Moss 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Ranger Camp | Prong Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3025 | 2026-12-15 |  | 345 | 0 | 61.4 | 0 |  | Mitchell | Howard | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10049, 10057 | Y |  |  | 0 | 81300 | 81299
73436 | Rockhound - Connell 345 kV Double-Circuit Line | Construct a new 345 kV Double-Circuit Line and establish a 345/138 kV Switch |  | Rockhound | Connell | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8718, R8807 | 2026-12-16 |  | 345 | 10 | 0 | 1200 |  | Martin | Midland | Tier 2 |  |  |  |  | 10085, 10086, 10087, 10088, 10033, 10036, 10062, 11371, 23840, 23841, 23855 | Y |  |  | 0 | 81403 | 73436
81418 | Reiter to Yarbrough 138 kV Line Rebuild | 138 kV existing line rebuild. |  | Reiter | Yarbrough | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8527 | 2026-12-16 |  | 138 | 0 | 27.2 | 0 |  | Ector | Crane | Tier 3 |  |  |  |  | 11111, 18545 | Y |  |  | 0 | 81419 | 81418
72502 | Tarpley Substation Upgrades | Provide transmission point of interconnection to Battery energy storage system near the Tarpley Substation. Add a 138kV bay and associated circuit breaker to existing substation (25INR0188) |  | Tarpley |  | Planned |  | BEC | Jhonatan Guerrero Rivera j.rivera@banderaelectric. 830-612-0048 |  | 2026-12-30 |  | 69 | 0.1 | 0 | 0 |  | Bandera |  | Tier 4 | [5 empty] | Y | N |  | 0 | 72503 | 72502
81034 | Lamesa - Willow Valley 138 kV Line | Rebuild Lamesa to Willow Valley 138 kV line. |  | Lamesa Switch | Willow Valley Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8654 | 2026-12-30 |  | 138 | 0 | 32.1 | 0 |  | Borden | Dawson | Tier 3 |  |  |  |  | 1163, 1301, 1307, 1308 | Y |  |  | 0 | 81035 | 81034
81152 | Rebuild China_Grove - Tributary 138 kV Line | Rebuild China_Grove - Tributary 138 kV Line |  | China Grove | Tributary | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8656 | 2026-12-30 |  | 138 | 0 | 23.7 | 0 |  | Mitchell | Howard | Tier 3 |  |  |  |  | 1318, 1394, 1571, 1572, 11571 | Y |  |  | 0 | 81153 | 81152
81410 | Oncor_FW_Reiter Switch Syncrhonous Condenser | Add Oncor_FW_Reiter Switch Syncrhonous Condenser |  | Reiter | Reiter | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | D20231 | 2026-12-30 |  | 345 | 0 | 0 | 0 | 0,350 | Ector | Ector | Tier 1 |  |  |  |  | 18553, 18554, 18544 | Y |  |  | 0 | 81411 | 81410
81415 | Oncor_FW_Tonkawa Switch Syncrhonous Condenser | Add Oncor_FW_Tonkawa Switch Syncrhonous Condenser |  | Tonkawa | Tonkawa | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | D20232 | 2026-12-30 |  | 345 | 0 | 0 | 0 | 0,350 | Scurry | Scurry | Tier 1 |  |  |  |  | 18556, 18557, 1048 | Y |  |  | 0 | 81416 | 81415
81686 | Blu Lacy: Build 345 kV Station to interconnect Pi | Build new 345 kV Station to interconnect Pi and add capacitors | NEW | Blu Lacy |  | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-12-30 |  | 345 | 0 | 0 | 0 | 0,523.6 | Nueces |  | Tier 3 |  |  |  |  | 84550, 8455, 80078, 85000 | Y | N |  | 0 | 81687 | 81686
4320 | CPSE_Brooks to Chavaneaux MLSE | Upgrade terminals at Brooks and Chavaneaux to ensure a 1364 A rating (minimum) |  | Brooks | Chavaneaux |  |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0733 | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y | Y |  |  | 11872 | 4320
51005 | Rocksprings to Friess Ranch: Rebuild 69 kV line | Rehab Rocksprings to Sonora 69 kV line | Project Description, Transmission Owner, and In-Service Date Update | Rocksprings | Friess Ranch | Planned | 1044 - 1217 | AEP TCC/AEP TNC, ETT | Dave Baker mlforcum@aep.com 918-599-2674 | 2792 | 2026-12-31 |  | 69 | 0 | 22.6 | 0 |  | Edwards | Sutton | Tier 3 | 19RPG018 | 2019-10-24 | 2019-11-18 |  | 8238, 60210 | Y | N |  | 0 | 51006 | 51005
55421 | Ballinger to Concho: Rebuild 69 kV line | Rebuild Ballinger to Concho 69 kV line, install POP switch for Rowena, install CB at Miles, install POP switch for Harriett REA | Terminal To Location, TSP/ Company Contact, and In-Service Date Update | Ballinger | San Angelo Concho | Planned | 1088 - 1271 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1861 | 2026-12-31 |  | 69 | 0 | 20.45 | 0 |  | Runnels | Tom Green | Tier 3 | 20RPG004 | 2020-04-08 | 2020-04-30 | 2020-05-08 | 6409, 6413, 6338, 6410, 6412, 6411, 6450 | Y | N |  | 0 | 55422 | 55421
64499 | Hyde Park to Downtown Ckt.32A Upgrades | Upgrade Hyde Park to Downtown Ckt.32A |  | Downtown | Hyde Park | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 345 | 0 | 1.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47500, 47690, 47510, 47570 | Y | N |  | 0 | 64500 | 64499
67422F | Greens Bayou to Clinton 138kV Conversion | Remove CASTEN and Wallisville substations from Ckt.10A service. Resulting in Ckt.10A Clinton to Greens Bayou |  | Clinton | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40250, 41682, 40352, 40720 | Y | N |  | 0 | 72776 | 67422
68205 | GENRAL to Garden Villas Rebuild | Rebuild and Reconductor portion of Ckt.12B GENRAL to Garden Villas to prepare for future 138kV Conversion |  | GENRAL | Garden Villas | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 69 | 0 | 9.91 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42690, 47670 | Y | N |  | 0 | 68206 | 68205
69888A | Deepwater to Clinton Ckts.33B-33C Line Upgrades | Fully reconductor Ckt.33B Deepwater to Texpet Switchrack to Harrisburg ahead of future 138kV conversions. |  | Deepwater | Harrisburg | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 69 | 0 | 3.8 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40470, 40800, 41560, 41561 | Y | N |  | 0 | 70971 | 69888
70628 | Japhet 138kV Distribution Sub and Upgrades | Upgrade portions of 69kV Ckt.12 Garden Villas to Bringhurst to Clinton. Install new 138kV Japhet distribution substation. Move 69kV Bringhurst substation load to new Japhet substation and retire Bringhurst substation. Retire portions of Ckt.12 and convert the remaining portions of Ckt.12 to 138kV service. Loop new Japhet substation to create new 138kV Ckt.13 University to Japhet to Clinton. |  | Japhet | University/Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 4.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45070, 47540, 40350, 40352, 42690, 47700, 47760, 47764 | Y | N |  | 0 | 78244 | 70628
73441 | Dupont Switch to Joslin: Rebuild 138 kV Line | Rehab the Dupont Switch to Joslin 138 kV Line | TSP/Company Contact, In-Service Date, and Tier Update | Dupont | Joslin | Planned |  | AEP TCC | Travis Coody mlforcum@aep.com 918-599-2674 |  | 2026-12-31 |  | 138 | 0 | 32.6 | 0 |  | Victoria | Calhoun | Tier 4 | 22RPG040 | 2022-11-01 | 2022-12-01 |  | 8140, 8141, 8143, 80064 | Y |  |  | 0 | 73442 | 73441
75786 | This project will create a POI Bus (station) named Skydancer to interconnect 23INR0295 | This project will create a POI Bus (station) named Skydancer to interconnect 23INR0295 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 68055, 68080, 68090 | Y |  |  | 0 | 75787 | 75786
77803 | Cowpen 345kV station from TNMP submitted Cowpen/Silverleaf RPG | This proposed RPG preferred solution project is currently under ERCOT internal review. |  |  |  | Conceptual |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 1 |  |  |  |  | 38042, 38043, 38044, 38048, 18669, 38023, 38027, 38045, 38055 | Y |  |  | 0 | 77804 | 77803
77805 | Partial Preliminary TNMP Pecos County RPG | This is part of a proposed RPG preferred solution project is currently under ERCOT internal review. |  | Leon Creek (bus # 38355) | Coyanosa (bus # 38380) | Conceptual |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Pecos | Reeves | Tier 1 |  |  |  |  | 38355, 38380 | Y |  |  | 0 | 77806 | 77805
77807 | Silverleaf 345kV station from TNMP submitted Cowpen/Silverleaf RPG | This proposed RPG preferred solution project is currently under ERCOT internal review. |  |  |  | Conceptual |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Ward | Ward | Tier 1 |  |  |  |  | 38143, 38147, 38148, 38149, 38150, 18668, 38091, 38145, 38165 | Y |  |  | 0 | 77808 | 77807
78468 | Pradera (PRD) CEHE-Owned 345kV Substation for Austin Bayou Solar (25INR0102) | New 345kV Pradera (PRD) substation for generator interconnection to Austin Bayou Solar (25INR0102). Loop Ckt.27 into Pradera substation to create new Ckt.27 Seabreeze to Pradera to Savannah. Install generator lead from Pradera (PRD) substation to AUSTIN (ABY) customer substation (25INR0102). |  | Pradera | Savannah/ Seabreeze | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42590, 43020, 43180 | Y | N |  | 0 | 82805 | 78468
81368 | Rio Pecos: Upgrade 138 kV Terminals | Upgrade the Soaptree and Whitebaker 138 kV terminals at the Rio Pecos 138 kV station | NEW | Rio Pecos |  | Planned | TP2023625 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6601, 38445 | Y | N |  | 0 | 81369 | 81368
81576 | Tesla: Build new 345 kV Terminal to interconnect Beta | Interconnect Beta at the Tesla 345 kV station | NEW | Tesla |  | Conceptual |  | ETT TNC/ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501 | Y |  |  | 0 | 81577 | 81576
81657 | Verhalen: Build new 138 kV Terminal to interconnect Eta | Interconnect Eta at the Verhalen 138 kV station | NEW | Verhalen |  | Conceptual |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60207 | Y |  |  | 0 | 81658 | 81657
81659 | Lytle: Build new 138 kV Terminal to interconnect Cinco II | Interconnect Cinco II at the Lytle 138 kV station | NEW | Lytle |  | Conceptual |  | AEP TCC/ETT | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 | 0,34.5 | Medina |  | Tier 4 |  |  |  |  | 8962 | Y |  |  | 0 | 81660 | 81659
81697 | Amber: Build 345 kV Station to interconnect Kappa | Build new 345 kV Station to interconnect Kappa and add capacitors | NEW | Amber |  | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 | 0,523.6 | Nueces |  | Tier 3 |  |  |  |  | 84555, 80078, 84550, 85000 | Y |  |  | 0 | 81698 | 81697
81783 | Seabird: Build 138 kV Station to interconnect Mu | Build new 138 kV Station to interconnect Mu | NEW | Ingleside | Seabird | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2026-12-31 |  | 138 | 2.9 | 0 | 0 | 0,69.1 | San Patricio | Nueces | Tier 4 |  |  |  |  | 84250, 8425, 8808 | Y | N |  | 0 | 81784 | 81783
81799 | Four Corners: Build 345 kV Station to interconnect Nu | Build new 345 kV Station on the Edith Clarke to Tesla line to interconnect Nu | NEW | Four Corners |  | Conceptual |  | AEP TNC/ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Hardeman |  | Tier 4 |  |  |  |  | 61616, 60501, 60505 | Y | N |  | 0 | 81800 | 81799
81825 | Houdini: Build 345 kV Station to interconnect Xi | Build new 345 kV Station to interconnect Xi | NEW | Houdini |  | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 88800, 43990, 44000 | Y |  |  | 0 | 81826 | 81825
67422G | Greens Bayou to Clinton 138kV Conversion | Convert Wallisville substation from Ckt.10A service to 138kV loop service on unnamed 138kV Greens Bayou to Clinton Ckt.xx to create new Ckt.xx TEXWAL to Wallisville to Clinton. Serve CASTEN customer substation from Wallisville with dedicated transformer service. |  | Greens Bayou | Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 2.17 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41660, 40250, 41680, 40350, 41575 | Y | N |  | 0 | 72775 | 67422
78461B | West Columbia to Damon and Needville to Big Creek Ckt.89A Upgrades | Rebuild/reconductor Needville to Big Creek Ckt.89 as a Hardening upgrade. |  | Needville | Big Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 0 | 5.46 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 78463 | 78461
72457 | AddKiowaToQuinlanLine | Add 138kV line from Kiowa to Quinlan |  | Kiowa | Quinlan | Planned |  | RYBRN |  |  | 2027-01-01 |  | 138 | 8 | 0 | 0 |  | Hunt | Hunt | Tier 2 |  |  |  |  | 6796, 6884 | Y |  |  | 0 | 72458 | 72457
81229 | Upgrade Oaks Auto | Upgrade Oaks Auto to 150MVA |  | Oaks | Oaks | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-01-01 |  | 138 | 0 | 0 | 150 |  |  |  | Tier 4 |  |  |  |  | 5712, 5713 | Y |  |  | 0 | 81230 | 81229
81590 | Rio Medina substation | Adds Rio Medina Load serving station |  | Rio Medina |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-01-01 |  | 138 | 4.5 | 0 | 0 |  | Medina |  | Tier 2 |  |  | 2024-02-01 |  | 5805, 5804 | Y | N |  | 0 | 81591 | 81590
81594 | Dunlay substation | Adds STEC Dunlay Load serving station |  | Dunlay |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-01-01 |  | 138 |  | 0 | 0 |  | Medina |  | Tier 2 |  |  |  |  | 5807, 5802, 5813 | Y | N |  | 0 | 81595 | 81594
65154 | Mason Switch to Yellowjacket: Rebuild 69 kV Line | Rehab the Mason Switch to Yellowjacket 69 kV Line | In-Service Date Update | Mason Switch | Yellowjacket | Planned | 1142 - 1320 | AEP TNC | Brian Oyster twang1@aep.com 918-599-2635 | 2836 | 2027-01-31 |  | 69 | 0 | 26.45 | 0 |  | Menard | Mason | Tier 4 | 21RPG014 | 2021-08-01 | 2021-09-01 |  | 6363, 6396, 23824 | Y | N |  | 0 | 65155 | 65154
65837 | New Cachena Substation |  |  | 5133 | 5323 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 5068, 5133, 5323 | Y |  |  | 0 | 65838 | 65837
79456A | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072) | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072). Loop Ckt.18 into Huizache substation to create new Ckt.18 Speedway to Huizache to DOW. |  | Huizache | Speedway/DOW | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-02-28 |  | 345 |  |  | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 46640, 42500, 43060 | Y | N |  | 0 | 79460 | 79456
79456B | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072) | Install generator lead from Huizache (HUI) substation to customer substation HIGHCH (HIC) for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072). |  | Huizache | HIGHCH (High Chap) | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-02-28 00:01 |  | 345 | 0.07 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 79461 | 79456
45015 | Barnhart to Cassava: Rebuild 69 kV line | Rebuild the Barnhart to Cassava 69 kV line | In-Service Date Update | Barnhart | Cassava | Planned | 942 - 1120 | AEP TNC | LaRissa Lundry twang1@aep.com 918-599-2635 | 2756 | 2027-02-28 01:00 |  | 69 | 0 | 6.021 | 0 |  | Irion | Irion | Tier 4 |  |  |  |  | 6532, 6530, 6537, 60359 | Y | N |  | 0 | 65525 | 45015
78173 |  |  |  | Trimmier | Trimmier | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 0 | 0 | 0,12 | Bell | Bell | Tier 4 |  |  |  |  | 136 | Y |  |  | 0 | 78174 | 78173
78179 |  |  |  | Ding Dong | Ding Dong | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 0 | 0 | 0,12 | Bell | Bell | Tier 4 |  |  |  |  | 115 | Y |  |  | 0 | 78180 | 78179
80336 |  |  |  | WESTLOOP | BROCK | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 2.23 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 480, 487 | Y |  |  | 0 | 80337 | 80336
80340 |  |  |  | Keith Switch | Iola | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 6.1 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 2, 4 | Y |  |  | 0 | 80341 | 80340
80342 |  |  |  | HILLTOP LAKES | HILLTOP LAKES | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 0 | 60 |  | Leon | Leon | Tier 4 |  |  |  |  | 48, 47 | Y |  |  | 0 | 80343 | 80342
80295 | Add 2nd transformer at Ponder | Add 2nd transformer at Ponder |  | Ponder | Ponder | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-04-15 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 642 | Y |  |  | 0 | 80296 | 80295
54892 | Eden to North Brady: Rebuild 69 kV line | Rehab Eden to North Brady 69 kV line |  | Eden | North Brady | Planned | 1039 - 1266 | AEP TNC | Larry Brown twang1@aep.com 918-599-2635 | 1856 | 2027-04-30 |  | 69 | 0 | 32.7 | 0 |  | Concho | McCulloch | Tier 3 | 22RPG009 | 2022-03-23 | 2022-04-14 |  | 6384, 60797, 6006, 6372, 6380, 6385 | Y | N |  | 0 | 65568 | 54892
70662 | Cobra: Build new 345 kV station | Interconnect Garcitas Solar to the Radiant to Static 345 kV line | In-Service Date Update | Cobra |  | Planned |  | AEP | Adam Wells mlforcum@aep.com 918-599-2674 | TP2022750 | 2027-04-30 |  | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 8728, 5915, 8676, 8715 | Y |  |  | 0 | 70663 | 70662
76123 | D'Hanis Capacitor 2nd step addition | D'Hanis Capacitor 2nd step addition 9.6 MVAR |  | D'Hanis |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-05-01 |  | 69 | 0 | 0 | 0 | 0,9.6 |  |  | Tier 4 |  |  |  |  | 5814 | Y | N |  | 0 | 76124 | 76123
76790 | Upgrade Pearsall Auto | Upgrade Pearsall Auto |  | Pearsall | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5893, 5895 | Y |  |  | 0 | 76791 | 76790
84892 | New transmission line between Tally and Ranchtown |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5358, 5422 | Y |  |  | 0 | 84893 | 84892
84894 | Upgrade transmission line between Tally and Texas Research |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5422, 5430 | Y |  |  | 0 | 84895 | 84894
4270 | Handley - Hemphill 138 kV Line | Upgrade existing line | Project Deferral | Handley | Hemphill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5214 | 2027-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1950, 2164, 2167 | Y | N |  |  | 11818 | 4270
6287 | Sherry Sw. - Webb/Kennedale 345 kV DCKT Line | Upgrade the existing 345 kV Line |  | Sherry | Webb/Kennedale | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4252 | 2027-05-15 |  | 345 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 3 |  |  |  |  | 1911, 1918, 1930, 1929, 1932, 1934 | Y |  |  |  | 14016 | 6287
71182 | Reiter 345/138 kV Switch | Construct a new 345/138 kV switch |  | Odessa EHV | Wolf/Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8629 | 2027-05-15 |  | 345 | 0 | 0 | 1200 |  | Ector | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 18544, 18546, 18547, 1018, 11010, 11028, 18545 | Y |  |  | 0 | 81601 | 71182
71881 | Install 31.3 Mvar capacitor bank at Andice. | Install 31.3 Mvar capacitor bank at Andice. Formerly TPIT project number 70365. |  | Andice |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson |  | Tier 4 |  |  |  |  | 70522 | Y | Y |  | 0 | 71882 | 71881
73540 | LCRATSC_Carlson_Substation_Addition | Substation addition to provide Point of Interconnection for Oncor Lund substation addition. |  | Carlson |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org (512) 578-451 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7338, 3650, 7337 | Y | N |  | 0 | 73541 | 73540
73570 | LCRATSC_Steger_Substation_Addition | Substation addition to provide Point of Interconnection for Oncor New Sweden substation addition. |  | Steger |  | Conceptual |  | LCRATSC | Dylan PReas dylan.preas@lcra.org (512) 578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7339, 7336, 7337 | Y | N |  | 0 | 73571 | 73570
76312 | Establish Dunham 345/138kV Switch | Establish Dunham 345/138kV Switch and Burger Lake Sub |  | Dunham | Dunham | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5007 | 2027-05-15 |  | 138 | 0 | 0 | 600 |  | Denton | Denton | Tier 3 |  |  |  |  | 1840, 1842, 11842, 21851 | Y |  |  | 0 | 82052 | 76312
78404 | BBEC Bastrop Village Addition |  |  | Bastrop Village |  | Planned |  | BBEC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7561, 7555, 7556 | Y | N |  | 0 | 78406 | 78404
80870 | Add synchronous condenser at Bakersfield substation. |  |  | Bakersfield (BAKESW) | Bakersfield (BAKESW) | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | 1030378 | 2027-05-15 |  | 345 | 0 | 0 | 0 | -350350 | Pecos | Pecos | Tier 1 |  |  |  |  | 76101, 76102, 76002 | Y |  |  | 0 | 80926 | 80870
81232 | Cattleman – Bitter Creek/Champion Creek 345 kV Reroute | Terminate Morgan Creek – Bitter Creek/Champion Creek Double-Circuit 345 kV Line into Cattleman 345 kV Switch |  | Cattleman | Bitter Creek and Champion Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8647 | 2027-05-15 |  | 345 | 0 | 5 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 11032, 11033, 11034, 1414, 10053, 71050 | Y |  |  | 0 | 81665 | 81232
81373 |  |  |  | Longstreet | Buckholts | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-05-15 |  | 138 | 0 | 1.5 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 108, 110, 65, 3749 | Y |  |  | 0 | 81374 | 81373
71187 | Reiter - Tesoro 345 kV Double-Circuit Line | Construct new 2.5-mile 345 kV double-circuit line from Tesoro to Reiter |  | Tesoro | Reiter | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8629 | 2027-05-16 |  | 345 | 5 | 0 | 0 |  | Midland | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 18540, 18544 | Y |  |  | 0 | 71189 | 71187
80576 | AEP_TCC_Add_Chalmer_Permanent_station |  | NEW | Chalmers |  | Planned | DP23X0014 | AEP | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2027-05-21 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8668, 8750, 8111, 8127, 89500 | Y |  |  | 0 | 80577 | 80576
81548 | Haber: Build 345 kV Station to interconnect Iota | Build new 345 kV Station on the Cobra to Static 345 kV line to interconnect Iota | NEW | Haber |  | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2027-05-28 |  | 345 | 7 | 0 | 0 |  | Victoria |  | Tier 3 |  |  |  |  | 81003, 81006, 8676, 8728 | Y |  |  | 0 | 81549 | 81548
81553 | Haber: Build new 345 kV Terminal to interconnect Theta | Interconnect Theta at the Haber 345 kV station | NEW | Haber |  | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2027-05-29 |  | 345 | 1 | 0 | 0 |  | Victoria |  | Tier 3 |  |  |  |  | 81005, 81003 | Y |  |  | 0 | 81554 | 81553
59086 | Pulsar to Victoria: Rebuild 138 kV line | Rebuild 138 kV line from Pulsar to Victoria | Schedule Update | Edna | Victoria | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020888 | 2027-05-30 |  | 138 | 0 | 42.76 | 0 |  | Jackson | Victoria | Tier 3 |  | 2022-02-22 | 2022-03-01 |  | 8118, 8172 | Y | N |  | 0 | 65585 | 59086
70706 | Tungsten(Carbide): Rebuild Station | Rehab Tungsten(Carbide) 138/69 kV Station | Transmission Status, Tier, RPG Number, and RPG Dates Update | Tungsten |  | Planned |  | AEP TCC | Teresa Trotman mlforcum@aep.com 918-599-2674 |  | 2027-05-30 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 4 | 21RPG024 | 2021-12-16 | 2022-01-18 |  | 8149, 8152, 8161, 8189, 8190, 80135, 110336, 5598, 8144, 8154, 8159, 8536, 8723, 110331, 110332, 110334, 110335 | Y |  |  | 0 | 78605 | 70706
81556 | Haber: Build new 345 kV Terminal to interconnect Crunch | Interconnect Crunch at the Haber 345 kV station | NEW | Haber |  | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2027-05-30 |  | 345 | 1 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 81004, 81003 | Y |  |  | 0 | 81557 | 81556
54120 | Rebuild Tejas-Commanche (Bundled 795 ACSS) | Rebuild Tejas - Commanche 138 kV line with Bundled 795 ACSS conductor. |  | Tejas 138 kV Substation (Bus # 38530) | Commanche 138 kV Substation (Bus # 38560) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | STE07318 | 2027-05-31 |  | 138 | 0 | 0.95 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38530, 38560 | Y |  |  | 0 | 54121 | 54120
60502 | Rebuild Apache-Amoco with bundled 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38620, 38720 | Y |  |  | 0 | 60503 | 60502
67427 | Greens Bayou to Clinton 138kV Conversion | Upgrade Ckt.16C MINING Switchrack to MINING/BENTON ahead of future 138kV Conversions |  | Mining Switchrack | BENTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 69 | 0 | 1.9 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41062, 41063, 48177, 40470, 41380, 48171 | N | N |  | 0 | 67428 | 67427
70891 | Eola Tap: Rebuild 69 kV Line | Rehab Eola Tap 69 kV Line | In-Service Date, Estimated Cost Update | Eola Tap | Eola | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-05-31 |  | 69 | 0 | 11.69 | 0 |  | Concho | Concho | Tier 4 |  |  |  |  | 6370, 6371 | Y | N |  | 0 | 70892 | 70891
77031 | Las Lomas: Construct New Station | Construct new 138/13 kV station Las Lomas | NEW | Las Lomas |  | Planned |  | AEP TCC | Eric Locke mlforcum@aep.com 918-599-2674 | DP24X0003 | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 8806, 8793, 8798 | Y |  |  | 0 | 77032 | 77031
15TPIT0031 | Chavaneaux_Chavaneaux Tap Rebuild (Brooks to Chavaneaux ckt) | Rebuild 138 kV transmission from Chavaneaux to Chavaneaux Tap. This rebuild is for Brooks to Chavaneaux ckt. |  | Brooks | Chavaneaux | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0260 | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y |  |  | There are no transformers associated with this project | 9555 | 2304
67091 | Second 138 kV transmission Line from DL-DP CKT1034 | Second 138 kV transmission Line from Dunlap to Decker CKT1034 |  | 9045 | 9188 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 138 | 5.22 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9045, 9188 | Y |  |  | 0 | 67092 | 67091
81655 | Candela: Build 345 kV Station to interconnect Zeta | Build new 345 kV Station to interconnect Zeta | NEW | Candela |  | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2027-06-01 |  | 345 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8755, 8317, 8704 | Y |  |  | 0 | 81656 | 81655
81724 | Calabaza: Build 138 kV Station to interconnect Omicron | Build new 138 kV Station to interconnect Omicron | NEW | Calabaza |  | Conceptual |  | AEP TCC/LCRA | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 80380, 8168, 8441, 78568, 80260 | Y |  |  | 0 | 81725 | 81724
81746 | Calabaza: Build new 138 kV Terminal to interconnect Lambda | Interconnect Lambda at the Calabaza 138 kV station | NEW | Calabaza |  | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2027-06-02 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 80380 | Y | N |  | 0 | 81747 | 81746
45068 | Merida to Harlandale Rebuild | CPSE_Merida to Harlandale Rebuild |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0233 | 2027-06-05 |  | 138 | 0 | 10 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5190, 5310, 5385, 5395 | Y |  |  | 0 | 45069 | 45068
75255C | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5230, 5260 | Y |  |  | 0 | 75849 | 75255
75255E | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5056, 5231 | Y |  |  | 0 | 75851 | 75255
75255A | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5231, 5901 | Y |  |  | 0 | 75256 | 75255
75255B | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5231, 5230 | Y |  |  | 0 | 75848 | 75255
75255D | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5056, 5231 | Y |  |  | 0 | 75850 | 75255
49556 | Ozona: Rebuild 69 kV station | Replace existing Ozona 69 kV station with a new 69 kV ring bus | TSP/Company Contact, In-Service Date, and Estimated Cost Update | Ozona |  | Planned | 1018 - 1196 | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 | 2780 | 2027-06-30 |  | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6550, 6560 | Y | N |  | 0 | 65538 | 49556
81238 | HIF |  |  |  |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2027-06-30 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8754, 5915, 8123 | Y |  |  | 0 | 81239 | 81238
84896 | New Legend Falls Substation looped into the existing Tally to Texas Research transmission line. This station supports the RPG approved Rio Medina project |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-07-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5259, 5422, 5430 | Y |  |  | 0 | 84897 | 84896
85008 | Add Rio Medina - Legend Falls Tline | Add Rio Medina - Legend Falls Tline as part of the Rio Medina RPG Project |  | Rio Medina |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-07-01 12:01 |  | 138 | 5.6 | 0 | 0 |  | Medina | Medina | Tier 2 |  |  | 2024-02-01 |  | 5805, 5259 | Y | N |  | 0 | 85009 | 85008
52464 | Alamito Creek to Ft. Davis: Rebuild 69 kV Line | Alamito Creek to Ft. Davis: Rebuild 69 kV line | Project Title, Project Description, and In-Service Date Update | Alamito Creek | Ft Davis | Planned | 1070 - 1243 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 2831 | 2027-08-31 |  | 69 | 0 | 20.5 | 0 |  | Presidio |  | Tier 4 |  |  |  |  | 6676, 6677, 6691, 6678, 6692 | Y | N |  | 0 | 65564 | 52464
66202B | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Elkhart - Crockett 69 kV Line |  | Elkhart | Crockett | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6182 | 2027-09-15 |  | 69 | 0 | 19.5 | 0 |  | Anderson | Houston | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3285, 3286, 3289, 3290 | Y |  |  | 0 | 71894 | 66202
66206B | Upgrade Temple - Minerva 69 kV Line | Upgrade Marak - Minerva 69 kV Line |  | Marak | Minerva | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6186 | 2027-09-15 |  | 69 | 13.1 | 0 | 0 |  | Milam | Milam | Tier 3 | 22RPG034 | 2022-10-01 | 2022-11-01 |  | 3643, 3684, 3685, 3689 | Y |  |  | 0 | 68924 | 66206
66492C | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Jacksboro Amoco - Chico City Services 69 kV Line |  | Jacksboro Amoco | Chico City Services | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3006 | 2027-09-15 |  | 69 | 0 | 7.3 | 0 |  | Jack | Wise | Tier 4 |  |  |  |  | 1554, 1555 | Y |  |  | 0 | 72963 | 66492
71910 | Rebuild the Hillsboro - Elm Mott 69 kV Line | Rebuild the Hillsboro - Elm Mott 69 kV Line |  | Hillsboro | Elm Mott | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6221 | 2027-09-15 |  | 69 | 0 | 25.4 | 0 |  | Hill | McLennan | Tier 3 |  |  |  |  | 3408, 3523, 3524, 3525, 3526, 3528, 3527, 3529, 13525 | Y |  |  | 0 | 71911 | 71910
64067 | Bessel to King Ranch: 138 kV Line Rebuild | Rehab the Bessel to King Ranch 138 kV line | Circuit Miles Rebuilt, Ending County, and RPG Number Update | Bessel | Stratton | Planned |  | AEP TCC | Michael Glueck mlforcum@aep.com 918-599-2674 | TA2020081 | 2027-11-30 |  | 138 | 0 | 26.59 | 0 |  | Nueces | Kleberg | Tier 4 | 23RPG001 | 2023-01-25 | 2023-02-24 |  | 8498, 8512, 8665, 8060, 8514, 80228 | Y |  |  | 0 | 64068 | 64067
70710 | Eden to Yellowjacket: Rebuild 69 kV Line | Rehab Eden to Yellowjacket 69 kV line | In-Service Date, Estimated Cost Update | Eden | Yellowjacket | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2021119 | 2027-11-30 |  | 69 | 0 | 0 | 0 |  | Concho | Menard | Tier 4 |  |  |  |  | 6363, 6372 | Y |  |  | 0 | 70711 | 70710
72999 | Haskell to Munday: Rebuild 69 kV Line | Rehab Haskell to Munday 69 kV Line | TPS/Company Contact, RPG Number, Date Submitted to ERCOT for RPG Review, Date RPG Review Completed, In-service Date Update | Haskell | Munday | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-11-30 |  | 69 | 0 | 21.71 | 0 |  | Haskell | Knox | Tier 4 | 22RPG043 | 2022-12-15 | 2023-01-11 |  | 6123, 6124, 60021, 6107, 6122, 6125, 6126 | Y | N |  | 0 | 73000 | 72999
73001 | Truscott Humble Tap: Rebuild 69 kV Line | Rehab Truscott Humble Tap 69 kV line |  | Moorhouse | Truscott Humble | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-11-30 |  | 69 | 0 | 13.92 | 0 |  | Knox | Knox | Tier 4 |  |  |  |  | 6084, 60023, 6080, 6082, 6085 | Y | N |  | 0 | 73002 | 73001
80502 | Lon Hill: Construct New 345 kV Terminal | Interconnect the Tom Cruise load to the Lon Hill 345 kV station | NEW | Lon Hill |  | Planned | TP2023885 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2027-11-30 |  | 345 | 0.1 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 80037, 8455 | Y |  |  | 0 | 80503 | 80502
1549 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-15 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 | [5 empty] | Y | N |  |  | 8754 | 1549
71912B | Rebuild the Killeen Fort Hood - Killeen Taft 138 kV Line | Rebuild the Killeen Park Street Tap - Killeen Taft 138 kV Line |  | Killeen Park Street Tap | Killeen Taft | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6245 | 2027-12-15 |  | 138 | 0 | 3.3 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3619, 3621, 3639 | Y |  |  | 0 | 71914 | 71912
72011 | Tonkawa - Ranger Camp 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Tonkawa | Ranger Camp | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3025 | 2027-12-15 |  | 345 | 0 | 21.3 | 0 |  | Mitchell | Scurry | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10049, 11048 | Y |  |  | 0 | 81371 | 72011
81296 | Prong Moss – Rockhound 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Prong Moss | Rockhound | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3025 | 2027-12-15 |  | 345 | 0 | 60.2 | 0 |  | Midland | Howard | Tier 1 | 23RPG029 |  |  |  | 10062, 10057 | Y |  |  | 0 | 81297 | 81296
81440 | Wolf to Monahan to Pecos / Odessa EHV to Reiter138 kV Line Rebuild | 138 kV existing line rebuild. |  | Wolf/Odessa EHV | Pecos/Reiter | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8527, R8629 | 2027-12-16 |  | 138 | 0 | 11.6 | 0 |  | Ward | Ector | Tier 3 |  |  |  |  | 1013, 1027, 1107, 11117, 18545 | Y |  |  | 0 | 81441 | 81440
57910 | Uvalde to West Batesville: Rebuild 138 kV Line | Rebuild the Uvalde to West Batesville 138 kV line | In-Service Date Update | Uvalde | West Batesville | Planned | 1117 - 1295 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3836 | 2027-12-31 |  | 138 | 0 | 20.6 | 0 |  | Uvalde | Zavala | Tier 4 |  |  |  |  | 8234, 8236 | Y | N |  | 0 | 65580 | 57910
72032 | Stewart to West Bay Ckts 48A & 59A Upgrades | Reconductor Ckts. 48A & 59A Stewart to West Bay as a Hardening upgrade. |  | Stewart | West Bay | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 40 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 43290, 43520, 43521 | N |  |  | 0 | 72033 | 72032
73100 | Asherton to Piloncillo: Rebuild 138 kV Line | Rehab Asherton to Piloncillo 138 kV line | In-Service Date Update | ASHERTON | PILONCILLO | Planned | TA2021030 | AEP TCC | William Simmons mlforcum@aep.com 918-599-2674 |  | 2027-12-31 |  | 138 | 0 | 13.43 | 0 |  | Dimmit | Dimmit | Tier 4 |  |  |  |  | 8283, 8970, 80481 | Y |  |  | 0 | 73101 | 73100
76237 | Lobo: new 345 kV terminal | Cuchillas Solar interconnection to Lobo station | In-Service Date Update | Lobo |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2023320 | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80219 | Y |  |  | 0 | 76238 | 76237
78461A | West Columbia to Damon and Needville to Big Creek Ckt.89A Upgrades | Rebuild/reconductor portions of West Columbia to Damon Ckt.89A as a Hardening upgrade. |  | West Columbia | Damon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 6.6 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 78462 | 78461
45566 | Holly - Southside: 138 kV Line Rating Increase | Increase MOT for Holly - Southside 138 kV Line | NEW | Holly | Southside | Planned | 994 - 1172 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3747 TP-2019-065 | 2028-01-30 |  | 138 | 0 | 1.8 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8483, 8486 | Y | N |  | 0 | 65532 | 45566
59394 | Pointer to Rule: Rebuild 69 kV Line | Rehab the Pointer to Rule 69 kV Line | In-Service Date and Service Level kV Update | Pointer | Rule | Planned | 1122 - 1300 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 1867 | 2028-01-31 |  | 69 | 0 | 14.78 | 0 |  | Haskell | Knox | Tier 4 |  |  |  |  | 6014, 6115, 763, 6120, 60346 | Y | N |  | 0 | 59395 | 59394
55624 | Escondido to Ganso: Rebuild 138 kV line | Rebuild 138 kV line from Escondido to Ganso | In-Service Date Update | Escondido | Ganso | Planned | 1105 - 1283 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3825 | 2028-02-28 |  | 138 | 0 | 10.198 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  |  | 8260, 8267 | Y |  |  | 0 | 65575 | 55624
55626 | Ganso to Hamilton Road: Rebuild 138 kV line | Rebuild 138 kV line from Ganso to Hamilton Road | In-Service Date Update | Maverick | Hamilton Road | Planned | 1105 - 1283 | AEP TCC | Bill Roberts mlforcum@aep.com 918-599-2674 | 3824 | 2028-02-28 |  | 138 | 0 | 41.1 | 0 |  | Maverick | Val Verde | Tier 3 | 22RPG044 | 2022-12-15 | 2023-01-17 |  | 8267, 8692, 8255 | Y |  |  | 0 | 65576 | 55626
80970 | Joule: Construct New 345 kV Station | Interconnect Zeissel Solar and Storage to the new Joule 345 kV station on the Clear Crossing to Coulomb 345 kV line | NEW | Joule |  | Planned | TP2024020 | ETT TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2028-02-28 |  | 345 | 0 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  |  | 60094, 60702, 60722 | Y | Y |  | 0 | 80971 | 80970
80327 | RTP projects included the addition of 18.4 MVAR capacitor at Whitesboro SW | RTP projects included the addition of 18.4 MVAR capacitor at Whitesboro SW |  | Whitesboro SW | Whitesboro SW | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-03-15 |  | 138 | 0 | 0 | 0 | 0,18.4 | Grayson | Grayson | Tier 4 |  |  |  |  | 718 | Y |  |  | 0 | 80328 | 80327
80330 |  |  |  | DWU Southside | McCree | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-03-15 |  | 69 | 0 | 7.45 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 230, 832 | Y |  |  | 0 | 80331 | 80330
80334 |  |  |  | CONCORD | WILDCAT TAP | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-03-15 |  | 138 | 0 | 4.9 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 388, 394 | Y |  |  | 0 | 80335 | 80334
51001 | Friess Ranch to Sonora: Rebuild 69 kV line | Rehab Rocksprings to Sonora 69 kV line | In-Service Date Update | Friess Ranch | Sonora | Planned | 1044 - 1217 | AEP TNC/AEP TCC | Dave Baker mlforcum@aep.com 918-599-2674 | 2791 | 2028-03-31 12:00 |  | 69 | 0 | 24.3 | 0 |  | Sutton | Sutton | Tier 3 | 19RPG018 | 2019-10-24 | 2019-11-18 |  | 8238, 8239, 60438, 6513, 60210, 6570 | Y | N |  | 0 | 65554 | 51001
4834 | Cresson - Rocky Creek 138 kV Line | Construct new line | Project Deferral | Cresson | Rocky Creek | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5228 | 2028-05-15 |  | 138 | 3 | 0 | 0 |  | Tarrant | Parker | Tier 2 |  |  |  |  | 1881, 2202 | Y | N |  |  | 12436 | 4834
71877 | CPSE_Cagnon to Shepherd Rebuild (Phase B) |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0281 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5054, 5378, 5230, 5465 | Y |  |  | 0 | 71878 | 71877
73053 | Wimberley Loop to New Substation | Adds new 138 kV branch (219 MVA) from Wimberley to a new three terminal ring bus substation between Dripping Springs and Rutherford. |  | Wimberley | Cebolla Creek | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2028-05-15 |  | 138 | 13.44 | 0 | 0 |  | Hays | Hays | Tier 2 | 22RPG026 | 2022-08-29 | 2023-02-03 |  | 70511, 70496, 70509, 70512 | Y | N |  | 0 | 73054 | 73053
81225 | Cattleman - Morgan Creek CT Yard 138 kV Double-Circuit Line | Construct a new 138 kV double-circuit line from Cattleman to Morgan Creek CT Yard |  | Cattleman | Morgan Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8647 | 2028-05-15 |  | 345 | 0 | 6.6 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10054, 1032 | Y |  |  | 0 | 81226 | 81225
70796 | El Campo to Pulsar: Rebuild 138 kV line | Rehab 138 kV Line from El Campo to Pulsar | In-Service Date Update | El Campo | Pulsar | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TA2018020 | 2028-05-31 |  | 138 | 0 | 13.26 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8099, 8102, 8192 | Y |  |  | 0 | 70797 | 70796
80420 |  | Rebuild / Reconductor Greens Prairie to South Switch 138kV Line |  | Bryn South Switch | Greens Pairie | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-06-01 |  | 138 | 0 | 4.5 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32007, 32880, 32878, 32893 | Y |  |  | 0 | 80421 | 80420
81588 | Chalybe: Expand station with two new 345/138 kV autotransformers to interconnect Delta | Interconnect Delta at the 345 kV Chalybe station | NEW | Chalybe |  | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2028-06-01 |  | 345 | 46 | 0 | 1350 |  | Cameron |  | Tier 4 |  |  |  |  | 88337, 79500, 79501, 8735 | Y | N |  | 0 | 81589 | 81588
81302 | Rockhound - Midland East 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Rockhound | Midland East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3025 | 2028-06-15 |  | 345 | 0 | 24.2 | 0 |  | Midland | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1021, 10062 | Y |  |  | 0 | 81303 | 81302
55605 | Rebuild 69 kV line from Campwood to Rocksprings | New Barksdale to Rocksprings: Rebuild 69 kV line | In-Service Date Update | New Barksdale | Rocksprings | Planned | 1102 - 1280 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3819 | 2028-08-31 |  | 69 | 0 | 19.51 | 0 |  | Edwards | Edwards | Tier 3 |  |  |  |  | 8365, 8238 | Y |  |  | 0 | 65572 | 55605
55617 | Rebuild 69 kV line from Campwood to Rocksprings | Campwood to New Barksdale: Rebuild 69 kV line | In-Service Date Update | New Barksdale | Campwood | Planned | 1102 - 1280 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3820 | 2028-08-31 |  | 69 | 0 | 7.73 | 0 |  | Edwards | Edwards | Tier 3 |  |  |  |  | 8633, 8365 | Y |  |  | 0 | 65573 | 55617
70630 | Ballinger to Santa Anna: Rebuild 69 kV line | Rebuild 69 kV line and rebuild taps on the Ballinger to Santa Anna 69 kV line. | In-Service Date Update | Ballinger | Santa Anna | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2021193 | 2028-08-31 |  | 69 | 0 | 0 | 0 |  | Runnels | Coleman | Tier 3 | 22RPG028 | 2022-08-01 | 2022-09-01 |  | 6341, 6342, 6344, 6345, 6346, 60019, 60024, 60029, 6329, 6338, 6343, 6349, 6353 | Y |  |  | 0 | 70664 | 70630
66492D | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Chico West - Chico City Services 69 kV Line |  | Chico City Services | Chico West | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3006 | 2028-09-15 |  | 69 | 0 | 6 | 0 |  | Jack | Jack | Tier 4 |  |  |  |  | 1553, 1554 | Y |  |  | 0 | 76368 | 66492
5889 | MIRAGE - 138kV Substation Removal | Remove 138kV MIRAGE customer-owned substation from CEHE service. |  | MIRAGE | MCCABE/BIMONT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42360, 40209, 42351, 40200 | N | N |  |  | 13606 | 5889
50876 | Victoria to Port Lavaca: Retire 69 kV Line | Retire 69 kV Line on Victoria to Port Lavaca | In-Service Date and Estimated Cost Update | Port Lavaca | Victoria | Planned | 1054 - 1227 | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 | 3782 | 2028-11-30 |  | 69 | 0 | 29 | 0 |  | Calhoun | Victoria | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8135, 8136, 8169 | Y | N |  | 0 | 50877 | 50876
55470 | Bison to Ozona: Rebuild 69 kV Line | Rehab 69 kV line from Bison to Ozona | Project Title and In-Service Date Update | Bison | Ozona | Planned | 1095 - 1273 | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 | 1863 | 2028-11-30 |  | 69 | 0 | 27 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  |  | 6549, 6560, 60395 | Y | N |  | 0 | 65570 | 55470
69277 | Cangrejo to Carbide: Rebuild 138 kV Line | Rebuild 138 kV Line from Cangrejo to Carbide | In-Service Date and RPG Dates Update | Cangrejo | Carbide | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2028-11-30 |  | 138 | 0 | 11 | 0 |  | Calhoun | Calhoun | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8140, 8155, 8190, 8723 | Y |  |  | 0 | 69278 | 69277
78545 | Brookhollow to Cangrejo: Rebuild 69 kV Line | Rebuild 69 kV line from Brookhollow to Cangrejo | Project Title, Project Description, In-Service Date, Dollars, and Service Level kV Update | Brookhollow | Cangrejo | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2028-11-30 |  | 69 | 0 | 2.15 | 0 |  | Calhoun | Calhoun | Tier 1 |  |  |  |  | 8133, 8135, 8720, 8723 | Y |  |  | 0 | 78546 | 78545
3818 | Rebuild Calallen to Robstown | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Calallen | Robstown | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-12-01 |  | 69 | 0 | 6.26 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5626, 5634 | Y | N |  |  | 11275 | 3818
84902 | Rebuild Spruce to Pawnee into a double circuit |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5400, 5725 | Y |  |  | 0 | 84903 | 84902
81236 | Cattleman – Longshore 345 kV Double-Circuit Line Rebuild | Rebuild the existing 345 kV Double Circuit Line |  | Cattleman | Longshore | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3025 | 2028-12-15 |  | 345 | 0 | 66.8 | 0 |  | Howard | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1058, 18548, 10053 | Y |  |  | 0 | 81385 | 81236
81240 | Consavvy – Odessa EHV 345 kV Double Circuit Line Rebuild | Rebuild the existing 345 kV Double-Circuit Line |  | Consavvy | Odessa EHV | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3025 | 2028-12-15 |  | 345 | 0 | 40 | 0 |  | Midland | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1125, 11016, 11028, 11387, 18540, 18548 | Y |  |  | 0 | 81241 | 81240
81277 | Midland East – Midland County NW 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Midland East | Midland County Northwest | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3025 | 2028-12-15 |  | 345 | 0 | 42.6 | 0 |  | Midland | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1021, 1185 | Y |  |  | 0 | 81278 | 81277
81268 | Longshore – Consavvy 345 kV Double-Circuit Line Rebuild | Rebuild existing 345 kV Double-Circuit Line |  | Cattleman | Longshore | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3025 | 2028-12-16 |  | 345 | 0 | 66.8 | 0 |  | Howard | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1058, 11387, 18548 | Y |  |  | 0 | 81388 | 81268
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2028-12-22 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 7239 | Y | N |  |  | 10694 | 3336
67915 | Asherton to West Batesville: Rebuild 138 kV Line | Rehab Asherton to West Batesville 138 kV line | Project Title, Project Description, Transmission Owner Update | Asherton | West Batesville | Planned |  | AEP TCC/ETT | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2028-12-30 |  | 138 | 0 | 36.09 | 0 |  | Dimmit | Zavala | Tier 3 |  |  |  |  | 8236, 8283, 8285 | Y |  |  | 0 | 67916 | 67915
50645 | CPSE_Rafter 138kV Cap Bank | [6 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-01-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5355 | Y |  |  | 0 | 50646 | 50645
73116 | Install new Cedar Port Mobile (CDM) 138kV Distribution Substation | Install new Cedar Port Mobile (CDM) 138kV Distribution Substation. Loop from existing Ckt.03B to create new Ckt.03B Trinity Bay to Cedar Port Mobile to KENNY tap. |  | Cedar Port Mobile | Trinity | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-01-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40921, 48360, 41610 | N | N |  | 0 | 73120 | 73116
80323 | Add 2nd transformer at Retta Substation | Add 2nd transformer at Retta Substation |  | Retta | Retta | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-15 |  | 138 | 0 | 0 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 429 | Y |  |  | 0 | 80324 | 80323
80346 |  |  |  | SANDY SWITCH | CRUTCHFIELD | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-15 |  | 138 | 0 | 3.2 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 5, 8 | Y |  |  | 0 | 80347 | 80346
80373 |  |  |  | IOLA | CRUTCHFIELD | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-15 |  | 138 | 0 | 5.5 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 4, 8 | Y |  |  | 0 | 80374 | 80373
80579 | La Palma to Stewart Road: Convert to 138 kV | Convert the La Palma to Stewart Road 69 kV line to 138 kV | NEW | La Palma | Stewart Road | Planned | TA2020071 | AEP TCC | William Lovelace mlforcum@aep.com 918-599-2674 |  | 2029-03-30 |  | 138 | 0 | 37.5 | 0 |  | Cameron | Hidalgo | Tier 3 | 23RPG005 | 2023-03-01 | 2023-03-23 |  | 8040, 8701, 8703, 8748, 8751, 8949, 80104, 5778, 8310, 8314, 8951, 80229 | Y | N |  | 0 | 80580 | 80579
50898 | Alamito Creek to Paisano to Alpine: Rebuild 69 kV line | Rehab Alamito Creek to Paisano to Alpine 69 kV line | In-Service Date Update | Alamito Creek | Alpine | Planned | 1045 - 1218 | AEP TNC | Charles Gibson twang1@aep.com 918-599-2635 | 2793 | 2029-03-31 |  | 69 | 0 | 22.26 | 0 |  | Presidio | Brewster | Tier 4 | 20RPG017 |  |  |  | 6667, 6666, 6672 | Y | N |  | 0 | 50899 | 50898
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0385 | 2029-05-15 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5416, 5250, 5395 | Y | N |  | There are no transformers associated with this project | 10365 | 3021
72051 | Twinwood Mobile (TWM) 138kV Distribution Substation | Install new Twinwood Mobile (TWM) 138kV Distribution Substation. Loop from existing Ckt.25E to create new Ckt.25E Foster to Twinwood Mobile to Peters |  | Twinwood | Foster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-30 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44861, 44256, 46220 | N | N |  | 0 | 72052 | 72051
64065 | Alice to Kingsville 138 kV Line Rebuild | Rebuild the Alice to Kingsville 138 kV line to address aging infrastructure | Transmission Status and In-Service Date Update | Alice | Kingsville | Conceptual |  | AEP TCC | Michael Glueck mlforcum@aep.com 918-599-2674 | TA2021079 | 2029-05-31 |  | 138 | 0 | 22.48 | 0 |  | Jim Wells | Kleberg | Tier 4 |  |  |  |  | 8503, 8518 | Y |  |  | 0 | 66649 | 64065
6687 | Rebuild Rio Hondo to East Rio Hondo | Rebuild the 138 kV line from Rio Hondo to East Rio Hondo. |  | Rio Hondo | East Rio Hondo | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-06-01 |  | 138 | 0 | 8.19 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5764, 8319 | Y | N |  |  | 14458 | 6687
84898 | New Eastside Switching Station |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5295, 5035, 5110, 5250, 5294, 5371, 5395, 5400, 5485 | Y |  |  | 0 | 84899 | 84898
80297 | Add 2nd load at Muenster | Add 2nd load at Muenster |  | Muenster | Muenster | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-07-15 |  | 138 | 0 | 0 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 695 | Y |  |  | 0 | 80298 | 80297
14TPIT0098 | Cost Substation Addition | Upgrade the existing 69-kV substation |  | Cost |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2029-10-26 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7622 | Y | N |  | 0 | 78325 | 3321
6685 | Van Vleck substation loop | Replaces single circuit radial line connected to a pole mounted switch with a double circuit transmission loop to the Van Vleck substation and upgrades the 4/0 ACSR to 795 ACSR on 138 kV capable poles. |  | Van Vleck Substation | Van Vleck Switch | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-12-01 |  | 69 | 2 | 2 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5556, 5557, 5558, 5560 | Y | N |  |  | 14456 | 6685
59260 | Mason Phillips Tap to Mason Phillips: Rebuild 69 kV Line | Rehab the Mason Phillips Tap to Mason Phillips 69 kV Line | Contact, Schedule Update | Seaquist | Mason Phillips | Planned | 1127 - 1305 | AEP TNC | Christopher Carroll twang1@aep.com 918-599-2635 | 1872 | 2029-12-01 |  | 69 | 0 | 13.7 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6395, 6407, 60458 | Y | N |  | 0 | 65588 | 59260
84900 | Rebuild Pawnee to Tango into a double circuit |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5725, 8689 | Y |  |  | 0 | 84901 | 84900
61552 | Matador to Turkey: Rebuild 69 kV Line | Rebuild 69 kV line from Matador to Turkey | In-Service Date and Estimated Cost Update | Matador | Turkey | Planned | 1128 - 1306 | AEP TNC | Shawn Ketcher twang1@aep.com 918-599-2635 | 1873 | 2029-12-31 |  | 69 | 0 | 26.9 | 0 |  | Motley | Hall | Tier 4 |  |  |  |  | 6020, 6044, 6024, 6039, 6041, 6140, 60351 | Y | N |  | 0 | 65596 | 61552
70898 | Flomot Tap: Rebuild 69 kV Line | Rehab Flomot Tap 69 kV Line | In-Service Date, Estimated Cost Update | Flomot Tap | Flomot | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2029-12-31 |  | 69 | 0 | 7.06 | 0 |  | Motley | Motley | Tier 4 |  |  |  |  | 6041, 6042 | Y | N |  | 0 | 70899 | 70898
61550 | East Munday to Lake Pauline: Rebuild 138 kV Line | Rehab East Munday to Lake Pauline 138 kV line | In-Service Date Update | East Munday | Lake Pauline | Planned | 1129 - 1307 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 1874 | 2030-04-30 |  | 138 | 0 | 59.97 | 0 |  | Knox | Hardeman | Tier 4 | 20RPG018 |  |  |  | 6037, 6050, 6110 | Y | N |  | 0 | 65594 | 61550
52070 | Carver to Maxwell: Rebuild 138 kV line | Rehab Carver to Maxwell 138 kV Line | Transmission Owner, TSP/Company Contact, In-Service Date Update | Carver | Maxwell | Planned | 1079 - 1252 | AEP TCC/AEP TNC | Charity Kreher twang1@aep.com 918-599-2635 | 3804 | 2030-05-31 |  | 138 | 0 | 60.24 | 0 |  | Sutton | Val Verde | Tier 3 | 22RPG042 | 2022-12-02 | 2022-12-28 |  | 8259, 8261, 60412, 8991, 8998, 60440 | Y | N |  | 0 | 65562 | 52070
70889 | SA College Hills: Rebuild 69 kV Station | Rehab SA College Hills Station | In-Service Date Update | SA College Hills |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2031-04-30 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6468, 6470 | Y |  |  | 0 | 70890 | 70889
72956 | Bellville South - Prairie View Transmission Line Upgrade | the proposed project converts the existing 69kV transmission line T283 from Bellville South- Quanex Sw - Sunnyside - Prarie View substation to 138kV. The proposed project improves the reliabiltiy of transmission facilities on the 26.1 mile transmission line and increases the line capacity for long term system growth. |  | Bellville South | Prairie View | Conceptual | Project transitioned to STEC from LCRA . Previous Mod Project #47428 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-05-15 |  | 69 | 0 | 0 | 0 |  | Austin | Waller | Tier 3 |  |  |  |  | 7269, 57660, 57664, 57666 | N | N |  | 0 | 72957 | 72956
3595 | Bevo to AEP Carrizo Springs 69 kV line | Add 2 mile line by double circuiting two existing circuits, as recommended in 2013 RTP. |  | Bevo | Carrizo Springs | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 69 | 0 | 2 | 0 |  | Dimmit | Dimmit | Tier 1 |  | 2012-04-12 | 2012-08-12 | 2012-09-12 | 5871, 8244 | N | N |  | This new line was part of Karnes and Medina Electric Cooperatives Project that was approved in 2012. This also helped voltage on AEP transmission under contingencies. While much of the projected load is now on the system, not all of the projected load materialized. Studies with newer load projections have not shown the need for this line. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 10984 | 3595

## CompletedTPIT060124NoCost
JUNE BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 6/1/2024
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
5430Q | Conversion to 138kV | Retire the existing 69kV RD Wells substation together with the autotransformers |  | RD Wells |  | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2023-01-01 | 2019-07-01 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 932, 930 | Y | N | N/A | 0 | 55211 | 5430
5430H | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the Reconstruct 69kV BonnieBrae-NLakes sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2023-01-01 | 2018-12-11 | 138 | 0 | 1.521 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 928, 931 | Y | N | N/A | 0 | 55202 | 5430
5430P | Conversion to 138kV | Transfer the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2023-01-01 | 2019-07-01 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 910, 932 | Y | N | N/A | 0 | 55210 | 5430
67900 | NBU ECMornhinweg Substation Upgrade | NBU is adding a second power transformer at EC Mornhinweg and reconfiguring the substation to a ring bus arrangement. |  | EC Mornhinweg | GPI Switch | Under Construction | 61593 | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2023-01-01 01:00 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 | [5 empty] | Y | N |  | 0 | 67901 | 67900
68754 | Buchanan Ranch 138 kV Expansion | Expand existing substation with additional transformers and capacitor bank |  | Buchanan Ranch | Buchanan Ranch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8616 | 2023-01-05 | 2023-10-15 | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 11335, 23857, 23858 | Y |  |  | 0 | 68756 | 68754
62450 | Pin Oak 138 kV Switch (Formerly Big Brown Tap) | Pin Oak 138 kV Switch (Formerly Big Brown Tap) |  | Pin Oak | Pin Oak | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2014 | 2023-01-15 |  | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3505, 3506, 3510, 196, 212, 3507 | Y |  |  | 0 | 62451 | 62450
69904 | Interconnects Leon Creek Bitcoin |  |  | TNMP Leon Creek (bus # 38355) | Customer substation (bus # 38356) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-01-15 |  | 138 | 0 | 0 | 0 | 0,160 | Pecos | Pecos | Tier 4 |  |  |  |  | 38356, 38355 | Y |  |  | 0 | 69905 | 69904
66020 | New substation to connect Mustang Creek INR | New substation to connect Mustang Creek INR |  | Galow |  | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-01-27 | 2022-11-15 | 138 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5521, 5523, 78104 | Y | N |  | 0 | 66021 | 66020
63433 | Rebuilds AEP Creosote-TNMP Coyanosa138 kV line as Dbl Ckt |  |  | AEP Creosote (bus # 60377) and TNMP TransPecos Tap (bus # 38376) | TNMP Coyanosa (bus # 38380) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-01-28 |  | 138 | 0 | 0.87 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38376, 38380, 60377 | Y |  |  | 0 | 63434 | 63433
66530 | Add Consavvy 345/138 kV Switch | Add Consavvy 345/138 kV Switch |  | Consavvy | Consavvy | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8498 | 2023-01-30 | 2023-02-14 | 345 | 0 | 0 | 1200 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 11386, 11387, 11388, 11389, 1030, 1058, 1125, 1133, 1329, 11016, 11123, 19000, 23856, 23860 | Y |  |  | 0 | 66531 | 66530
58006 | Magnolia Cap Bank | Install Cap bank at Magnolia | IN-SERVICE | Magnolia |  | In-Service |  | AEP TCC | James Douglas bcogan@aep.com 918-599-2674 | TP2020066 | 2023-01-30 | 2022-12-19 | 138 | 0 | 0 | 0 | 0,14.4 | Karnes |  | Tier 4 |  |  |  |  | 8583 | Y |  |  | 0 | 58007 | 58006
61875 | Hungerford to East Bernard Ckt.60 Upgrades | Upgrade Hungerford to East Berrnard Ckt.60 to increase thermal limits |  | Hungerford | Caney | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-01-31 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44150, 44190 | Y | N |  | 0 | 61876 | 61875
57167 | Faysville substation conversion from 69 to 138 kV | Converts Faysville to 138 and connects to Redgate |  | Faysville | Red Gate | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-01-31 | 2023-06-15 | 138 | 8.46 |  | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5780, 5782, 5786, 5788, 5784, 8377 | Y | N |  | 0 | 63732 | 57167
51996 | Rebuild Markham Tap to AEP Markham Tap | Rebuild Markham Tap to AEP Markham Tap with 138 kV capable structures |  | Markham Tap | AEP MarkhamTap | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-02-15 | 2023-06-15 | 69 | 0 | 1.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5557, 8984 | Y | N |  | 0 | 51997 | 51996
59763 | Construct three terminal 138 kV capable switching station | Change Markham hard wire tap point to 3 way switching station |  | Cayce Switch |  | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-02-15 | 2023-05-15 | 69 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5554, 5557, 5555, 5556, 8984 | Y | N |  | 0 | 65899 | 59763
59518 | upgrade the Desoto-Sterrett 138 kV Line | upgrade the existing Desoto-Sterrett 138 kV Line |  | Desoto | Sterrett | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4122 | 2023-02-15 | 2023-01-15 | 138 | 0 | 8.3 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  |  | 217, 2317, 2424 | Y |  |  | 0 | 59519 | 59518
4146 | Hillje 345kV Substation Expansion for Juanita Hill Solar - (21INR0480) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Juanita Hill Solar |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-02-28 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 11666 | 4146
65652 | Interconnects Tarbush Data Canter |  |  | TNMP Tarbush (bus # 38295) | Customer substation (bus # 38296) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-02-28 |  | 138 | 0 | 0 | 0 | 0,160 | Pecos | Pecos | Tier 4 |  |  |  |  | 38296, 38295 | Y |  |  | 0 | 65653 | 65652
72593B | Marshall Ford to Trading Post Storm Hardening | Phase 1: Reconductor segment of T323 Marshall Ford to Paleface and T315 Marshall Ford to Trading Post that is double circuit using Galveston ACCC conductor. (Replaces ERCOT Project # 61264B) |  | Marshall Ford | Trading Post | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-02-28 |  | 138 | 0 | 3.6 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70477, 77356 | Y | N |  | 0 | 72594 | 72593
58542B | CATTAIL_SUBSTATION | 1) Cat Tail to Cherokee 138kv line |  | Cherokee (39075) | Cat Tail ( 38580 ) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-03-01 |  | 138 | 1.5 | 0 | 0 |  | Galveston | Galveston | Tier 2 |  | 2020-04-16 | 2020-09-16 |  | 38580, 39075 | Y |  |  | 0 | 71934 | 58542
54084 | King Mountain Sub Upgrade | Provide transmission service to a generator. Add a 138-kV bay and associated circuit breaker to the existing substation. ERCOT (ERCOT Generation Interconnection or Change Request No. 20INR0226) |  | King Mountain Sub | King Mountain Sub | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-03-01 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 76635 | Y | N |  | 0 | 54085 | 54084
57343 | Rosita Creek Substation 138-kV T2 Power Transformer Addition | Add second 138/13.09-kV power transformer bay with new 138-kV transmission switch and circuit switcher interconnected at LCRA Switch# 12669. New power transformer capacity will be 15/20/25 MVA. | Recent projected load increases beyond ALDR. Justification is to provide on-site backup power source for new and existing critical medical center, governmental and educational facility loads. Power transformer lead-time increases. | Pueblo | Escondido | Planned |  | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2023-03-01 |  | 138 | 0 | 0 | 0 |  | Maverick | Maverick | Tier 4 | [5 empty] | Y | N |  | 0 | 57344 | 57343
69483 | Wolf Tank Storage Interconnect | Wolf Tank Storage Interconnect | IN-SERVICE | Lobo Station | Wolf Tank Storage WSL | In-Service |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2021136 | 2023-03-03 | 2023-03-03 | 138 | 0.2 | 0 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 80221 | Y |  |  | 0 | 69484 | 69483
61356 | Hays Energy-Henne Split Transmission Line Upgrade | This project will increase the reliability and capacity of the transmission facilities on the T389 Bergheim to Hays Energy 5.4-mile 345-kV section of transmission line by replacing the aging conductor from Hays Energy Substation to Henne Split. |  | Hays Energy | Henne Split | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-03-03 |  | 345 | 0 | 5.4 | 0 |  | Hays | Comal | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7043, 7770 | Y | N |  | 0 | 78301 | 61356
59265 | Hurst - International Airport 138 kV Double-Circuit Line Section | Upgrade existing 138 kV Line |  | Hurst | International Airport | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5216 | 2023-03-15 | 2022-12-15 | 138 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 2115, 2116, 2117, 2121, 2125, 2243, 2244 | Y |  |  | 0 | 59266 | 59265
7124 | Flat Iron - Barr Ranch - Pegasus South 138 kV Line | Construct new Flat Iron - Barr Ranch - Pegasus South 138 kV Line and Barr Ranch 138 kV Switch |  | Flat Iron | Pegasus South | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8574 | 2023-03-15 | 2023-05-15 | 138 | 18 | 0 | 0 | 0,55.2 | Midland | Midland | Tier 2 | 21RPG010 | 2021-06-02 | 2021-06-23 | 2021-12-13 | 11235, 1237, 11217 | Y |  |  | 0 | 62668 | 7124
14TPIT0010 | Handley - Sherry 138 kV line | Upgrade existing line |  | Handley | Sherry | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5155-E | 2023-03-15 12:00 | 2022-12-15 | 138 | 0 | 8.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1919, 1920, 1950, 1951, 2245, 2247, 2251, 2252 | Y | N |  | 0 | 59262 | 2582
72593A | Marshall Ford to Trading Post Storm Hardening | Phase 2: Rebuild single circuit section of Marshall Ford to Trading Post (T315) and reconductor with bundled 795 ACSR Conductor, 440 MVA; Reconductor segment of T323 Marshall Ford to Paleface that is double circuited with T315 using Cardinal ACCC conductor. (Replaces ERCOT Project # 61264A) |  | Marshall Ford | Trading Post | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-03-22 |  | 138 | 0 | 4.1 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7356, 70505 | Y | N |  | 0 | 72595 | 72593
50440 | Delhi Substation Addition | Add a new load serving substation 10 miles north of IH-10 along 304, w/30 MVA PWT. |  | Delhi | Delhi | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-03-31 |  | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7896 | Y | N |  | 0 | 50441 | 50440
57645 | Hillje 345kV Danish Fields Solar (21INR0069) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Danish Fields Solar |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 57646 | 57645
4895 | CPSE_Capitol Cement Transmission Reconfiguration | Re-configurate Capitol Cement by loop into the existing Dresden to Skyline 138 kV transmission line and removing the existing Captiol Cement to Tuttle 138 kV transmission line. |  | Capitol Cement | Dresden/Skyline | Planned | S-0767, S-0961 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0246 | 2023-03-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5075, 5130, 5370, 5435 | Y | N |  |  | 12507 | 4895
51734 | Blue Stem to Delhi Transmission Line | Build new 9.5 mile 138/69 kV transmission. |  | BlueStem | Delhi | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-03-31 02:00 |  | 69 | 9.5 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7895, 7230, 7231, 7896 | Y | N |  | 0 | 51843 | 51734
72392 | TNMP_72392_OLD_OCEAN_SLCP_IMPEDANCE_RECONDUCTOR | REBUILD OLD-OCEAN TO PHILLIPS 5 |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-04-01 | 2023-05-03 | 69 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39750, 39870 | Y |  |  | 0 | 72393 | 72392
78339 | [7 empty] | RYBRN |  |  | 2023-04-13 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6795, 6999, 2625 | Y |  |  | 0 | 78340 | 78339
61436 | Bastrop West - Split Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 2.4-mile portion of Bastrop West ¿ Sim Gideon (T410) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Bastrop West | Sim Gideon | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-04-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 | 22RPG005 | 2022-03-04 |  |  | 7555, 7310 | Y | N |  | 0 | 78305 | 61436
72599 | Hunter to McCarty Lane Storm Hardening | Phase 2: Rebuild single-circuit section of Hunter to McCarty Lane 138 kV with single, circuit bundled 795 ACSR Conductor, 440 MVA. (Replaces ERCOT Project # 61262) |  | McCarty Lane | Hunter | Planned |  | PEC/LCRATSC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-04-22 |  | 138 | 0 | 1.57 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 70491 | Y | N |  | 0 | 72601 | 72599
63900 | Nebula: Build New 345 kV Station | Interconnect Andromeda Solar on the Dermott to Figaro 345 kV Line | IN-SERVICE | Nebula |  | In-Service | 1135 - 1313 | ETT TNC | Adam Wells twang1@aep.com 918-599-2635 | 1880 | 2023-04-29 | 2023-04-29 | 345 | 0 | 0 | 0 |  | Scurry |  | Tier 4 |  |  |  |  | 60011, 11305, 60715 | Y | N |  | 0 | 63901 | 63900
70188 | LCRATSC_ClearSprings_CB_Addition | Provide a transmission point of interconnection for a new Battery Energy Storage System at the Clear Springs Substation by adding an additional 138-kV double bus, double breaker bay to accommodate the new interconnection. Contingency Update |  | Clear Springs | Clear Springs | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-04-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 | [5 empty] | Y | Y |  | 0 | 70189 | 70188
61865 | Muldoon Substation Addition | Provide transmission service to a generator. LCRA TSC will construct a new substation, Muldoon Substation, on T133 between LCRA TSC Flatonia and Plum Substations and more specifically between str #192 and str #197. The substation will be a three breaker ring bus configuration and will provide a 138-kV line termination for a 240 MW solar generation facility. |  | Muldoon Substation | Muldoon Substation | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-04-30 |  | 138 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  |  | 7279, 7248, 7274 | Y | N |  | 0 | 61866 | 61865
56003G | Mont Belvieu Reliability Project | Upgrade Ckt.84D Cedar Bayou Plant to Cedar Bayou Tap to HOPSON with minimum 682MVA Emergency Rating |  | Cedar Bayou Plant | Cedar Bayou/HOPSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-04-30 |  | 138 | 0 | 8.61 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40012, 40015, 41690 | Y | N |  |  | 56081 | 56003
70998 | Hillje 345kV Substation - Danish Fields Battery Storage - Generator Interconnection (21INR0450) | Install Danish Fields Battery Storage¿ Connect at the same generator lead as Danish Fields Solar I-II-III at Hillje CNP station. |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-04-30 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 70999 | 70998
66011C | CNP ARCHER POI for BROTMAN Power | Upgrade Ckt 26 Angleton to WINMIL to increase thermal limits |  | Angleton | WINMIL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-04-30 12:01 |  | 138 | 0 | 1.15 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 44531 | Y | N |  | 0 | 72742 | 66011
59095 | Athey: Build 138 kV Temporary Hard Tap | Build new 138 kV temporary tap on the Ft Stockton to Rio Pecos 138 kV line | IN-SERVICE | Athey |  | In-Service | 1123 - 1301 | AEP TNC | Shawn Ketcher twang1@aep.com 918-599-2635 | 1868 | 2023-05-01 | 2023-05-01 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60792, 60718, 60798 | Y | N |  | 0 | 59096 | 59095
73494 | Frontera Interconnection | Interconnect Frontera IPP at Frontera SW | IN-SERVICE | Frontera SW |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2023-05-02 | 2023-05-02 | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 | [5 empty] | Y | N |  | 0 | 73495 | 73494
52064 | Bay City - Lane City: 138 kV Line Rebuild | Rebuild the Bay City - Magill - Lane City 138 kV Line | IN-SERVICE | Bay City | Lane City | In-Service | 1078 - 1251 | AEP TCC | Marc E. Wilson mlforcum@aep.com 918-599-2674 | 3803 | 2023-05-03 | 2023-05-03 | 138 | 0 | 16 | 0 |  | Matagorda | Wharton | Tier 3 |  |  |  |  | 8111, 8113, 8127 | Y | N |  | 0 | 65558 | 52064
45101 | Chavaneaux_Chavaneaux Tap (Chavaneaux to Palo Alto)- 138 kV | CPSE_Chavaneaux_Chavaneaux 138 kV Tap Rebuild (Chavaneaux to Palo Alto). |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0256 | 2023-05-04 |  | 138 | 0 | 0.9 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5085, 5330 | Y |  |  | 0 | 45102 | 45101
58008 | Laredo VFT North to Las Cruces: Rebuild 138 kV Line | Rebuild Laredo VFT North to Las Cruces 138 kV line | IN-SERVICE | Laredo | Laredo | In-Service | 1116 - 1294 | AEP | William Lovelace mlforcum@aep.com 918-599-2674 | 3835 | 2023-05-04 | 2023-05-04 | 138 | 0 | 0.48 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8112, 80013 | Y |  |  | 0 | 76075 | 58008
70902 | LCRATSC_Settlers_Substation_Addition | Provide two transmission Points of Interconnection (POIs) on LCRA TSC-owned transmission lines T231 Bastrop City to Webberville and T171 Austrop to Sim Gideon to serve new BBEC customer load. |  | Austrop, Webberville | Sim Gideon, Bastrop City | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org +151-257-84514 |  | 2023-05-11 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7327, 7328, 7310, 7322, 7329, 9328 | Y | N |  | 0 | 70903 | 70902
7161 | Naval Base to North Padre Island: Rebuild 69 kV Line | Rehab Naval Base to North Padre Island 69 kV line | IN-SERVICE | Naval Base | North Padre Tap | In-Service | 909 - 1087 | AEP TCC | Bill Roberts mlforcum@aep.com 918-599-2674 | 3690 | 2023-05-11 | 2023-05-11 | 69 | 0 | 12.7 | 0 |  | Nueces | Nueces | Tier 3 | 19RPG001 | 2019-02-06 | 2019-03-06 |  | 8495, 8847, 8856 | Y | N |  | 0 | 65519 | 7161
61853 | LCRATSC Lampasas Substation Upgrade | This project will improve the reliability of Lampasas Substation by replacing obsolete and aged equipment and by converting the substation from single-bus-single-breaker design to double-bus-double-breaker design. Lampasas Substation is an important hub for the transmission system in Burnet, Lampasas, San Saba, and Mills counties, and this project will improve transmission system reliability in those areas. |  | Lampasas | Lampasas | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Lampasas | Lampasas | Tier 4 | [5 empty] | Y | N |  | 0 | 61854 | 61853
61455 | Hunt - Ingram Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 6.4-mile Hunt ¿ Ingram (T487) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Hunt | Ingram | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7144, 7142 | Y | N |  | 0 | 61456 | 61455
61599 | Pinto Creek Circuit Breaker Addition | This project provides a point of interconnection for a new generator by converting Pinto Creek Substation into a ring bus (GINR # 21INR0019). |  | Pinto Creek | Pinto Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kinney |  | Tier 4 |  |  |  |  | 78255 | Y | N |  |  | 61600 | 61599
53968 | Fayetteville_Salem_TransmissionLine_Rehabilitation | Increase the reliability of transmission facilities on the T177 Fayetteville to Salem 138-kV and T211 FPP Yard #1 to Salem 345-kV 19.3-mile double-circuit transmission line by replacing the existing Condor conductor from Fayetteville Substation to Salem Substation. |  | Fayetteville | Salem | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 345 | 0 | 19.3 | 0 |  | Fayette | Washington | Tier 3 | 22RPG011 | 2022-04-19 |  |  | 7056, 7286, 7058, 7289 | Y | N |  | 0 | 78300 | 53968
66175 | Liggett 138 kV Terminal Equipment | Upgrade the terminal equipment at Liggett 138 kV Switch |  | Liggett |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4094 | 2023-05-15 | 2023-05-30 | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 1922, 1924, 2053, 2055 | Y |  |  | 0 | 66176 | 66175
61440 | Harper Road - Jack Furman Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 4.6-mile Harper Road ¿ Jack Furman (T368) transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Harper Road | Jack Furman | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7140, 7141 | Y | N |  | 0 | 61441 | 61440
62669 | Pegasus South - Pleasant Farms Tap 138 kV Line Rebuild | Rebuild existing Pegasus South - Pleasant Farms Tap 138 kV Line |  | Pegasus South | Pleasant Farms Tap | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8574 | 2023-05-15 | 2023-05-30 | 138 | 0 | 9.6 | 0 |  | Midland | Ector | Tier 4 | 21RPG010 | 2021-06-02 | 2021-06-23 | 2021-12-13 | 1236, 1237, 71230 | Y |  |  | 0 | 62672 | 62669
54080 | Lockhart - Lulig Transmission Line Overhaul | LCRA TSC will perform an overhaul of T184 (from Lockhart structure #301 to Luling) with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T184 will be 795 ACSR Drake. Note: Condor conductor replacement (from Lockhart to structure #301) will be taken into account on Lockhart - Split Transmission Line Upgrade project with ISD of May 15, 2023. |  | Lockhart (structure #301) | Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7216, 7224 | Y | N |  | 0 | 54081 | 54080
71871 | Update Line Characteristics and Rating. |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0280 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5053, 5054, 5230, 5378 | Y |  |  | 0 | 71872 | 71871
66196 | WichitaFalls PPG Terminal Equipment | Upgrade the existing terminal equipment at PPG |  | Wichita Falls PPG |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4025 | 2023-05-15 | 2023-05-11 | 138 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | 1484, 1485, 17005 | Y |  |  | 0 | 66197 | 66196
61453 | Ingram - Jack Furman Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 3.3-mile Ingram ¿ Jack Furman (T521) transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Ingram | Jack Furman | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7142, 7141 | Y | N |  | 0 | 61454 | 61453
54082 | Lockhart - Red Rock Transmission Line Overhaul | LCRA TSC will perform an overhaul of T578 (from Lockhart structure #301 to Red Rock) with replacement structures that are capable of operating at 138-kV and supporting a single 959 ACSR Suwannee conductor. The replacement conductor on T578 will be 959 ACSR Suwannee. This overhaul will include the installation of a 72-count optical ground wire (OPGW). Note: Condor conductor, new OPGW and any structure replacement (from Lockhart to structure #301) will be taken into account on Lockhart - Split Transmission Line Upgrade project with ISD of May 15, 2023. |  | Lockhart (structure #301) | Red Rock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Bastrop | Tier 4 |  |  |  |  | 7216, 7560 | Y | N |  | 0 | 54083 | 54082
53958 | Fairland - Lago Vista Transmission Line Rehabilitation | Increase the reliability of transmission facilities on the T414 Fairland - Lago Vista 21-mile 138-kV transmission line by replacing the existing Condor conductor with Drake conductor. |  | Fairland | Lago Vista | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Burnet | Travis | Tier 3 | 22RPG029 | 2022-09-14 |  |  | 70352, 7518 | Y | N |  | 0 | 53959 | 53958
72564 | Buttercup Bus Upgrade | Upgrade the Buttercup bus from operate/transfer to double-bus double-breaker. Replaces Project ID 51740. |  | Buttercup |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 70531 | Y | N |  | 0 | 72565 | 72564
63929 | Buntin Drive 69 kV Substation Conversion To 138 kV | Convert Buntin Drive 69 kV Substation To 138 kV |  | Buntin |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4064 | 2023-05-15 | 2023-05-26 | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2984, 2486, 2494, 2951 | Y |  |  | 0 | 63930 | 63929
62636 | Rebuild Waco West (Peppervine) 138 kV Switch | Rebuild Waco West (Peppervine) 138 kV Switch |  | Waco West | Waco West | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6141 | 2023-05-15 | 2023-11-28 | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3446, 3436, 3433, 3560, 3563, 3590, 3591, 3437, 13436 | Y |  |  | 0 | 62637 | 62636
62349 | Rebuild Fairfield West as Ranchland 138 kV Switch | Rebuild Fairfield West as Ranchland 138 kV Switch |  | Ranchland | Ranchland | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6136 | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3504, 3558, 196, 3495, 3503, 3625, 13501, 13681 | Y |  |  | 0 | 71865 | 62349
61591 | Sandy Creek Autotransformer Upgrade | Increase the reliability of substation equipment at Sandy Creek Substation through the replacement of the Sandy Creek 138/69-kV AT1 autotransformer with a new 70 MVA unit. Increase the capacity of T400 Sandy Creek - Sunrise Beach 69-kV transmission circuit by upgrading limiting element jumper at Sunrise Beach Substation. |  | Sandy Creek | Sunrise Beach | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7121, 7400, 7127 | Y | N |  | 0 | 61592 | 61591
54103 | Hilltop - Strahan Transmission Line Upgrade | Increase the reliability of transmission facilities on the T445: Hilltop ¿ Strahan 1.25-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | Hilltop | Strahan | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7190, 7193 | Y | N |  | 0 | 54104 | 54103
53999 | ElCampo - Ricebird Transmission Line Strom Hardening | Increase the reliability of transmission facilities on the T589 El Campo ¿ Ricebird 4.6-mile 138-kV transmission line. |  | El Campo | Ricebird | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8102, 78104 | Y | N |  | 0 | 54000 | 53999
67766 | Southlake Capacitors | Install new 138 kV capacitor bank |  | Southlake |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3011 | 2023-05-15 | 2023-05-26 | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 2020 | Y |  |  | 0 | 67767 | 67766
59263 | Weatherford Switch - Azle 138 kV Line | Upgrade existing 138 kV Line |  | Weatherford | Azle | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5172 | 2023-05-15 | 2023-05-01 | 138 | 0 | 11.5 | 0 |  | Parker | Tarrant | Tier 4 |  |  |  |  | 1592, 2062, 15015 | Y |  |  | 0 | 59524 | 59263
67906 | LCRATSC_WeltnerRoad_CB_Addition | LCRA TSC will install circuit breakers at Weltner Road Substation in order to increase the reliability to the load served by NBU. This project will also configure the bus at Weltner Road to a ring bus. Update contingencies |  | Weltner Road | Weltner Road | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG +151-257-84514 |  | 2023-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 | [5 empty] | Y | N |  | 0 | 67907 | 67906
52318 | Royse Switch - Greenbriar Switch 138 kV Line | Upgrade the Royse Switch - Greenbriar Switch 138 kV Line |  | Royse | Greenbriar | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4292 | 2023-05-15 01:00 | 2023-09-22 | 138 | 0 | 0 | 0 |  | Collin | Rockwall | Tier 3 | 20RPG002 |  | 2020-04-13 |  | 2706, 2472, 2708, 12527 | Y |  |  | 0 | 52319 | 52318
67610 | LCRATSC_ChiefBrady_Substation_Upgrade | Chief Brady Substation will be upgraded to increase the bus rating and replace equipment identified as obsolete. The substation upgrade will also install Tier 3 Physical Security Measures. -Contingency Update |  | Chief Brady | Chief Brady | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG +151-257-84514 |  | 2023-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 | [5 empty] | Y | N |  | 0 | 67611 | 67610
56350A | Burnett - Bowie 69 kV Line | Rebuild Smith Creek - Tower one 69 kV Line (FKA Bellevue - Bowie) and establish Hopewell Switch |  | Bowie | Ringgold Magnolia Tap | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4015 | 2023-05-17 | 2023-05-26 | 69 | 0 | 10 | 0 |  | Montague | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 1540, 1547, 1548, 1549, 1550, 11548, 11550, 17010, 632, 768, 33770, 11582 | Y | N |  | 0 | 73038 | 56350
4487 | Nueces Area 69kV Reinforcement | Expand and add new 138/69kV Auto at Valero East 69kV substation. Add 5th breaker to Champlin 138kV substation. Construct Champlin to Valero East 138kV Line. | IN-SERVICE | Champlin | Valero East | In-Service | 709 - 0879 | AEP TCC | John Pulay mlforcum@aep.com 918-599-2857 | 2903 TP2016067 | 2023-05-22 01:00 | 2023-05-22 | 138 | 1.6 | 0 | 200 |  | Nueces |  | Tier 4 | 19RPG011 |  |  |  | 8528, 8476 | Y | N |  |  | 13570 | 4487
59452 | Air Liquide Pass Through 138 kV Station | Air Liquide to construct 138 kV Ring Bus | IN-SERVICE | Dupont SW Ingleside |  | In-Service |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2020197 | 2023-05-26 | 2023-05-26 | 138 | 0.01 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8978, 8979, 8422, 8818 | Y | Y |  | 0 | 59453 | 59452
71299 | McKenzie to Westside: Rebuild 138 kV Line | Rebuild McKenzie to Westside 138 kV Line | IN-SERVICE | McKenzie Road | Westside | In-Service | 968 - 1146 | ETT TCC | James Weaver mlforcum@aep.com 918-599-2674 | TP2018126 | 2023-05-30 | 2023-05-30 | 138 | 0 | 11.48 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8485, 8858 | Y | N |  | 0 | 71300 | 71299
59804C | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86N Jonte to Lockwood tap to Scenic Woods radial |  | Lockwood | Jonte/Scenic Woods | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46331, 46032, 45660, 46336 | Y | N |  | Cost included in main project | 72789 | 59804
72057 | Greens Bayou to LYCHEM Ckt.08 Upgrade (2023) | Rebuild and reconductor a de-energized section of Ckt.38Z. Loop the rebuilt section into 138kV Ckt.08F between Moore Road and Uvalde tap. The reconfiguration creates additional conductor impedance on the line to increase the fault duty margin for future generation. |  | Moore Road | Uvalde | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 3.25 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40559, 40281, 40555, 41023, 41651 | Y | N |  | 0 | 72784 | 72057
68242A | Garrott to Midtown to Polk Ckt.90 Upgrades Phase Two | Replace Midtown reactor R2 at 0.343 Ohm. Adjust underground circuit ratings to reflect the updated reactor R2 values. |  | Garrott | Midtown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47661, 47707, 47708, 47709, 47730, 47706, 47731 | Y | N |  | 0 | 72026 | 68242
59804B | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86M Jonte to Greens Road tap |  | Jonte | Greens Road | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45821, 45660, 46331 | Y | N |  | Cost included in main project | 72791 | 59804
70606 | ARCHER to Karsten Ckt.26 Upgrades | Upgrade Ckt.26 Archer to Karsten to increase thermal limits. |  | ARCHER | Karsten | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 8.51 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44410 | Y | N |  | 0 | 70607 | 70606
66043B | Ckt29 THW-WhiteOak Reconductor and 138kV Conversion | Reconductor remaining portions of 69kV Ckt.29A TH Wharton to Little York to White Oak for 138kV conversion. Reconnect as 138kV Ckt.11A TH Wharton to Little York to White Oak. Swap positions for Ckt.95A and Ckt. 81K at the approach spans into TH Wharton. |  | TH Wharton | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 12.33 | 0 |  | Harris | Harris | Tier 4 | 21RPG016 | 2021-09-08 | 2021-09-30 | 2021-09-30 | 45512, 45990, 45995, 45101, 45510, 45511, 45515, 45530, 45781, 45862, 46100, 46301, 45500, 45760, 45782, 45921, 45922, 46615, 46620, 46660 | Y | N |  | 0 | 72853 | 66043
63971 | Mykawa Distribution Facilities | Install distribution facilities at MYKAWA substation |  | Mykawa |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 42751, 42752, 42753, 42750, 42741, 42742, 43051 | Y | N |  | 0 | 63972 | 63971
67270C | BP23 Reliability Upgrades | Upgrade Ckt.08L HO Clarke to BUNKER to increase thermal limits |  | HO Clarke | BUNKER | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 | 2023-05-31 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47150, 47340 | Y | N |  | 0 | 67273 | 67270
62133 | West Columbia to Damon Ckt.89A Thermal Uprate | Upgrade West Columbia to Damon to Ckt.89A to Minimum 210 MVA Continuous rating |  | West Columbia | Damon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 10.3 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42370, 43380, 43384 | Y | N |  | 0 | 62134 | 62133
59804A | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86E Crosby to Newport to Jonte |  | Jonte | Crosby/Newport | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 41150, 46032 | Y | N |  | 0 | 72790 | 59804
64505A | Flewellen to Peters Ckt.25E Upgrades | Upgrade Ckt.25E Flewellen to Foster to increase thermal limits |  | Flewellen | Foster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:01 |  | 138 | 0 | 1.9 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 21RPG011 | 2021-06-04 | 2021-07-02 |  | 44230, 44256, 44861, 46220 | Y | N |  | 0 | 64506 | 64505
65716A | Jonte Related Upgrades | Upgrade Ckt.86N Jonte to Lockwood tap to increase thermal limits |  | Jonte | Lockwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 0.1 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 46032 | Y | N |  | 0 | 65717 | 65716
65716B | Jonte Related Upgrades | Install 20 MVAR cap bank at Jonte substation |  | Jonte |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 0 | 0 | 0,20 | Harris |  | Tier 4 |  |  |  |  | 45660 | Y | N |  | 0 | 65718 | 65716
66013 | CNP WATERHOLE POI for G Star Solar | New 345kV Waterhole (WAT) substation for generator interconnection to G-Star Solar. Loop Ckt.62 into substation to create new Ckt.62 Bailey to Waterhole to Jones Creek. |  | Waterhole | BAILEY/Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 345 | 0.08 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44880, 42530, 44040 | Y | N |  | 0 | 66014 | 66013
61362 | Henne-River Oaks Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the 2.4-mile T237 River Oaks to Henne 138-kV and T389 Bergheim to Hays Energy 345-kV double-circuit transmission line between River Oaks Substation and Henne Split and the 1.4-mile T237 River Oaks to Henne 138-kV single-circuit transmission line between Henne Split and Henne Substation by replacing the aging conductors. |  | Henne | River Oaks | Planned | 61406, 61358, 61392, 61350, 61234, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-15 |  | 345 | 0 | 3.8 | 0 |  | Comal | Comal | Tier 4 | 22RPG005 | 2022-03-04 |  |  | 7173, 7770, 7043, 7172 | Y | N |  | 0 | 78302 | 61362
66194A | Holliday - Navy Kickapoo 69 kV Line | Establish Pecan Tree and Shortgrass 138 kV substations |  | Holliday | Bowman | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4022 | 2023-06-15 | 2023-04-01 | 138 | 0 | 0 | 0 |  | Archer | Archer | Tier 4 |  |  |  |  | 11525, 11528, 1527, 1424, 1431, 11527 | Y |  |  | 0 | 78352 | 66194
61932A | Holliday - Seymour 69 kV Line | Rebuild the Holliday - Seymour 69 kV Line. |  | Holliday | Seymour | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4028 | 2023-06-15 | 2023-03-01 | 69 | 0 | 0 | 0 |  | Archer | Baylor | Tier 3 | 21RPG007 | 2021-04-26 | 2021-05-18 |  | 1527, 1530, 1532, 1534 | Y |  |  | 0 | 73027 | 61932
57925 | Midland County Northwest to Texaco Mabee Tap 138 kV Double-Circuit Line Section | Add Midland County NW - Texaco Mabee Tap 138 kV Double-Circuit Line Section Rebuild |  | Midland County Northwest | Texaco Mabee Tap | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8558 | 2023-06-15 01:00 | 2022-12-21 | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 | 21RPG003 | 2021-02-16 | 2021-03-12 |  | 11299, 11300, 11301, 1178, 1179, 1182, 1183, 1174 | Y |  |  | 0 | 60059 | 57925
66621 | Sandhills - Sandhills Tap 138 kV Line Rebuild | Add Sandhills - Sandhills Tap 138 kV Line Rebuild |  | Sandhills | Sandhills Tap | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8612 | 2023-06-16 | 2023-05-30 | 138 | 0 | 23 | 0 | 0,55.2 | Ector | Crane | Tier 4 |  |  |  |  | 10006, 10007, 1103, 1104, 11111, 11117 | Y |  |  | 0 | 66681 | 66621
3505 | Cibolo Substation, T3 transformer addition | Add T3, 40 MVA 138-26.18 kV power transformer, CSW and low side |  | Cibolo |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-06-21 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7608 | Y | N |  |  | 10887 | 3505
61459 | Buchanan CTEC-Buchanan Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 2.8-mile Buchanan ¿ Buchanan CTEC (T106) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Buchanan CTEC | Buchanan | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7092, 7101 | Y | N |  | 0 | 61460 | 61459
54204 | Gonzales - Hochheim Transmission Line Overhaul | Increase the reliability and capacity of transmission facilities on the T542 Luling ¿ Cuero 19.6-mile 69-kV transmission line from Gonzales (structure #33) to Hochheim Tap. LCRA TSC will perform an overhaul of T542 with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T542 will be 795 ACSR Drake. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Gonzales | DeWitt | Tier 4 |  |  |  |  | 7223, 78577 | Y | N |  | 0 | 54205 | 54204
59317 | Deer Park Tap to Cardiff Ckt.96E Upgrades | Upgrade Deer Park Tap to Cardiff Ckt.96E to Minimum 300 MVA Emergency rating |  | Deer Park | Cardiff | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-06-30 |  | 138 | 0 | 5.8 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42240, 42610, 43250, 48085, 48401, 48108, 48388 | Y | N |  | 0 | 78245 | 59317
71942 | LCRATSC_Birdhouse_Substation_Addition | LCRATSC will provide a point of interconnection for a new solar and battery energy storage system at a new 138-kV Birdhouse Substation |  | Birdhouse | Birdhouse | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 |  | 138 | 0 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  |  | 7255, 7224, 7245 | Y | N |  | 0 | 72418 | 71942
61461 | Buchanan CTEC - Pitsburg Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 14.5-mile Buchanan CTEC ¿ Pitsburg (T267) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Buchanan CTEC | Pitsburg | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Llano | Llano | Tier 3 | 22RPG030 | 2022-09-14 |  |  | 7101, 7119, 7116 | Y | N |  | 0 | 61462 | 61461
72874 | LCRATSC Twin Buttes 345-kV CB Addition | This project provides a point of interconnection for a new solar and battery energy storage system at the 345-kV Twin Buttes Substation by adding a position to an existing breaker-and-a-half bay to accommodate the interconnection. Update contingencies |  | Twin Buttes |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-06-30 |  | 138 | 1 | 0 | 0 |  | Tom Green |  | Tier 4 | [5 empty] | Y | N |  | 0 | 72875 | 72874
45084B | Braunig to Highland Rebuild | Rebuild approximately sixteen circuit miles of 138kV transmission from Braunig to Highland Hills/Brooks. This rebuild is between 'Schillers Tap to Braunig'. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0194, T-0238 | 2023-07-15 |  | 138 | 0 | 16 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5095, 5205 | Y |  |  | 0 | 45086 | 45084
50446 | Santa Clara Substation Addition | Add a new load serving substation 10 miles west of City of Seguin, of IH-10, w/ twin 40 MVA PWTs. |  | Santa Clara Substation | Santa Clara Substation | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-07-28 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7891 | Y | N |  | 0 | 50447 | 50446
51736 | Cibolo to McQueeney Transmission Line | Install 10.62 miles of 1192 Bunting to existing transmission structures, circuit to help with load flows per the TPA and will be source for Santa Clara Substation. |  | Cibolo | McQueency | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-07-28 |  | 138 | 10.62 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7608, 7606 | Y | N |  | 0 | 51737 | 51736
51841 | Cibolo-McQueeney Tap to Santa Clara Transmission Line Addtition | Build 5 onmiles of new double circuit 138kV t-line loop, 1192 ACSR Bunting, from H-pole structure to Santa Clara Substation |  | H-pole ( Structure/Tap) | Santa Clara | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-07-28 |  | 69 | 10 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7606, 7608, 7891 | Y | N |  | 0 | 57331 | 51841
59398B | San Bernard (SAN) Sub for Brazoria County Solar (20INR0098) | Upgrade San Bernard to West Columbia Ckt.60 to increase thermal limits. Increase fault duty at West Columbia to 63KA |  | San Bernard | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-07-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43010, 43110, 43190, 43341, 43120, 43380 | Y | N |  | 0 | 59768 | 59398
63493 | Noelke to Schneeman Draw 2nd circuit | Add the 2nd circuit to the CREZ Noelke to Schneeman Draw 345 kV line |  | Noelke | Schneeman Draw | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-07-31 | 2023-12-05 | 345 | 15.8 | 0 | 0 |  | Crockett | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 7053, 76005 | Y | N |  |  | 63494 | 63493
52183 | EXTER 69kV Substation Removal | Remove EXTER 69kV Substation from Ckt.53B |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-07-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Harris | Tier 4 |  |  |  |  | 42600, 43510, 49087, 42080, 44440, 43500 | Y | N |  | Cost included in MOD 52181 - ENCO new customer sub | 73718 | 52183
63491 | Schneeman Draw to Big Hill 2nd circuit | Add the 2nd circuit to CREZ Schneeman Draw to Big Hill 345 kV line |  | Schneeman Draw | Big Hill | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-07-31 | 2023-12-06 | 345 | 59.1 | 0 | 0 |  | Crockett | Schleicher | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76003, 76005 | Y | N |  |  | 63492 | 63491
64572A | HO Clarke Bus Upgrade | Upgrade bus work at HO Clarke 138kV facilities |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-07-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47150, 47175, 47170 | Y | N |  | 0 | 64573 | 64572
64572B | HO Clarke Bus Upgrade | Upgrade Ckt.90A HO Clarke to HOC TR1 to increase thermal limits |  | HO Clarke | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-07-31 00:02 |  | 138 | 0 | 0.44 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47175, 47151 | Y | N |  | Cost included in main entry | 64574 | 64572
73381 | TNMP_JACKRABBIT_CUTIN_AC_4-5-2023 |  |  | BUS 38091 TNPECOS___1 | BUS 38114 TNREEVSCOT1 | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-08-02 | 2023-09-01 | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38095, 38091, 38114 | Y |  |  | 0 | 73382 | 73381
58917 | Horizon 138 bus and line to Pearsall | Adds new Horizon Switch station to connect Horizon solar generation and a line to Pearsall |  | Horizon Swttch | Pearsall | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-08-11 | 2023-07-15 | 138 | 0.4 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5897, 5895 | Y | N |  | 0 | 58918 | 58917
61851 | Marion AT2 Autotransformer Upgrade | Increase the reliability of substation equipment at Marion Substation through the replacement of the Marion AT2 345/138-kV autotransformer and installation of three 345-kV shunt reactors. |  | Marion 345 | Marion 138 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-08-25 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7044, 7178, 7822 | Y | N |  | 0 | 61852 | 61851
5166 | Poesta to Three Rivers: Rebuild 69 kV line | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. | IN-SERVICE | Borglum | Three Rivers | In-Service | 742 - 0925 | AEP TCC | Dave Gotez bcogan@aep.com 918-599-2857 | 2915 | 2023-08-29 | 2023-08-29 | 138 | 6 | 22 | 0 |  | Bee | Live Oak | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8156, 8142, 8199, 84006, 8196, 8400, 8403 | Y | N |  | 0 | 57889 | 5166
57890 | Brightside Permanent Connection | Construct Charter Station | IN SERVICE | Beeville | Three Rivers | In-Service | 1114 - 1292 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3833 | 2023-08-30 | 2023-08-30 | 138 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8142, 8156, 8403 | Y |  |  | 0 | 57891 | 57890
60530 | Rebuild TI-South with 959 ACSS | update the impedance |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-09-01 |  | 138 | 0 | 2.76 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 37080, 37100 | Y |  |  | 0 | 60531 | 60530
57731B | Hornsby Substation Addition | Construct a new 345-kV substation between Clear Springs to Gilliland Creek 345-kV transmission line to provide transmission service to a load-serving substation. Restore 138-kV transmission line from Decker to Sand Hill by removing temporary substation/arrangements made in first phase to serve load. |  | Clear Springs | Gilleland Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-09-29 |  | 345 | 0 | 0 | 960 |  | Travis | Travis | Tier 4 |  |  |  |  | 7047, 7916, 7050, 9187, 7340, 9216 | Y | N |  | 0 | 57740 | 57731
71946 | LCRATSC_Hornsby_CircuitBreaker_Addition | Provide transmission service to a generator by adding an additional breaker-and-a-half bay to Hornsby Substation to accommodate a new circuit termination. |  | Hornsby |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-09-29 |  | 345 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 | [5 empty] | Y | N |  | 0 | 71947 | 71946
73129 | Cenizo: Build 345 kV terminal | Build new terminals at Cenizo, Del Sol, Lobo, and Pomelo | IN-SERVICE | Cenizo |  | In-Service |  | ETT TCC | James Weaver mlforcum@aep.com 918-599-2674 | TP2021704 | 2023-10-13 | 2023-10-13 | 345 | 0 | 0 | 0 |  | Webb |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80220 | Y | Y |  | 0 | 73130 | 73129
67904 | Haggerty 138 kV Switch | Establish Haggerty 138 kV Switch |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4330 | 2023-10-15 | 2021-11-04 | 138 | 0 | 0 | 0 |  | Grayson |  | Tier 4 |  |  |  |  | 1740, 2644, 12677, 1714, 1715, 1717, 1749, 1750, 1753 | Y |  |  | 0 | 67905 | 67904
70824 | Lavender 138 kV Switch | Establish Lavender 138 kV Switch |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5326 | 2023-10-15 | 2023-06-15 | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2261, 2429, 2967 | Y |  |  | 0 | 70825 | 70824
66218A | Hillsboro - Italy 69 kV Line | Rebuild the Hillsboro-Milford 69 kV Line |  | Hillsboro | Milford | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4326 | 2023-10-15 | 2023-12-15 | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  | 2021-04-23 | 2021-05-18 |  | 2338, 3523 | Y |  |  | 0 | 73689 | 66218
71161 | Haggerty-Anna and Haggerty-Stone Creek 138 kV Lines | Establish Haggerty-Anna and Haggerty-Stone Creek 138 kV Lines |  | Haggerty | Anna and stone creek | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4333 | 2023-10-15 | 2023-10-03 | 138 | 0 | 0 | 0 |  | Grayson | Grayson | Tier 4 |  |  |  |  | 1713, 1699, 1715, 1717, 1753, 1754, 1839, 12677 | Y |  |  | 0 | 71162 | 71161
72346 | FM524_CUT_IN_LINE_S | CUTING FM524 INTO LINE S |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-10-23 | 2023-10-15 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 39703, 110505 | Y |  |  | 0 | 72347 | 72346
71944 | LCRATSC_SingleTree_Substation_Addition | LCRATSC will provide a transmission point of interconnection for a new wind resource on the Noelke – Schneeman Draw 345-kV double circuit transmission line by adding a new 345-kV breaker-and-a-half substation, Single Tree Substation. |  | Single Tree | Single Tree | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-10-30 |  | 345 | 0 | 0 | 0 |  | Crockett | Crockett | Tier 4 |  |  |  |  | 76004, 7053, 76005 | Y | N |  | 0 | 72350 | 71944
66200A | Upgrade Taylor - Holland 69 kV Line | Rebuild the Holland - Bartlett Tap 69 kV Line |  | Taylor | Holland | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6173 | 2023-10-30 | 2023-11-15 | 69 |  | 5.7 | 0 |  | Bell | Bell | Tier 4 | 22RPG036 |  |  |  | 3646, 13647 | Y |  |  | 0 | 66201 | 66200
69475 | Wormser Road: Install cap bank | Install cap bank at Wormser Road | IN-SERVICE | Wormser |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2023-10-30 | 2023-10-30 | 138 | 0 | 0 | 0 | 0,23 | Webb |  | Tier 4 |  |  |  |  | 8295 | Y | N |  | 0 | 69476 | 69475
76137 | Molina: Install cap bank | Install cap banks at Santo Nino, Molina, and Wormser Road | IN-SERVICE | Molina |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2023-10-30 | 2023-10-30 | 138 | 0 | 0 | 0 | 0,15.4 | Webb |  | Tier 4 |  |  |  |  | 80230 | Y |  |  | 0 | 76138 | 76137
69007 | Tiempo: Build new 345 kV station | Construct new Tiempo 345 kV station for the ETT 2nd circuits project | N-SERVICE | Tiempo |  | In-Service |  | ETT TCC | Adam Wells mlforcum@aep.com 918-599-2674 | TP2021706 | 2023-10-30 | 2023-10-30 | 345 | 0 | 0 | 0 |  | Zapata |  | Tier 1 |  |  |  |  | 80224, 80226, 80220, 162499 | Y | Y |  | 0 | 69008 | 69007
64999C | PH Robinson to LaMarque Ckt.93B Upgrades | Rebuild and reconductor portions of Ckt.93B Hitchcock to LarMarque as a Hardening upgrade. Upgrade substation equipment at Hitchcock to increase thermal limits. |  | Hitchcock | LarMarque | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 138 | 0 | 4.95 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-13 | 2021-05-14 | 42800, 42860 | Y | N |  |  | 65002 | 64999
59804E | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.90C to create new Ckt.90E Jonte to Lockwood tap to Lauder tap to Scenic Woods radial |  | Jonte | Lockwood/Lauder/Scenic Woods | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46031, 45660 | Y | N |  | Cost included in main project | 72793 | 59804
72236 | Hawk Hollow Sw (Eiffel Solar) | Establish Hawk Hollow Sw |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4346 | 2023-10-31 | 2022-12-31 | 138 | 0 | 0 | 0 |  | Lamar | Lamar | Tier 4 |  |  |  |  | 11768, 1693, 1768, 11770, 144263 | Y |  |  | 0 | 72237 | 72236
59804D | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.90C to create new Ckt.90C North Belt to Greens Road tap to Jonte |  | Greens Road | North Belt/Jonte | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45822, 46112, 45660, 46031 | Y | N |  | Cost included in main project | 72792 | 59804
43460 | Moody to Stewart Ckt.63 Upgrades P1016 | Upgrade Ckt.63 Moody to Stewart as a Hardening project |  | Moody | Stewart | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 138 | 0 | 3.81 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42950, 42951, 42952, 42953, 43290, 43355, 43405, 43520, 43521 | Y |  |  | 0 | 43461 | 43460
57350 | Lyons to Gay Hill T-line pole change out and reconductor | Replace existing structure with upgraded structures and replace existing 336.4 ACSR Linnet with 795 ACSR Drake on Lyons to Gay Hill transmission line. |  | Lyons | Gay Hill | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet.coop curtis.fischer@bluebonnet (979) 716-0253 |  | 2023-10-31 |  | 138 | 0 | 11.51 | 0 |  | Burleson | Washington | Tier 4 |  |  |  |  | 7572, 7573 | Y |  |  | 0 | 57351 | 57350
64999A | PH Robinson to LaMarque Ckt.93B Upgrades | Rebuild and reconductor portions of Ckt.93B AlgoaCorner to Alta Loma as a Hardening upgrade. |  | PH Robinson | Alta Loma | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 138 | 0 | 22.31 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-13 | 2021-05-14 | 42015, 42061 | Y | N |  | 0 | 65000 | 64999
68242B | Garrott to Midtown to Polk Ckt.90 Upgrades Phase Two | Adjust underground circuit ratings to reflect the updated reactor R2 values. |  | Midtown | Polk | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47707, 47709, 47731, 47730 | Y | N |  | 0 | 72027 | 68242
64999B | PH Robinson to LaMarque Ckt.93B Upgrades | Rebuild and reconductor portions of Ckt.93B Alta Loma to Hitchcock as a Hardening upgrade. Upgrade substation equipment at Hitchcock to increase thermal limits. |  | Alta Loma | Hitchcock | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 00:01 |  | 138 | 0 | 6.38 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-13 | 2021-05-14 | 42061, 42800 | Y | N |  |  | 65001 | 64999
68673 | Reconductor TNMP Wink-Oncor Wink Ckt 2 |  |  | TNMP WInk (37900) | Oncor Wink (1074) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-11-01 |  | 138 | 0 | 1.18 | 0 |  | Winkler | Winkler | Tier 4 |  |  |  |  | 1074, 37900 | Y |  |  | 0 | 68674 | 68673
5165 | Poesta: Construct a new 138/69 kV station | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. | IN-SERVICE | Borglum |  | In-Service | 742 - 0925 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 2914 TP2014129 | 2023-11-02 | 2023-11-02 | 138 | 0 | 0 | 130 |  | Bee |  | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8196, 8197, 8205, 8107, 8198, 8199, 8904 | Y | N |  |  | 13315 | 5165
67917 | Brackettville and Hamilton Road Relay Upgrades for Pinto Creek | Upgrade relays at Brackettville 138 kV station and upgrade relays at Hamilton Road 138 kV station | IN-SERVICE | Brackettville | Hamilton Road | In-Service |  | AEP TCC | Michael Pitts mlforcum@aep.com 918-599-2674 |  | 2023-11-15 | 2023-11-15 | 138 | 0 | 0 | 0 |  | Kinney | Val Verde | Tier 4 |  |  |  |  | 78255, 8252, 8255 | Y |  |  | 0 | 67918 | 67917
73125 | Del Sol: Line settings | Build new terminals at Cenizo, Del Sol, Lobo, and Pomelo | N-SERVICE | Del Sol |  | In-Service |  | ETT TCC | James Weaver mlforcum@aep.com 918-599-2674 | TP2021704 | 2023-11-16 | 2023-11-16 | 345 | 0 | 0 | 0 |  | Webb |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80335 | Y | Y |  | 0 | 73126 | 73125
45399 | Bearkat Loop - Bearkat to Longshore | Adds 345 KV line from Bearkat to Longshore. |  | Bearkat | Longshore | Planned |  | WETT/ONCOR | Yang Zhang yzhang@wettllc.com 737-218-4520 |  | 2023-11-16 |  | 345 | 27 | 0 | 0 |  | Glasscock | Howard | Tier 1 |  | 2017-08-15 | 2018-09-19 | 2018-10-09 | 1058, 59903 | Y | N |  | 0 | 45473 | 45399
76245 | Pomelo to Pronto: Build new 345 kV line | Install conductor between North Edinburg and Tiempo | IN-SERVICE | Pomelo | Pronto | In-Service |  | ETT TCC | Teresa Trotman mlforcum@aep.com 918-599-2674 | TP2021702 | 2023-11-16 | 2023-11-16 | 345 | 11.5 | 0 | 0 |  | Hidalgo | Starr | Tier 3 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80231, 8574, 80355 | Y | N |  | 0 | 76246 | 76245
69005 | Rapido: Build new 345 kV station | Construct new Rapido 345 kV station for the ETT 2nd circuits project | IN-SERVICE | Rapido |  | In-Service |  | ETT TCC | Adam Wells mlforcum@aep.com 918-599-2674 | TP2021707 | 2023-11-17 | 2023-11-17 | 345 | 0 | 0 | 0 |  | Starr |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80227, 80381, 80355, 161855 | Y | Y |  | 0 | 69006 | 69005
75682 | Add Branch between Libra and Elm Creek |  |  | 5133 | 170882 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2023-11-27 |  | 345 | 0.16 | 0 | 0 |  | Wilson | Guadalupe | Tier 4 |  |  |  |  | 5133, 170882 | Y |  |  | 0 | 75683 | 75682
5792A | Leonard Road Substation 138 | Convert Leonard RD Sub to 138kV. Substation will be on a radial fed out of Smetana Sub until Line from Atkins to Leonard Rd is complete. Leonard Rd has dual voltage Transformer. |  |  |  | Planned |  | BRYN |  |  | 2023-11-30 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32051, 32851, 32864 | Y | N |  | 0 | 72135 | 5792
61400 | Esperanza-Fair Oaks Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the 4.3-mile T503 Esperanza to Fair Oaks Ranch 138-kV and T656 Bergheim to Kendall 345-kV double-circuit transmission line between Esperanza Substation and existing structure #173 and the 0.12-mile T506 Fair Oaks to Fair Oaks Ranch 138-kV and T656 double-circuit transmission line between Fair Oaks Substation and structure #173B by replacing the aging conductors. |  | Esperanza | Fair Oaks | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-11-30 |  | 345 | 0 | 4.42 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 5470, 7710, 7770, 7046, 7169 | Y | N |  | 0 | 78303 | 61400
75901 | Upgrade Ckt.90D Garrott to Midtown to increase thermal limits | Upgrade Ckt.90D Garrott to Midtown to increase thermal limits |  | Garrott | Midtown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47660, 47707, 47661, 47709 | Y | N |  | 0 | 75902 | 75901
67987 | BIGVUE to Channelview Relay Upgrades | Upgrade BIGVUE and Channelview relays to increase thermal limits on Ckt.03G BIGVUE to Lyondell |  | BIGVUE | Lyondell | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40190, 40281, 40280, 48232 | Y | N |  | 0 | 67988 | 67987
7013 | NASA Substation Upgrades | Upgrade substation equipment at NASA on Ckt.06 NASA to Webster to increase thermal limits |  | NASA | NASA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42970, 42610, 43500 | Y | N |  |  | 14835 | 7013
4567 | BRYN_4567_Smetana_to_Leonard | Build Smetana to Leonard Rd 138 line in existing 69KV ROW of old Annex to Atkins line |  | 32897 | 32863 | Planned |  | BRYN |  |  | 2023-11-30 |  | 138 | 0.75 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32850, 32868, 32853, 32851 | Y |  |  | 0 | 76693 | 4567
64491 | Bellaire to Smithers Ckt.98A Upgrade | Upgrade Bellaire to Smithers Ckt.98A to increase thermal limits |  | Bellaire | Smithers | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 47000, 44650 | Y | N |  | 0 | 64492 | 64491
66368 | Rebuild West Columbia Main - Brazoria 138kV with 795 ACSS |  |  | West Columbia Main (bus # 39500) | Brazoria (bus # 39600) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-12-01 |  | 138 | 0 | 10.2 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 39600 | Y |  |  | 0 | 66369 | 66368
64754 |  | Loop new 138kV Crossroads substation into existing 138kV Potranco to AMD transmission line |  |  |  | Planned | T-0310 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0962 | 2023-12-01 | 2022-05-12 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5102, 5002, 5346 | Y |  |  | 0 | 64755 | 64754
66198 | Rebuild West Columbia Main-CNP West Columbia with bundled 795 ACSS |  |  | TNMP West Columbia Main (bus # 39500) | CenterPoint West Columbia (bus # 43380) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-12-01 |  | 138 | 0 | 0.32 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 43380 | Y |  |  | 0 | 66199 | 66198
72570 | PEC_HeroWay_Substation_Addition | Add new three terminal ring bus substation to 138 kV line between Nameless and Leander and install 46.7 MVA distribution transformer. The new substation will be located approximately 3.1 miles (45% of existing line length) from Leander substation. Replaces Project ID 63906. |  | Nameless | Leander | Planned | 61279 | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 70536, 70525, 70526 | Y | N |  | 0 | 72571 | 72570
78281 | [5 empty] | In-Service |  | RYBRN |  |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6791, 6807, 2626 | Y |  |  | 0 | 78282 | 78281
73127 | Pomelo: Construct (2) 345 kV terminals | Build new terminals at Cenizo, Del Sol, Lobo, and Pomelo | IN-SERVICE | Pomelo |  | In-Service |  | ETT TCC | James Weaver mlforcum@aep.com 918-599-2674 | TP2021704 | 2023-12-07 | 2023-12-07 | 345 | 0 | 0 | 0 |  | Starr |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8574 | Y | Y |  | 0 | 73128 | 73127
69002 | Pronto: Build new 345 kV station | Construct new Pronto 345 kV station for the ETT 2nd circuits project | IN-SERVICE | Pronto |  | In-Service |  | ETT TCC | Adam Wells mlforcum@aep.com 918-599-2674 | TP2021709 | 2023-12-08 | 2023-12-08 | 345 | 0 | 0 | 0 |  | Starr |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80231, 80355, 80381, 160885, 161855 | Y | Y |  | 0 | 69003 | 69002
76247 | Rapido to Tiempo: Build new 345 kV line | Install conductor between North Edinburg and Tiempo | IN-SERVICE | Rapido | Tiempo | In-Service |  | ETT TCC | Teresa Trotman mlforcum@aep.com 918-599-2674 | TP2021702 | 2023-12-13 | 2023-12-13 | 345 | 26.5 | 0 | 0 |  | Starr | Zapata | Tier 3 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80224, 80227, 80355 | Y | Y |  | 0 | 76248 | 76247
55299 | Munday to Throckmorton: Rebuild 69 kV line | Rehab 69 kV line from Munday to Throckmorton | IN-SERVICE | Munday | Throckmorton | In-Service | 1094 - 1272 | AEP TNC | Raza Ansari twang1@aep.com 918-599-2635 | 1862 | 2023-12-14 | 2023-12-14 | 69 | 0 | 34.55 | 0 |  | Knox | Throckmorton | Tier 4 | 21RPG015 | 2021-08-24 | 2021-09-28 |  | 6107, 6204, 6205 | Y | N |  | 0 | 65569 | 55299
68768 | Buffalo - Triangle 138 kV Line | Upgrade the existing 138 kV Line |  | Buffalo | Triangle | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8618 | 2023-12-15 | 2023-09-30 | 138 | 0 | 3.5 | 0 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 23837, 23839 | Y |  |  | 0 | 68770 | 68768
64484 | Cumby_Kiowa Conversion | Converting voltages for several Rayburn buses from 69 kV to 138 kV. |  | Cumby | Kiowa | Planned |  | RYBRN |  |  | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Hunt | Hunt | Tier 4 |  |  |  |  | 6823, 6861, 6869, 6871, 37361 | Y |  |  | 0 | 72129 | 64484
65366 | Converts TNMP Lone Oak to 138 kV. | TNMP Lone Oak conversion projected to be ready by 5/15/2023. |  | Rayburn Loan Oak (Bus # 6871) | TNMP Loan Oak (Bus # 37360) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Rains | Rains | Tier 4 |  |  |  |  | 37360, 37361 | Y |  |  | 0 | 65367 | 65366
66571 | Texaco Mabee Tap - Midland East 138 kV Line Rebuild | Add Texaco Mabee Tap - Midland East 138 kV Line Rebuild |  | Texaco Mabee Tap | Midland East | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8304 | 2023-12-15 | 2023-12-15 | 138 | 0 | 15.4 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 11278, 11279, 11280, 1023, 1171, 1178, 1184, 11301 | Y |  |  | 0 | 76426 | 66571
72582B | Nameless to Leander Transmission Line Upgrade | Rebuild and upgrade Leander to Hero Way with double-circuit capable structures. Install 1 ckt with bundled 795 kcmil conductor (440 MVA).(Replaces ERCOT Project # 61279B) |  | Leander | Hero Way | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70525, 70536 | Y | N |  | 0 | 72584 | 72582
59745 | Royse Switch - Oates (GP&L) 138 kV Line | Upgrade existing 138 kV Line |  | Royse | Oates | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4236 | 2023-12-15 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Rockwall | Dallas | Tier 4 | [5 empty] | Y |  |  | 0 | 59746 | 59745
63933 | Cedar Crest 69 kV Substation Conversion To 138 kV | Convert Cedar Crest 69 kV Substation To 138 kV |  | Cedar Crest |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4193 | 2023-12-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2486, 12486, 2495, 2982, 2985, 2493, 2494 | Y |  |  | 0 | 68789 | 63933
50896 | Garnet: Build new 138 kV station | Interconnect Norton solar farm on the Ballinger to Oak Creek 138 kV line | IN-SERVICE | Garnet |  | In-Service | 1049 - 1222 | AEP TNC | Bryan Oyster mlforcum@aep.com 918-599-2674 | 2824 | 2023-12-15 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Runnels |  | Tier 4 |  |  |  |  | 60451, 6325, 6340 | Y | N |  | 0 | 50897 | 50896
64856 | North Edinburg to Palmito: Build second circuit 345 kV line | Hang conductor to complete a double circuit between North Edinburg and Palmito for the ETT 2nd circuits project | IN-SERVICE | North Edinburg | Palmito | In-Service |  | ETT TCC/SHARYLAND | Teresa Trotman mlforcum@aep.com 918-599-2674 | TP2021701 | 2023-12-15 | 2023-12-15 | 345 | 48 | 0 | 0 |  | Hidalgo | Cameron | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8383, 79500 | Y | Y |  | 0 | 68950 | 64856
69417 | Crater Rock 138 kV Switch | Establish Crater Rock 138 kV Switch |  | Horseshoe Springs | Three Mile Draw | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8604 | 2023-12-15 | 2023-12-14 | 138 | 0 | 0 | 0 |  | Culberson | Culberson | Tier 4 |  |  |  |  | 11224, 1095, 11103 | Y |  |  | 0 | 69419 | 69417
71991 | Valley South 345 kV Reactors | Install new 345 kV reactors |  | Valley South |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3013 | 2023-12-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1729 | Y |  |  | 0 | 71992 | 71991
71180 | Hutto - Brushy Creek 138 kV Line | Hutto - Hutto East (Teal) - Brushy Creek 138 kV Line |  | Hutto | Brushy Creek | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6211 | 2023-12-15 | 2023-12-15 | 138 | 11.6 | 10.4 | 0 |  | Williamson | Williamson | Tier 3 | 22RPG016 | 2022-05-01 | 2022-06-01 |  | 3362, 3541, 3673, 3692, 3693 | Y |  |  | 0 | 71181 | 71180
69552A | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 138 kV Switch (Oncor) | Hard Tap POI to be complete in May 2024 | Teal | Teal | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6165 | 2023-12-15 |  | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3362, 3363, 3364, 13364, 3666, 3673 | Y |  |  | 0 | 69553 | 69552
59835 | Royse Switch-Terrell Switch 69 kV Line Conversion to 138 kV | Convert the existing 69 kV Line to 138 kV |  | Royse | Terrell | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3223 | 2023-12-15 |  | 69 | 0 | 0 | 0 |  | Rockwall | Rockwall | Tier 4 |  |  |  |  | 2722, 2773, 12722, 12730, 2463, 2472, 2721, 12729, 2471, 2729, 3188, 12470 | Y |  |  | 0 | 59836 | 59835
72000 | DeCordova Switch_Carmichael Bend Switch 138 kV Line | Upgrade existing DeCordova Switch Carmichael Bend Switch 138 kV Line |  | DeCordova Switch | Carmichael Bend Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3019 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Hood | Hood | Tier 4 |  |  |  |  | 1891, 2888 | Y |  |  | 0 | 72001 | 72000
76564 | Little Pond 345 kV Switch | Establish the Little Pond 345 kV Switch |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6188 | 2023-12-15 | 2023-12-15 | 345 | 0 | 0 | 0 |  | Milam |  | Tier 4 |  |  |  |  | 3377, 3687, 3704 | Y |  |  | 0 | 76565 | 76564
68968 | North Edinburg to Pomelo: Build new 345 kV line | Install conductor between North Edinburg and Tiempo | IN-SERVICE | North Edinburg | Pomelo | In-Service |  | ETT TCC | Teresa Troman mlforcum@aep.com 918-599-2674 | TP2021702 | 2023-12-15 | 2023-12-15 | 345 | 40.501 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 3 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8383, 8574 | Y | Y |  | 0 | 76241 | 68968
62436 | Cedar Hill - Desoto Hampton Road 138 kV Line | Rebuild the existing 138 kV Line |  | Cedar Hill Switch | Desoto Hampton Road | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4175 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 3058, 3059, 3060, 3066, 3065 | Y |  |  | 0 | 62437 | 62436
72002 | Anna Autotransformer #2 tertiary reactors | Install new reactors on Anna Autotransformer #2 |  | Anna |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4013 | 2023-12-15 |  | 345 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  |  | 12374 | Y |  |  | 0 | 72003 | 72002
76385 | Gibson 345 kV Switch | Establish the Gibson 345 kV Switch |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6218 | 2023-12-15 | 2023-12-15 | 345 | 0 | 0 | 0 |  | Milam |  | Tier 4 |  |  |  |  | 3706, 3705, 39950 | Y |  |  | 0 | 76386 | 76385
45670 | East Stiles - Rocky Road 138 kV Line | Upgrade the existing 138 kV line |  | East Stiles | Rocky Road | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8597 | 2023-12-15 | 2023-09-15 | 138 | 0 | 7.1 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  |  | 23864, 23869 | Y |  |  | 0 | 71129 | 45670
66186 | Carrollton Northwest - Carrollton East 138 kV Line | Terminate the existing Northlake - Carrollton East 138 kV Line at Carrollton Northwest |  | Carrollton East |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4205 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2362, 2363, 2385, 2578 | Y |  |  | 0 | 66187 | 66186
68761 | Blue Acres - South Midland 138 kV Line | Upgrade the existing 138 kV Line |  | Blue Acres | South Midland | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8617 | 2023-12-15 | 2023-08-31 | 138 | 0 | 5.5 | 0 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 23857, 23860 | Y |  |  | 0 | 68764 | 68761
71997 | Collin Autotransformer #2 tertiary reactors | Install new reactors on Collin Autotransformer #2 |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4014 | 2023-12-15 |  | 345 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  |  | 29578 | Y |  |  | 0 | 71998 | 71997
64382 | Bowman Auto 1 Upgrade | Upgrade existing Bowman Auto #1 300 MVA to 600 MVA. |  | Bowman | Bowman | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4021 | 2023-12-15 |  | 345 | 0 | 0 | 600 |  | Archer | Archer | Tier 3 | 22RPG008 | 2022-03-15 | 2022-04-15 |  | 1422, 1423, 29048 | Y | N |  | 0 | 64383 | 64382
66006 | Sherry 138 KV Switch Terminal Equipment | Upgrade terminal equipment a Sherry 138 kV Switch |  | Sherry |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5101 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 1919, 2257 | Y |  |  | 0 | 66007 | 66006
68793 | Expanse 345/138 kV Switch | Construct a new 345/138 kV switch |  | Brown | Grady | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8593 | 2023-12-15 | 2023-12-15 | 345 | 0 | 0 | 1200 |  | Martin | Martin | Tier 3 | 22RPG007 | 2022-03-06 | 2022-04-04 |  | 11366, 11367, 11368, 11369, 11370, 11338, 23842 | Y |  |  | 0 | 74017 | 68793
71164 | Haggerty-Bells 138 kV Line Section | Rebuild portion of Haggerty-Bells 138 kV Line Section |  | Haggerty | Bells | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4336 | 2023-12-16 |  | 138 | 0 | 0 | 0 |  | Grayson | Grayson | Tier 4 |  |  |  |  | 1753, 1699, 12677 | Y |  |  | 0 | 71165 | 71164
62041 | Twinwood 138kV Distribution Substation | Remove Twinwood Mobile (TWM) substation and install new Twinwood (TWN) 138kV Distribution Substation. Loop from existing Ckt.25E to create new Ckt.25E Foster to Twinwood to Peters |  | Twinwood | Foster/ Peters | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-30 |  | 138 | 0.08 | 0 | 0 |  | Fort Bend | Austin | Tier 4 |  |  |  |  | 44860, 44861, 44230, 44256, 46220 | Y | N |  | 0 | 62042 | 62041
57412 | GENRAL Substation Removal | Remove 69kV GENRAL substation from CNP service |  | GENRAL | Garden Villas | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 |  | 69 | 0 | 9.91 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47670, 42690, 47540 | Y | N |  | 0 | 61869 | 57412
66050 | 138 kV Fulshear Distribution Substation | Install Fulshear Distribution Substation to create Ckt.25 FOSTER to Fulshear to Twinwood. |  | Fulshear | FOSTER/Twinwood | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44750, 44230, 44256, 44860, 46220 | Y | N |  | 0 | 81349 | 66050
70194 | LCRATSC_Hallettsville_Mont_TL_Overhaul | LCRA TSC will perform an overhaul on the 2.3-mile Hallettsville ¿ Mont (T593) 138-kV transmission line. |  | Hallettsville | Mont | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-12-31 |  | 138 | 0 | 2.3 | 0 |  | Lavaca | Lavaca | Tier 4 |  |  |  |  | 7246, 7249 | Y | Y |  | 0 | 78306 | 70194
70596 | LCRATSC_CraneEast_CB_Sub_Upgrade | Install circuit breakers in a ring bus configuration at Crane East Substation. Install two (2) 31.2 MVAR 138-kV capacitor banks at Crane East Substation. All substation equipment at Crane East Substation connected in series with the existing 138-kV transmission lines shall support a minimum rating of 3000 A at 105 degree F ambient temperature. |  | Crane EAst |  | Planned |  | LCRATSC | Dylan Preas dylan.preas.@lcra.org 512-578-4514 |  | 2023-12-31 |  | 138 | 0 | 0 | 0 | 0,62.4 | Upton | Upton | Tier 4 |  |  |  |  | 71214 | Y | N |  | 0 | 70597 | 70596
75564 | Brightright Switch (Hopkins Solar) |  |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R990 | 2024-01-01 | 2023-05-15 | 345 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 11684, 11688, 11689, 120825 | Y |  |  | 0 | 75565 | 75564
76620 | This is a duplicate project. Correct project is MOD78457 | This is a duplicate project. Correct project is MOD78457 |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  | 0 | 76621 | 76620
52260 | India to DWU Rebuild | India to DWU Rebuild |  | India | Dallas Water Utilities | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-01-01 |  | 69 | 0 | 0 | 0 |  | Ellis | Dallas | Tier 4 |  |  |  |  | 230, 2351 | Y |  |  | 0 | 52261 | 52260
57521B | Stone Lake New Sub Ckt66 | Upgrade Ckt.66 Hockley to Stone Lake BP2023 as a transmission project. |  | Stone Lake | Hockley/Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-05 |  | 138 | 0 | 15.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45880, 45886 | Y | N |  | Cost included in main entry | 80168 | 57521
61516 | Blissard - East Stiles 138 kV Line Section | Rebuild the Blissard - East Stiles 138 kV Line Section |  | Blissard | East Stiles | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8565 | 2024-01-05 | 2023-06-29 | 138 | 0 | 13.1 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  |  | 11353, 23869 | Y |  |  | 0 | 61518 | 61516
72649A | Add_Celina_Load |  |  |  |  | Planned |  | RYBRN |  |  | 2024-01-05 |  | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 6790, 6793, 6825, 2350 | Y |  |  | 0 | 78608 | 72649
59088 | Alice - Falfurrias: Line Rebuild | Alice - Falfurrias: Line Rebuild |  | Alice | Falfurrias | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2020088 | 2024-01-05 |  | 69 | 0 | 3.67 | 0 |  | Jim Wells | Brooks | Tier 2 |  |  |  |  | 8500, 8508, 8878, 8894 | Y |  |  | 0 | 65586 | 59088
76914 | Ocelot: Build new 138 kV station | BPUB interconnection at Ocelot on Military Highway to Palo Alto |  | Military Highway | Palo Alto | Conceptual | TP2023032 | AEP TCC | Michael Forcum mlforcum@aep.com 918-282-8376 |  | 2024-01-05 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8047, 8275, 8950 | Y |  |  | 0 | 76915 | 76914
71000 | TCC& TNC Cap Bank Rehab | TCC& TNC Cap Bank Rehab |  |  |  | Planned |  | AEP TCC&TNC | Glen Reed gareed@aep.com 918-599-2664 | TA2022031 | 2024-01-05 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6216, 6338, 6468, 6615, 8169, 8348, 8427 | Y | N |  | 0 | 71001 | 71000
76141 | Santo Nino: Install cap bank | Install cap banks at Santo Nino, Molina, and Wormser Road |  | Santo Nino |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2024-01-05 |  | 138 | 0 | 0 | 0 | 0,23.1 | Webb |  | Tier 4 |  |  |  |  | 8653 | Y |  |  | 0 | 76142 | 76141
52322 | Establish Courtney Creek Switch | Establish Courtney Creek 138/69 kV Switch |  | Courtney Creek Switch | Athey (AEP) | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8479 | 2024-01-05 | 2023-05-23 | 138 | 0 | 0 | 82 |  | Pecos | Pecos | Tier 4 | [5 empty] | Y |  |  | 0 | 80768 | 52322
61519 | Salt Flat Road - Skywest 138 kV Line Rebuild | Salt Flat Road - Skywest 138 kV Line Rebuild |  | Salt Flat Road | Skywest | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8569 | 2024-01-05 | 2023-12-15 | 138 | 0 | 1 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23859, 71210 | Y |  |  | 0 | 61521 | 61519
5621 | South McAllen-Bentsen and North Edinburg-West Edinburg 138 kV Station Upgrades | 138 kV Upgrades at North Edinburg and South McAllen |  | North Edinburg | North McAllen | Planned | 795 - 0980 | AEP TCC | Todd Siegert bcogan@aep.com 918-599-2857 | 3585 | 2024-01-05 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8367, 8371, 8631, 79603 | Y | N |  |  | 13351 | 5621
72085 | [7 empty] | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2024-01-05 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8668, 89500, 8111, 8127 | Y |  |  | 0 | 72086 | 72085
76916 | Snapdragon: Build new 138 kV station | Desert Vine Solar interconnection to Snapdragon on Zapata to Revilla line |  | Revilla | Zapata | Conceptual |  | AEP TCC/ETT | Michael Forcum mlforcum@aep.com 918-282-8376 | TP2023012 | 2024-01-05 |  | 138 | 0 | 0 | 0 |  | Starr | Zapata | Tier 4 |  |  |  |  | 8736, 8299, 8957 | Y | Y |  | 0 | 76917 | 76916
63964 | Bronco: Build new 69 kV Terminal | Interconnect House Mountain BESS to the Bronco 69 kV Station |  | Bronco |  | Planned | 1140 - 1318 | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 | 1885 | 2024-01-05 |  | 69 | 0 | 0 | 0 |  | Brewster |  | Tier 4 | [5 empty] | Y | N |  | 0 | 63965 | 63964
62728 | Wink - Shifting Sands 69 kV Line Conversion to 138 kV | Convert the existing Wink - Shifting Sands 69 kV Line to 138 kV |  | Wink | Shifting Sands | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8581 | 2024-01-05 | 2023-12-15 | 69 | 0 | 13 | 0 |  | Winkler | Winkler | Tier 4 | [5 empty] | Y |  |  | 0 | 80770 | 62728
52688 | Angleton Substation Expansion | Expand Angleton substation for the Myrtle Solar generator interconnection (19INR0041). |  | Angleton |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-05 | 2022-12-08 | 138 | 0.07 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110 | Y | N |  | 0 | 55842 | 52688
45689 | Pronghorn - Salt Flat Road 138 kV Line | Upgrade the existing 138 kV line |  | Pronghorn | Salt Flat Road | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8642 | 2024-01-05 | 2023-12-30 | 138 | 0 | 7.2 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23856, 23859 | Y |  |  | 0 | 71135 | 45689
50872 | Structure 25/7 - Medio Creek: Rebuild 138 kV Line | Rehab Structure 25/7 to Medio Creek 138 kV Line |  | Haisley | Medio Creek | Under Construction |  | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 | TA2018060 | 2024-01-05 |  | 138 | 0 | 14.9 | 0 |  | San Patricio | Refugio | Tier 3 | 19RPG014 | 2019-08-13 | 2019-10-07 |  | 8912, 8920 | Y | N |  | 0 | 65546 | 50872
64589 | Jeanetta Auto A3 Upgrade | Upgrade Jeanetta Auto A3 to increase thermal limits |  | Jeanetta |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-05 | 2023-01-12 | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47300, 47310, 49082 | Y | N |  | 0 | 64590 | 64589
59552 | Rebuild Eskota - Sweetwater No.2 69 kV Line | Rebuild Eskota - Sweetwater No.2 69 kV Line |  | Eskota | Sweetwater No. 2 | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8570 | 2024-01-05 | 2023-05-30 | 69 | 0 | 16.3 | 0 |  | Nolan | Nolan | Tier 4 |  |  |  |  | 1382, 1386, 1387, 1340, 1381, 1383, 1384, 1385, 11384 | Y |  |  | 0 | 76429 | 59552
72309 | AEP_TCC_LonHillHaisley | Lon Hill to Structure 25/4: Rebuild 138 kV Line |  | Lon Hill | Haisley | Planned |  | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 |  | 2024-01-05 |  | 138 | 0 | 10.2 | 0 |  | San Patricio | San Patricio | Tier 3 |  |  |  |  | 8027, 8046, 8912, 8920 | Y |  |  | 0 | 72310 | 72309
57521C | Stone Lake New Sub Ckt66 | Add Cap Bank #1 at Stone Lake Substation |  | Stone Lake |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-05 00:01 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  |  | 44840 | Y | N |  | Cost included in main entry | 80169 | 57521
57521D | Stone Lake New Sub Ckt66 | Add Cap Bank #1 at Stone Lake Substation |  | Stone Lake |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-05 00:02 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  |  | 44840 | Y | N |  | Cost included in main entry | 80170 | 57521
44854 | Lipton: Build 138 kV Box Bay | New Lipton 138 kV Station, replaces Lipton Hard Tap |  | Lipton |  | Under Construction |  | AEP TCC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | TP2018214 | 2024-01-14 |  | 138 | 0 | 0 | 0 |  | Zavala |  | Tier 4 |  |  |  |  | 8285, 88285, 8236, 8283 | Y | N |  | 0 | 44855 | 44854
71193 | Blue Acres - Yosemite 138 kV Line | Upgrade the existing 138 kV line |  | Blue Acres | Yosemite | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8638 | 2024-01-15 |  | 138 | 0 | 5.9 | 0 |  | Midland | Midland | Tier 4 | [5 empty] | Y |  |  | 0 | 80828 | 71193
71995 | Weatherford West 138 kV Switch Terminal Equipment | Upgrade terminal equipment at Weatherford West 138 kV Switch |  | Weatherford |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5519 | 2024-01-15 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 512, 1589 | Y |  |  | 0 | 71996 | 71995
62327 | Upgrade Fairfield West - Big Brown Tap 138 kV Line | Upgrade Fairfield West - Big Brown Tap 138 kV Line |  | Fairfield West | Big Brown Tap Switch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6138 | 2024-01-15 | 2023-12-15 | 138 | 0 | 8 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 196, 3508, 3510 | Y |  |  | 0 | 62328 | 62327
66178 | Centerville Switch - Centerville Road - Lake Hubbard Switch 138 kV Double-Circuit Line | Upgrade the existing 138 kV DCKT Line |  | Lake Hubbard | Centerville | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4127 | 2024-01-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2439, 2450, 2917, 2918, 2401, 2402 | Y |  |  | 0 | 66179 | 66178
64774 |  | Loop new 138kV Donop substation into existing 138kV Southton to Braunig transmission line. |  |  |  | Planned | T-0311 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0963 | 2024-01-25 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5128, 5030, 5394 | Y |  |  | 0 | 64775 | 64774
57912 | Champlin to Weil Tract: Rebuild 138 kV Line | Rebuild Champlin to Weil Tract 138 kV Line | Schedule Update | Champlin | Weil Tract | Planned | 1111 - 1289 | ETT TCC | Thomas Naves mlforcum@aep.com 918-599-2674 | 3830 | 2024-01-30 |  | 138 | 0 | 1.37 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8476, 8482 | Y | N |  | 0 | 65581 | 57912
48587 | Tesoro 345/138 kV Switch | Construct a new 345/138 kV switch (formerly known as Quail East) |  | Consavvy | Quail/Midessa South | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8634 | 2024-01-30 | 2024-02-05 | 345 | 0 | 0 | 1200 |  | Midland | Midland | Tier 3 | 22RPG032 | 2022-10-11 | 2022-11-07 |  |  | Y |  |  | 0 | 80829 | 48587
66128 | Clarkwood: Build new 138 kV terminal | Interconnect BRP Carina BESS to the Clarkwood 138 kV station | Schedule Update | BRP Carina | Clarkwood | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2021308 | 2024-01-30 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 88479, 8479 | Y |  |  | 0 | 66129 | 66128
50882 | Lon Hill to Structure 25/4: Rebuild 138 kV Line | Rehab Lon Hill to Structure 25/4 138 kV Line | Schedule Update | Lon Hill | Haisley | Planned | 1055 - 1228 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3785 | 2024-01-30 |  | 138 | 0 | 10.2 | 0 |  | San Patricio | San Patricio | Tier 3 | 19RPG014 | 2019-08-13 | 2019-10-07 |  | 8027, 8920, 8452, 8924 | Y | N |  | 0 | 65548 | 50882
65725 | James Rowe: Construct New Distribution Station | Construct New Distribution Station on the North McAllen to West McAllen 138 kV Line | Schedule Update | James Rowe |  | Planned | 1030 - 1208 | AEP TCC | Alison Scribailo mlforcum@aep.com 918-599-2674 | 3769 | 2024-01-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8041, 8367, 8631 | Y | N |  | 0 | 65726 | 65725
67913 | Pomelo: Build new 345 kV terminal | Interconnect Anemoi Storage to the Pomelo 345 kV station | Schedule Update | Hidalgo | Hidalgo | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2024-01-30 |  | 345 | 0.05 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 | [5 empty] | Y |  |  | 0 | 67914 | 67913
50954 | Whitepoint: Add Second Auto | Whitepoint: Add Second Auto | Schedule Update | Whitepoint |  | Planned | 1085 - 1258 | AEP TCC | Dave Goetz mlforcum@aep.com 918-599-2674 | 3805 | 2024-01-30 |  | 345 | 0 | 0 | 500 |  | San Patricio |  | Tier 4 |  |  |  |  | 8956, 8961 | Y | N |  | 0 | 50955 | 50954
50160 | Beeville to Goliad: Rebuild 69 kV Line | Rehab 69 kV Line from Beeville to Goliad | Schedule Update | Beeville | Goliad | Planned | 961 - 1139 | AEP TCC | Eric Scott bcogan@aep.com 918-599-2857 | 3719 TA2018010 | 2024-01-30 |  | 69 | 0 | 22.21 | 0 |  | Bee | Goliad | Tier 3 | 19RPG008 | 2019-04-30 | 2019-05-30 |  | 8584, 8586, 8587 | Y | N |  | 0 | 65542 | 50160
4495 | Champlin: Station Reconfigure | Expand existing breaker configuration to a four (4) breaker ring bus expandable to a six (6) breaker ring bus configuration. | Schedule Update | Champlin |  | Planned | 694 - 0864 | AEP TCC | John Pulay mlforcum@aep.com 918-599-2674 | 3541 TP2014064 | 2024-01-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8711, 8476, 8479, 8528 | Y | N |  | 0 | 78259 | 4495
61398 | Whitepoint 138 kV Station: Upgrade Pelican Terminal | Whitepoint 138 kV Station: Upgrade Pelican Terminal | Schedule Update | Whitepoint |  | Planned |  | AEP TCC | Brandon Cogan mlforcum@aep.com 918-599-2674 | TP2020040 | 2024-01-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 | 19RPG0016 |  |  |  | 8961, 80259 | Y |  |  | 0 | 61399 | 61398
64089 | Peregrine Solar Interconnection | Connect the Peregrine Solar to the Coleto Creek to Grissom 345 kV line | Schedule Update | Coleto Creek | Grissom | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2024-01-30 |  | 345 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8673, 88673, 8164, 8624 | Y |  |  | 0 | 64090 | 64089
69226 | Rebuild 69 kV Line from Point Comfort to Carancahua | Rebuild 69 kV Line from Point Comfort to Carancahua |  | Point Comfort | Carancahua | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2024-01-30 |  | 69 | 0 | 0 | 0 |  | Calhoun | Jackson | Tier 4 |  |  |  |  | 8131, 8132, 8555 | Y |  |  | 0 | 69227 | 69226
66292 | Salvare: Build 345 kV station | Interconnect Iris Energy on the Jim Treece to Tesla 345 kV line | Schedule Update | Salvare |  | Under Construction |  | ETT TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2024-01-30 |  | 345 | 0.01 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60510, 60511, 60504, 61001 | Y | N |  | 0 | 66293 | 66292
66192 | Abilene NW: Build 138 kV terminal | Interconnect Lancium to the Abilene NW 138 kV station | Schedule Update | Abilene Northwest | Lancium | Under Construction |  | AEP TNC | Brian Oyster twang1@aep.com 918-599-2635 |  | 2024-01-30 |  | 138 | 0.2 | 0 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6476, 6228 | Y | N |  | 0 | 66193 | 66192
69481 | Resaca: Install Cap Bank | Resaca Capacitor | Schedule Update | Resaca |  | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2024-01-30 |  | 69 | 0 | 0 | 0 | 0,11.5 | Cameron |  | Tier 4 |  |  |  |  | 8626 | Y |  |  | 0 | 69482 | 69481
64941A | PETSON to MONSAN Ckt.04D Upgrade | Upgrade Ckt 04D PETSON to MONSAN to increase thermal limits. Upgrade MONSAN equipment to 4000A. |  | PETSON | MONSAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-30 12:00 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43070, 42940 | Y | N |  | 0 | 75897 | 64941
67217B | Addicks to Campbell Ckts 09 & 21 Upgrades | Upgrade Ckt.21H Addicks to Campbell tap to increase thermal limits |  | Addicks | Campbell | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 3.53 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45610, 48349, 46610, 48057 | Y | N |  | Cost included in Phase A | 67219 | 67217
67217A | Addicks to Campbell Ckts 09 & 21 Upgrades | Upgrade Ckt.09I Addicks to Campbell tap to increase thermal limits |  | Addicks | Campbell | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 3.53 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45610, 48056 | Y | N |  | 0 | 67218 | 67217
66074 | Double ckt Soaptree-Holiday-AlamoSt |  |  | Soaptree (bus # 38450) | Alamo Street (bus # 38330) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-01-31 |  | 138 | 0 | 31.9 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38331, 38450, 38455 | Y |  |  | 0 | 66075 | 66074
71196 | Grey Well Draw - Pecan Grove 138 kV Line | Rebuild existing 138 kV line |  | Grey Well Draw | Pecan Grove | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8640 | 2024-01-31 | 2024-02-05 | 138 | 0 | 7.8 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23860, 23861 | Y |  |  | 0 | 71198 | 71196
72034 | Blodgett to TECO Ckt.37C Upgrades | Rebuild/Reconductor Ckt.37C Blodgett to TECO as a Hardening upgrade |  | Blodgett | TECO | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 3.02 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47520, 47430 | Y | N |  | 0 | 72035 | 72034
70665B | Danek (DNK) CEHE Substation for Remy Jade - 23INR0339 | Upgrade Ckt.03G BIGVUE to Lyondell tap to increase thermal limits |  | BIGVUE | Lyondell | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40190, 41023 | Y | N |  | 0 | 75839 | 70665
69221 | Rebuild 69 kV Line from Blessings to Palacios | Rebuild 69 kV Line from Blessings to Palacios |  | Blessing | Palacios | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2024-01-31 |  | 69 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8119, 8131 | Y |  |  | 0 | 69222 | 69221
69224 | Brookhollow to Port Lavaca: Rebuild 138 kV Line | Rebuild 138 kV Line from Brookhollow to Port Lavaca |  | Brookhollow | Port Lavaca | Planned |  | AEP | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2024-01-31 |  | 138 | 0 | 2.7 | 0 |  | Calhoun | Calhoun | Tier 1 | 21RPG002 | 2021-02-01 | 2021-10-27 |  | 8133, 8135 | Y |  |  | 0 | 71834 | 69224
77146 | Reconducter WNK-AAT-MDT-FSH |  |  | Wink (37900) | Fishhook (38180) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-01-31 |  | 138 | 0 | 13.18 | 0 |  | Winkler | Ward | Tier 4 |  |  |  |  | 37900, 38135, 38140, 38180 | Y |  |  | 0 | 77147 | 77146
73452 | TNMP_WINK_FISHHOOK_RECONDUCTOR_AC_4-5-2023 |  |  | bus 37900 wink to bus 38180 fishhook |  |  |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-01-31 |  | 138 | 13.5 | 0 |  |  | Pecos | Pecos | Tier 4 |  |  |  |  | 37900, 38180 | Y |  |  | 0 | 73453 | 73452
67270E | BP23 Reliability Upgrades | Upgrade Ckt.27A DOW to Jones Creek to increase thermal limits |  | DOW | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 42530 | Y | N |  | 0 | 67275 | 67270
67270A | BP23 Reliability Upgrades | Upgrade Ckt.21J Airline to White Oak to increase thermal limits |  | Airline | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 3 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45630, 46610 | Y | N |  | 0 | 67271 | 67270
67933 | Springwood & Rayford Substation Upgrades | Install 3rd distribution transformer at Rayford substation. Install in-series breakers at Springwood to increase reliability on the Ckt.22B Rothwood to Rothwood loop. |  | Rothwood | Springwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46270, 46273, 48273, 46260, 46295 | Y | N |  | 0 | 80833 | 67933
63495 | Cedar Canyon to Noelke 2nd circuit | Add the 2nd circuit to CREZ Cedar Canyon to Noelke 345 kV line |  | Cedar Canyon | Noelke | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-01-31 |  | 345 | 16 | 0 | 0 |  | Crockett | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76015, 7053 | Y | N |  |  | 63496 | 63495
66532 | Grey Well Draw - Pronghorn 138 kV Line Rebuild | Add Grey Well Draw - Pronghorn 138 kV Line Rebuild |  | Grey Well Draw | Pronghorn | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8606 | 2024-01-31 | 2024-02-05 | 138 | 9.9 | 0 | 0 |  | Midland | Midland | Tier 4 | [5 empty] | Y |  |  | 0 | 80769 | 66532
64493 | Bellaire to WAP Ckt.50A Upgrade | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits |  | Bellaire | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 47000, 44005 | Y | N |  | 0 | 64494 | 64493
67422A | Greens Bayou to Clinton 138kV Conversion | Rebuild-Reconductor Ckt.61A Greens Bayou to Wallisville (TEXWAL LOCATION) to Prepare for 138kV Conversion |  | Greens Bayou | Wallisville | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 69 | 0 | 6.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40720, 41681 | Y | N |  | 0 | 72769 | 67422
72049 | Crabb River Road to Imperial Ckt.80B Upgrades | Reconductor portions of Ckt.80B Crabb River Road to Imperial as a Hardening upgrade |  | Crabb River | Imperial | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 5.04 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44341, 48167 | Y | N |  | 0 | 81350 | 72049
69908 | Install 138kV Capacitor Bank at FM524 |  |  | TNMP FM524 Substation (bus # 39703) |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-01-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39703 | Y |  |  | 0 | 69909 | 69908
67270B | BP23 Reliability Upgrades | Upgrade Ckt.37A Bellaire to Kirby to increase thermal limits |  | Bellaire | Kirby | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47015, 47320 | Y | N |  | 0 | 67272 | 67270
67270D | BP23 Reliability Upgrades | Upgrade Ckt.08B Knight tap to Stadium to Fannin to increase thermal limits |  | Knight | Fannin | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47090, 48198, 47420 | Y | N |  | 0 | 67274 | 67270
69888B | Deepwater to Clinton Ckts.33B-33C Line Upgrades | Rebuild-Reconductor portions of Ckt.33C Clinton to Harrisburg ahead of future 138kV conversions. |  | Clinton | Harrisburg | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 69 | 0 | 4.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40352, 40800 | Y | N |  | Cost included in other phase. | 70972 | 69888
70623C | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04 Danbury to Liverpool to Snug to increase thermal limits |  | Liverpool | Danbury/Snug | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 00:02 |  | 138 | 0 |  | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42870, 42875, 44890 | Y | N |  | 0 | 70626 | 70623
66221E | Galena Park Area Conversion Project | De-energize Ckt.20C Galena Park to Greens Bayou |  | Galena Park | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 00:04 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40725 | Y | N |  | Cost included in main entry | 80617 | 66221
66221J | Galena Park Area Conversion Project | Expand Clinton 138kV Facilities and Install 200MVA Autotransformer. Loop existing 138kV Clinton circuits into expanded 138kV Clinton substation. Install as Clinton Auto A1. |  | Clinton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 00:08 |  | 138 | 0 | 0 | 200 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 49004, 40350, 40235, 40352 | Y | N |  | Cost included in main entry | 80618 | 66221
64941B | PETSON to MONSAN Ckt.04D Upgrade | Upgrade Ckt 04D PETSON to MONSAN to increase thermal limits. Upgrade PETSON equipment to 4000A. |  | PETSON | MONSAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 12:00 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43070, 42940 | Y | N |  | 0 | 75898 | 64941
5206 | Brackettville to Escondido: Construct 138 kV line | Build a single circuit capable 138 kV circuit from Brackettville to Escondido station |  | Brackettville | Escondido | Planned | 762-0947 | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | 3570 TP2017041 | 2024-02-01 |  | 138 | 45 | 0 | 0 |  | Kinney | Maverick | Tier 2 | 16RPG001 | 2016-01-05 | 2017-01-20 | 2017-02-08 | 8252, 8260 | Y | N |  |  | 12865 | 5206
6931 | New Tres Lagos Substation | Adds new station and short line from W Edinburg-Alton line |  | West Edinburg | Alton | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-02-01 |  | 138 | 1.8 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5770, 5771, 5772 | Y | N |  |  | 14750 | 6931
68974 | Second circuit from San Miguel to Fowlerton 345 kV | String the second circuit on existing towers from San Miguel to Fowlerton |  | San Miguel | Fowlerton | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-02-08 |  | 345 | 36.4 | 0 | 0 |  | Atascosa | McMullen | Tier 1 |  |  |  |  | 5901, 5709 | Y | N |  | 0 | 68975 | 68974
75514 | Rising Star Area Conversions | This project converts the voltage from Holder (292) to Nimrod (289) to 138 KV |  | Holder (292) | Nimrod (289) | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-02-12 |  | 138 | 0 | 28.5 | 0 |  | Brown | Comanche | Tier 4 |  |  |  |  | 289, 285, 292 | Y |  |  | 0 | 75515 | 75514
66124 | Prarie Swiitch Wind Interconnect | Connect Crawfish to El Campo to Lane City 138 kV Line | IN-SERVICE | EL CAMPO | LANE CITY PUMP | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2021286 | 2024-02-14 | 2024-02-14 | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8679, 8102, 8104 | Y |  |  | 0 | 66125 | 66124
64310 | Cumby-Cumby Tap Line Conversion | Cumby - Cumby Tap Radial Line 69 to 138 kV Conversion. Project requires coordination with RCEC and TNMP. |  | Cumby Tap | Cumby Substation | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R944 | 2024-02-16 |  | 138 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1812, 1813, 1815, 6861 | Y | N |  | 0 | 66059 | 64310
52147 | Rising Star Area Conversions | Converts voltage to 138 KV from Holder to Nimrod to Rising Star. |  | Holder |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-02-22 |  | 138 | 0 | 0 | 0 |  | Brown | Comanche | Tier 4 |  |  |  |  | 293, 292, 289 | Y |  |  | 0 | 52148 | 52147
6253 | AEN_New_Kramer_Lane_Substation |  |  | 9238 | 9276 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-02-26 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9276, 9077, 9238 | Y |  |  |  | 13981 | 6253
72055 | Fort Bend 138kV Substation Expansion for Brazos Bend BESS (23INR0363) | Expand Fort Bend 138kV substation for Brazos Bend BESS generator interconnection (23INR0363) |  | Fort Bend |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44280, 113302 | Y | N |  | 0 | 72056 | 72055
65003 | WA Parish to Nash Ckt.02B Upgrades | Upgrade Ckt.02B WA Parish to Nash to replace aging infrastructure and to address line clearance concerns |  | WA Parish | Nash | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 |  | 138 | 0 | 18.02 | 0 |  | Fort Bend | Brazoria | Tier 4 | 21RPG013 | 2021-08-08 | 2021-09-10 |  | 42980, 48364, 48365, 42410, 44010 | Y | N |  | 0 | 65004 | 65003
70665D | Danek (DNK) CEHE Substation for Remy Jade - 23INR0339 | Install generator lead from Danek (DNK) substation to JADE/Remy Jade. |  | Danek | JADE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  | 0 | 75841 | 70665
66221A | Galena Park Area Conversion Project | Remove Galena Park Auto A1. Remove Galena Park 69kV facilities. Remove Galena Park 138kV ring bus. Rebuild Galena Park substation for double-tap 138kV service. |  | Galena Park |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 |  | 69 | 0 | 0 | -200 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40610, 40752, 49015, 40612, 40630, 41172, 40611 | Y | N |  | 0 | 80619 | 66221
61228 | AEN_McNeil__JustinLane__ckt_811_reconductor | Reconductor 3.98 miles of circuit to 3000 Amps. |  | McNeil [9080] | Justin Lane [9225] | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-02-28 |  | 138 | 0 | 3.98 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9080, 9225 | Y |  |  | 0 | 61229 | 61228
66221B | Galena Park Area Conversion Project | De-energize Ckt.38A Galena Park to GYPSUM |  | Galena Park | GYPSUM | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:01 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40751, 40611, 40619, 40720 | Y | N |  | Cost included in main entry | 80620 | 66221
66221C | Galena Park Area Conversion Project | De-energize Ckt.17A Galena Park to Greens Bayou |  | Galena Park | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:02 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 |  | Y | N |  | Cost included in main entry | 80621 | 66221
66221D | Galena Park Area Conversion Project | De-energize Ckt.38B Clinton to Greens Bayou |  | Clinton | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:03 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40352, 40720 | Y | N |  | Cost included in main entry | 80622 | 66221
66221F | Galena Park Area Conversion Project | Rebuild Galena Park substation for double tap service. Bypass Galena Park breakers with Ckt.94 and tap Galena Park to create new Ckt.94M CITFIL to Normandy tap to Galena Park tap to TANKER |  | CITFIL | TANKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:05 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40613, 48130, 40612, 40630, 40731, 48261 | Y | N |  | Cost included in main entry | 80623 | 66221
66221G | Galena Park Area Conversion Project | Rebuild Galena Park substation for double tap service. Tap Galena Park TR2 on Ckt.21K between Fidelity and Witter. |  | Fidelity | Witter | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:06 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40612, 40590, 40710, 48402 | Y | N |  | Cost included in main entry | 80624 | 66221
66221H | Galena Park Area Conversion Project | Join 69kV Greens Bayou buses 40720 & 40725 at a Minimum 40KAIC |  | Greens Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:07 |  | 69 | 0 | 0 | 0 |  | Harris |  | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40725, 40720, 41570, 41681 | Y | N |  | Cost included in main entry | 80625 | 66221
4010 | Rebuild Magnolia - Seminole 138 kV line. | *Project pushed back to 2023. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | STE07216 | 2024-03-01 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38950, 38990 | Y |  |  |  | 11530 | 4010
76920 | Kingsville to Bunsen: Construct Primavera Tap | Add Tesla Load |  | Bunsen | Kingsville | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023059 | 2024-03-01 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8749, 88747, 8518, 8921 | Y |  |  | 0 | 76921 | 76920
68804 | Loop Nine 345/138 kV Switch | Establish Loop Nine 345/138 kV Switch |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4327 | 2024-03-05 |  | 345 | 0 | 0 | 0 |  | Ellis | Dallas | Tier 3 | 22RPG014 | 2022-05-15 | 2022-06-15 |  |  | Y |  |  | 0 | 81620 | 68804
62712 | Driver - Skywest 138 kV Line Rebuild | Rebuild the existing Driver - Skywest 138 kV Line |  | Driver | Skywest | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8564 | 2024-03-15 |  | 138 | 0 | 11.9 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 23863, 71210 | Y |  |  | 0 | 62716 | 62712
75516 | Rising Star Area Conversions | This converts from NImrod (289) to Rising Star (285) to 138 KV service |  | Nimrod (289) | Rising Star (285) | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-03-20 |  | 138 | 0 | 0 | 0 |  | Eastland | Comanche | Tier 4 |  |  |  |  | 285, 281, 289 | Y |  |  | 0 | 75517 | 75516
70964 | WETT 345 kV Volta witch | Construct new 345 kV Volta Switch and two approximately 0.15-mile 345 kV lines between WETT-owned Volta 345 kV Switch and Oncor-owned Expanse |  | Howard | Martin | Planned |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2024-03-25 |  | 345 | 0.3 | 0 | 0 |  | Howard | Martin | Tier 3 | 22RPG007 | 2022-03-06 | 2022-04-04 |  | 59910, 11366, 11369, 59900, 59901 | Y |  |  | 0 | 80004 | 70964
81396 |  |  |  | RUCKER | RUCKER | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-03-26 |  | 69 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 287, 1663 | Y |  |  | 0 | 81397 | 81396
71190 | Einstein - St Lawrence 138 kV Line | Upgrade the existing 138 kV line |  | Einstein | St. Lawrence | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8646 | 2024-03-28 |  | 138 | 0 | 4.6 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 23852, 23854 | Y |  |  | 0 | 71192 | 71190
66011A | CNP ARCHER POI for BROTMAN Power | CNP ARCHER POI for BROTMAN Power |  | ARCHER | Rosharon/MANVEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-29 12:00 |  | 138 | 0.66 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44430, 44600, 44390, 44410, 48173, 112969 | Y | N |  | 0 | 72740 | 66011
68229 | Penumbra: Build new 345 kV Station | Interconnect Montgomery Ranch Wind to the Avogadro to Edith Clarke 345 kV line | Contact, Cost Update | Penumbra |  | Planned |  | AEP TNC | Zach Lachiusa twang1@aep.com 918-599-2635 |  | 2024-03-30 | 2023-11-15 | 345 | 0 | 0 | 0 |  | Foard |  | Tier 4 |  |  |  |  | 60059, 60500, 60506, 60722 | Y | N |  | 0 | 68230 | 68229
80462 | Lon Hill to Weil Tract 138 kV(LCRA): Construct Temp Tap | Construct Temp Tap on the Lon Hill to Weil Tract 138 kV line |  | Nueces | Nueces | Planned |  | AEP | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2024-03-30 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 78569 | Y |  |  | 0 | 80463 | 80462
66635 | Lamesa 69 kV Substation Conversion to 138 kV | Add Lamesa 69 kV Substation Conversion to 138 kV |  | Lamesa 69 kV | Lamesa 138 kV | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8595 | 2024-03-30 |  | 69 | 0 | 0 | 0 |  | Dawson | Dawson | Tier 4 | [5 empty] | Y |  |  | 0 | 80849 | 66635
66011B | CNP ARCHER POI for BROTMAN Power | Upgrade Ckt.26 Rosharon to ARCHER to increase thermal limits. |  | ARCHER | Rosharon/MANVEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-30 12:00 |  | 138 | 0 | 1.28 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44600 | Y | N |  | 0 | 72741 | 66011
70961B | Crosby Sub Exp for HOLY/Citadel BESS and Upgrades | Upgrade Ckt.66F Baytown to Baytown TR1 tap to increase thermal limits |  | Baytown | Baytown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40170, 44630 | Y | N |  | 0 | 70963 | 70961
5792B | Leonard Road Substation 138 | Rebuild 138kV Line From Atkins to Leonard in existing 69kV Right of Way. |  | Leonard | Atkins | Planned |  | BRYN |  |  | 2024-03-31 |  | 138 | 0 | 2 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32862, 32851 | Y | N |  | 0 | 72136 | 5792
78476 | Waterhole 345kV Substation - Gulf Star Storage - Generator Interconnection (23INR0460) | Install Gulf Star Storage at Waterhole 345kV substation… Connect at the same generator lead as Gulf Star Solar (Gulf Star Storage - 23INR0460) |  | Waterhole |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 78477 | 78476
69896 | Singleton Expansion for Limousin Oak Storage (22INR0338) | Expand Singleton 345kV substation and install one generator lead for new interconnection to Limousin Oak Storage |  | Singleton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 |  | 345 | 0 | 0 | 0 |  | Grimes |  | Tier 4 | [5 empty] | Y | N |  |  | 69897 | 69896
69894 | HO Clarke Substation Expansion for Callisto Energy Center (22INR0490 & 22INR0491) | Expand HO Clarke substation for Callisto Energy Center generator interconnection (22INR0490 & 22INR0491) |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47150, 113105 | Y | N |  |  | 69895 | 69894
70623A | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04B Hudson to MONSAN to increase thermal limits. Reconductor to 2-959ACSS. |  | Hudson | MONSAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 |  | 138 | 0 | 2 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42100, 42940 | Y | N |  | 0 | 70624 | 70623
70665A | Danek (DNK) CEHE Substation for Remy Jade - 23INR0339 | New 138kV Danek (DNK) substation for generator interconnection to Remy Jade. Loop Ckt.08G into substation to create new Ckt.08 Crosby to Danek to Highlands tap. |  | Danek | Crosby/Highlands | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40890, 40396, 48141, 113219 | Y | N |  | 0 | 75840 | 70665
72870 | LCRATSC Soda Lake CB Addition | This project provides a point of interconnection for a new 202.99 MW Solar Energy at the 138-kV Soda Lake Substation by reconfiguring the Soda Lake Substation to breaker-and-a-half to add new 138-kV line terminal and one POI structure to accommodate the new interconnection. Update contingencies |  | Soda Lake |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-03-31 |  | 138 | 0 | 0 | 0 |  | Crane |  | Tier 4 | [5 empty] | Y | N |  | 0 | 78298 | 72870
55464 | Adds new Morrow sub near Pearsall | Adds new Morrow substation and short line from Morrow to the Pearsall substation |  | Pearsall | Morrow | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-03-31 |  | 138 | 0.91 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5896, 5895 | Y | N |  | 0 | 55465 | 55464
56012 | PSARCO Fault Duty Upgrade with Bus Reactors | Install (3) 10-Ohm Reactors at PSARCO by splitting PSARCO bus as a fault duty upgrade |  | PSARCO |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 41300, 41303, 41305, 40190, 48230, 41301, 110560, 110579, 110571, 110572, 110573, 110574, 110577 | Y | N |  | 0 | 82078 | 56012
70623E | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04B Hudson to MONSAN to increase thermal limits. Upgrade MONSAN equipment. |  | Hudson | MONSAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42100, 42940 | Y | N |  | 0 | 75627 | 70623
67422H | Greens Bayou to Clinton 138kV Conversion | Rebuild-Reconductor Ckt.61A Greens Bayou (TEXWAL LOCATION) to Wallisville to Prepare for 138kV Conversion |  | Greens Bayou | Wallisville | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 00:01 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40720, 41682 | Y | N |  | 0 | 72771 | 67422
70623B | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04A Mustang Bayou to Hudson to increase thermal limits |  | Hudson | Mustang | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 00:01 |  | 138 | 0 |  | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42960, 48112, 42100 | Y | N |  | 0 | 70625 | 70623
70623D | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04 Snug to PETSON to increase thermal limits |  | Snug | PETSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 00:03 |  | 138 | 0 |  | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 44890, 43070 | Y | N |  | 0 | 70627 | 70623
66017A | Westpark Area Upgrades | Upgrade Ckt.05E Bellaire to Sharpstown tap and Dunvale tap to Jeanetta to increase thermal limits |  | Bellaire | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 12:00 |  | 138 | 0 | 3.6 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47015, 47072, 47310, 48088, 44760, 44762, 48343 | Y | N |  | 0 | 78248 | 66017
65704 | Crosby 35kV Distribution Substation | Expand Crosby substation with 35kV Distribution Facilities |  | Crosby | Highlands/Atascosita |  |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 12:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40390 | Y | N |  | 0 | 65705 | 65704
66017B | Westpark Area Upgrades | Upgrade Ckt.24B Dunvale tap to Westchase tap to increase thermal limits. |  | Dunvale | Westchase | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 12:01 |  | 138 | 0 | 2.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44762, 47014, 47072, 47442 | Y | N |  | 0 | 78249 | 66017
54220 | Brazos' member will build McFarland substation, Brazos will install POI Picard | Brazos' member will build McFarland substation, Brazos will install POI Picard |  | Picard | Picard | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-04-01 |  | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 486, 485, 527 | Y |  |  | 0 | 54221 | 54220
77046 | AEP_TCC_OdemSandPit | Add Odem Sand station |  | Edroy | Smith | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | DP22X0028 | 2024-04-01 |  | 69 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8734, 8408, 8866 | Y |  |  | 0 | 77047 | 77046
52169 | Rising Star Area Conversions | This converts the voltage to 138 following Rising Star Substation Voltage Conversion |  | Rising Star | Downing | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-04-10 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 281, 285, 294 | Y |  |  | 0 | 52170 | 52169
81726 | Mobile substation | Project is to add a mobile substation next to Airport Substation tapping into the Transmission line that is Filter Plant to Airport Substation. Then connecting lines South Plant to Southmost by passing Airport Substation. This is due to Airport Substation being decommissioned in April. |  | 59420 Filter Plant, 59500 South Plant | Mobile substation, 5789 Southmost | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2024-04-15 | 2024-04-15 | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5946, 59430, 59460, 5789, 59420, 59500 | Y |  |  | 0 | 81727 | 81726
57169 | Rebuild Redgate to N Edinburg 138 kV | Rebuild Redgate to N Edinburg 138kV and opens Redgate tap |  | Redgate | Faysville Switch | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-04-27 |  | 138 | 0 | 3.45 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8380, 88380, 5779, 5784 | Y | N |  | 0 | 63733 | 57169
54811 | Winecup: Build 69 kV station | Construct new 69 kV box bay on the North San Angelo to San Angelo Grape Creek Tap 69 kV line | Schedule Update | Winecup |  | Planned | 1041 - 1268 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | 1858 | 2024-04-29 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 60796, 6459, 6465 | Y | N |  | 0 | 54812 | 54811
70665C | Danek (DNK) CEHE Substation for Remy Jade - 23INR0339 | Upgrade Ckt.03A PSARCO to BIGVUE to increase thermal limits |  | PSARCO | BIGVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-04-30 |  | 138 | 0.83 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 41305, 40190 | Y | N |  | 0 | 75838 | 70665
70204 | LCRATSC_McCarty_Rattler_TL_Upgrade | LCRA plans to upgrade T725 McCarty Lane - Rattler 138-kV transmission line to obtain a higher operational rating. |  | McCarty Lane | Rattler | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-04-30 |  | 138 | 0 | 1.27 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 7184 | Y | N |  | 0 | 78307 | 70204
67604 | Stafford Reconfigurations Ckt.05D | Reconfigure Stafford loads served from Ckt.05D. Create Ckt.05D Westchase tap to Stafford loop to Stafford TR4 tap to Missouri City tap |  | Stafford | Missouri City | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-04-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44670, 44671, 44672, 44673, 44674, 44676, 48352, 48351, 48356, 44761 | Y | N |  | 0 | 80779 | 67604
72596A | PEC_MarshallFord_Paleface_StormHardening | Rebuild single circuit section of Paleface to Marshal Ford and reconductor with Single 959 ACSS Conductor, 380 MVA; (Replaces ERCOT Project # 61274A) | 1/10/2023: Changes to description based on final design. | Paleface | Marshall Ford | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-04-30 |  | 138 | 0 | 3.65 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70477, 77356 | Y | N |  | 0 | 72598 | 72596
63902 | Bakersfield: Build New 345 kV Terminal | Interconnect Hydra BESS to the Bakersfield 345 kV Station | In-Service Date Update | Bakersfield |  | Under Construction | 1136 - 1314 | ETT TNC | Rasa Ansari twang1@aep.com 918-599-2635 | 1881 | 2024-04-30 |  | 345 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 76002, 135602 | Y | N |  | 0 | 63903 | 63902
76151 | Gas Pad Tap: Replace CTVT | Replace CTVT combination unit at Gas Pad station along the Lote Bush to Yucca Drive 138 kV line |  | Gas Pad Tap |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2024-04-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 11245, 60397 | Y | N |  | 0 | 76152 | 76151
68780 | Triangle - Yosemite 138 kV Line | Upgrade the existing 138 kV Line |  | Triangle | Yosemite | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8626 | 2024-04-30 |  | 138 | 0 | 11.2 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 11390, 23839, 23843, 23858 | Y |  |  | 0 | 68782 | 68780
70961A | Crosby Sub Exp for HOLY/Citadel BESS and Upgrades | Expand Crosby substation for HOLY/Citadel BESS generator interconnection (24INR0147). Reposition Ckt.08H to a new breaker position. |  | Crosby |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-04-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  | 0 | 70962 | 70961
72596B | PEC_MarshallFord_Paleface_StormHardening | Reconductor triple circuit section in conjunction with LCRA TSC Storm Hardening project (ERCOT Project #62068) with Single Suwanee Conductor. (Replaces ERCOT Project # 61274B) | 1/10/2023: Changes to description based on final design. | Paleface | Marshall Ford | Planned |  | PEC/LCRATSC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-05-01 |  | 138 | 0 | 11.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70477, 77356 | Y | N |  | 0 | 72597 | 72596
68055 | Rio Colorado substation | Adds new Rio Colorado load serving station between Bay City and Tin Top |  | Rio Colorado |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-05-01 |  | 69 | 3.8 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5563, 5560, 5569 | Y | N |  | 0 | 68056 | 68055
72582A | Nameless to Leander Transmission Line Upgrade | Rebuild and upgrade Nameless to Hero Way with double-circuit capable structures and cut in Hero Way substation (ERCOT Project #72570). Install 1 ckt with bundled 795 kcmil conductor (440 MVA). Final span of conductor and terminal equipment at Nameless will be upgraded to 440 MVA with ERCOT project #72576B. (Replaces ERCOT Project # 61279A) | 1/10/2023: Identified related substation project and added information to clarify timing for final circuit rating upgrade. | Hero Way | Nameless | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-05-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70526, 70536 | Y | N |  | 0 | 72583 | 72582
71319 | Upgrade Pearsall Station | Upgrade Pearsall Station to breaker and a half |  | Pearsall | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-05-04 |  | 138 | 0 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5893, 5895 | Y |  |  | 0 | 71320 | 71319
52175 | Rising Star Area Conversions | This continues the Rising Star Area Conversions with Downing to Mountary | Carlton to Downing 138 kV Conversion | Carlton | Downing | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-05-10 |  | 138 | 0 | 0 | 0 |  | Erath | Comanche | Tier 4 |  |  |  |  | 294, 281, 297 | Y |  |  | 0 | 52176 | 52175
67992B | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade,CPSE_Medina_to_36th_Street_Upgrade | Upgrade Medina to 36th Street 138KV Line to 213MVA. This change will remove a clearance related limit and not change the conductor. |  | 5305 | 5427 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2024-05-14 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5305, 5427 | Y |  |  | 0 | 67995 | 67992
56350B | Burnett - Bowie 69 kV Line | Rebuild Burnett-Ringgold Magnolia Tap Line |  | Burnett | Ringgold Magnolia Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4015 | 2024-05-14 |  | 69 | 0 | 20.1 | 100 |  | Wichita | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 1452, 1491, 1544, 1543, 1545 | Y | N |  | 0 | 73039 | 56350
56350C | Burnett - Bowie 69 kV Line | Establish Old lake switch and convert Fisher Road - Old Lake Switch (FKA Burnett-Ringgold Magnolia Tap) Line from 69 kV to 138 kV |  | Burnett | Ringgold Magnolia Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4015 | 2024-05-14 |  | 138 | 0 |  | 100 |  | Wichita | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 1452, 1543, 1544, 1545, 11540, 11541, 1426, 1491, 1524, 775, 33770 | Y | N |  | 0 | 73040 | 56350
5940B | Mountain Home Substation and Transmission Line Addition | Cut-in the existing Gillespie to Fredericksburg 138-kV transmission line (T379) at Peach substation (converted to 138-kV, located adjacent to Live Oak substation), re-terminate and convert the existing 69-kV Harper to Live Oak transmission line to form 138-kV Headwaters to Peach transmission line, and connect the existing 69-kV Gillespie to Live Oak (T131) and existing Live Oak to Goehman Tap (T287) transmission lines to create a continuous 69-kV circuit from Gillespie to Goehman Tap. |  | Headwater | Goehman Tap. | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017394 | 2024-05-15 |  | 138 | 0 | 22.5 | 0 |  | Kerr | Gillespie | Tier 1 | 16RPG015 | 2016-11-18 |  |  | 7412, 7130, 7410, 7413 | Y | N |  | 0 | 78336 | 5940
60094 | Convert Waco East - Elm Mott 69 kV Line to 138 kV | Convert Waco East - Elm Mott 69 kV Line to 138 kV and relocate the Waco East Substation to the double circuit line going towards Lake Creek/Waco West |  | Waco East | Elm Mott | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6147 | 2024-05-15 |  | 138 | 0 | 10 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3439, 3443, 3571, 3573, 3708, 13438, 3407, 3408, 3438 | Y |  |  | 0 | 62645 | 60094
61438 | Sim Gideon - Tahitian Village Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 5.1-mile Sim Gideon ¿ Tahitian Village (T648) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Sim Gideon | Tahitian Village | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7310, 7575 | Y | N |  | 0 | 61439 | 61438
51225 | Driver - Hadacol Corner 138 kV Line | Upgrade the existing 138 kV line |  | Driver Tap | Hadacol Corner | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8637 | 2024-05-15 |  | 138 | 0 | 3.2 | 0 |  | Midland | Reagan | Tier 4 |  |  |  |  | 23863, 23867 | Y |  |  | 0 | 71134 | 51225
61402 | Boerne-Esperanza Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the 1.7-mile T657 Boerne to Esperanza 138-kV and T656 Bergheim to Kendall 345-kV double-circuit transmission line between Boerne Split and Esperanza Substation and the 2.2-mile T657 Boerne to Esperanza 138-kV and T228 Boerne to Welfare double-circuit transmission line between Boerne Substation and Boerne Split by replacing the aging conductors. |  | Boerne | Esperanza | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 345 | 0 | 3.9 | 0 |  | Kendall | Kendall | Tier 4 | 22RPG005 | 2022-03-04 |  |  | 7153, 7168, 7770, 7046, 7710 | Y | N |  | 0 | 61403 | 61402
72876 | Provide 138 kV POD for Skybox at Teal Switch | Provide 138 kV POD for Skybox at Teal Switch |  | Teal | Skybox | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6259 | 2024-05-15 |  | 138 | 0.2 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3371, 3362 | Y |  |  | 0 | 72877 | 72876
73434 | Shaw 138 kV POD | Add Shaw 138 kV POD |  | Midkiff | Shaw POD | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8697 | 2024-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Reagan | Glasscock | Tier 4 |  |  |  |  | 18664, 11222 | Y |  |  | 0 | 73435 | 73434
76431 | Establish 345 kV Bale Switch | Establish 345 kV Bale Switch |  | 345kV St John Switch | 345kV Jewett Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6256 | 2024-05-15 |  | 345 | 0 | 0 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3711, 3384, 3390, 153733 | Y |  |  | 0 | 76432 | 76431
57908 | North Edinburg:138 kV Station Work | Install two 138 kV series reactors | Status Update | North Edinburg |  | Under Construction | 1112 - 1290 | AEP TCC | Curtis Brown mlforcum@aep.com 918-599-2674 | 3831 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 88381, 88382, 8380, 8383, 8341 | Y | N |  | 0 | 57909 | 57908
70225 | Junction: Install capacitor bank | Install Capacitor Bank at Junction Station | Estimated Cost Update | Junction |  | Planned |  | AEP TNC | Damian Raab twang1@aep.com 918-599-2635 |  | 2024-05-15 |  | 69 | 0 | 0 | 0 | 0,7.7 | Kimble |  | Tier 4 |  |  |  |  | 6400 | Y | N |  | 0 | 70226 | 70225
67377 | Upgrade Bowman Autotransfomer 2 | Upgrade existing Bowman Auto #2 300 MVA to 600 MVA. |  | Bowman | Bowman | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4026 | 2024-05-15 |  | 345 | 0 | 0 | 600 |  | Archer | Archer | Tier 3 | 22RPG008 | 2022-03-29 | 2022-04-15 |  | 1422, 1424, 29050 | Y | N |  | 0 | 67378 | 67377
76680 | Add Capacitor Bank at East Stiles | Add Capacitor Bank at East Stiles |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8693 | 2024-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 23869 | Y |  |  | 0 | 76681 | 76680
70190 | LCRATSC_Cuero_Substation_Upgrade | Increase the reliability of substation equipment at the Cuero Substation by converting the station bus layout from single bus single breaker to a breaker and a half configuration, replacing obsolete and/or aged equipment, upgrade facility structures as required, and installing a new control enclosure to adhere to high wind requirements. Contingency Update |  | Cuero | Cuero | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | DeWitt | DeWitt | Tier 4 | [5 empty] | Y | Y |  | 0 | 70191 | 70190
50710 | Quartz Sand 138 kV Switch | Construct a new 138 kV switch |  | Spraberry | Polecat Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8670 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 1328 | Y |  |  | 0 | 73335 | 50710
76676 | Roadrunner 138 kV Capacitors | Add Capacitor at Roadrunner. |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8677 | 2024-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 11199 | Y |  |  | 0 | 76679 | 76676
72572 | Highway 32 capacitor bank addition | Install 31.3 Mvar capacitor bank at Highway 32. Replaces Project ID 70363. |  | Highway 32 |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 | 0,31.2 | Hays |  | Tier 4 |  |  |  |  | 70546 | Y | Y |  | 0 | 72573 | 72572
71948 | LCRATSC_Copperas_Copperas_TL_Overhaul | LCRA TSC will perform an overhaul on the 2.4-mile portion of Copperas Cove Oncor – Copperas Cove PEC (T393) 138-kV transmission line between Copperas Cove PEC Substation and Oncor Tie existing structure #35/8. |  | Copperas (ONCOR) | Copperas (PEC) | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 3 | 0 |  | Coryell | Coryell | Tier 4 |  |  |  |  | 7061, 3630 | Y | N |  | 0 | 71949 | 71948
72878 | LCRATSC_Leesville_Substation_Addition | This project provides a point of interconnection for a new 95 MW Solar Farm and 33 MW Battery Energy Storage System via a new 138-kV Leesville Substation on T605 between Deer Creek and LCRA Nixon substations. |  | Leesville | Leesville | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7599, 7595, 7621 | Y | N |  | 0 | 72879 | 72878
71175 | Tall City - Pecan Grove 138 kV Line | Upgrade the existing 138 kV line |  | Tall City | Pecan Grove | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8635 | 2024-05-15 |  | 138 | 0 | 11.6 | 0 |  | Midland | Martin | Tier 4 |  |  |  |  | 23840, 23855, 23861 | Y |  |  | 0 | 71177 | 71175
71973 | Morgan Creek - Barber Lake Rebuild West Ckt | Rebuild the existing 138 kV line |  | Morgan Creek | Barber Lake | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8623 | 2024-05-15 |  | 138 | 0 | 4.75 | 0 |  | Mitchell | Mitchell | Tier 4 |  |  |  |  | 1032, 1190 | Y |  |  | 0 | 81360 | 71973
72863 | Delaware River 138 kV Switch | Establish Delaware River 138 kV Switch for merchant plant |  | Horseshoe Springs | Riverton | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8621 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Culberson | Reeves | Tier 4 |  |  |  |  | 11112, 11190, 11272 | Y |  |  | 0 | 72865 | 72863
76684 | Add Centralia 138 kV Capacitors | Add Centralia 138 kV Capacitors |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8700 | 2024-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 1209 | Y |  |  | 0 | 76685 | 76684
61457 | Nada - Ricebird Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 13.1-mile Nada ¿ Ricebird (T588) 138-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Nada | Ricebird | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Colorado | Wharton | Tier 4 |  |  |  |  | 78103, 78104 | Y | N |  | 0 | 61458 | 61457
61463 | Marshall Ford - McNeil Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 14.2-mile Marshall Ford ¿ McNeil (T197) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Marshall Ford | McNeil | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 | 22RPG018 |  | 2022-07-08 |  | 7356, 7542, 7334 | Y | N | 22RPG018 reclassified as Teir 4 neutral by REPG review on 1/08/2022 | 0 | 61464 | 61463
70200 | LCRATSC_ChiefBrady_RoundRock_TL_Upgrade | LCRA TSC will upgrade T378 Chief Brady - Round Rock 138-kV transmission line to achieve a higher operational rating. |  | Chief Brady | Round Rock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 5.1 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3668, 7366 | Y | N |  | 0 | 70201 | 70200
71940 | LCRATSC_Saxet_Substation_Addition | LCRA TSC will provide two transmission points of interconnection by installing taps on the LCRA TSC owned 138-kV transmission lines T522 Weil – Lon Hill and T437 Lon Hill – Nueces Bay to serve AEP customer load. |  | Saxet |  | Planned |  | LCRATSC/AEP TCC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 78568, 78569, 8441, 8452, 8482 | Y | Y |  | 0 | 72407 | 71940
68797 | Morgan Creek - Barber Lake East 138 kV Line | Upgrade the existing 138 kV Line |  | Morgan Creek | Barber Lake | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8624 | 2024-05-15 |  | 138 | 0 | 4.83 | 0 |  | Mitchell | Mitchell | Tier 4 |  |  |  |  | 1032, 11393 | Y |  |  | 0 | 81361 | 68797
70977 | Ozark Trail 345 kV Switch | Establish Ozark Trail 345 kV Switch to provide a POI for Hornet Solar |  | Ogallala | Tule Canyon | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8027 | 2024-05-15 |  | 345 | 0 | 0 | 0 |  | Castro | Swisher | Tier 4 |  |  |  |  | 23901, 23912, 23914 | Y |  |  | 0 | 70980 | 70977
73443 | Utilize Melton POI via Navarro 345 kV Switch for Project Lefty | Utilize Melton POI via Navarro 345 kV Switch for Project Lefty |  | Navarro | Navarro | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6338 | 2024-05-15 |  | 345 | 0.2 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3373, 68091 | Y |  |  | 0 | 73444 | 73443
61465 | Starcke - Wirtz Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 6.7-mile Starcke - Wirtz (T654) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Starcke | Wirtz | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Burnet | Burnet | Tier 4 |  |  |  |  | 7351, 7104 | Y | N |  | 0 | 61466 | 61465
70900A | Roanoke Area Upgrades | Establish Kingsridge 138 kV Switch |  | Kingsridge | Kingsridge | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5281 M5144 M5146 M5148 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 2033, 2034, 12043, 12044, 12045, 12046, 566, 1856, 2027, 2037, 2038, 12033, 12034, 2036, 12036 | Y | N |  | 0 | 72013 | 70900
71172 | Luther - Vealmoor 138 kV Line | Upgrade the existing 138 kV line |  | Luther | Vealmoor | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8636 | 2024-05-15 |  | 138 | 0 | 10 | 0 |  | Borden | Howard | Tier 4 |  |  |  |  | 23831, 23835 | Y |  |  | 0 | 71174 | 71172
45084A | Braunig to Highland Rebuild | Rebuild approximately six circuit miles of 138kV transmission from Braunig to Highland Hills/Brooks. This rebuild is between 'Highland Hills to Schillers Tap'. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0194, T-0238 | 2024-05-15 |  | 138 | 0 | 6 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5095, 5205 | Y |  |  | 0 | 45085 | 45084
78683A | POI for Connolly Storage (Denton Creek Switch) | Establish Connolly Storage POI |  | Bennett Road Switch | Krum Tap Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3500 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 1510, 1566, 1568 | Y |  |  | 0 | 79645 | 78683
69352 | Pebble Creek - Desoto 138 kV Line | Rebuild the Pebble Creek - Desoto 138 kV Line |  | Desoto | Pebble Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4328 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 | 22RPG014 | 2022-05-15 | 2022-06-15 |  | 2229, 2328, 2424 | Y |  |  | 0 | 69353 | 69352
71898 | Install two additional 9.2 Mvar stages at Carroll Springs 69 kV Cap Bank | Install two additional 9.2 Mvar stages at Carroll Springs 69 kV Cap Bank |  | Carroll Springs | Carroll Springs | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6241 | 2024-05-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Anderson | Anderson | Tier 4 |  |  |  |  | 3270 | Y |  |  | 0 | 71899 | 71898
71968 | Midkiff - Pemkiff 138 kV Line | Rebuild the existing 138 kV line |  | Midkiff | Pemkiff | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8641 | 2024-05-15 |  | 138 | 0 | 0.31 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 1210, 23871 | Y |  |  | 0 | 71970 | 71968
57726 | Commerce - Royse 69 kV Line Conversion to 138 kV | Convert existing 69 kV Line to 138 kV |  | Commerce Switch | Royse | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R985 | 2024-05-15 01:00 |  | 138 | 0 | 38.3 | 0 |  | Hunt | Rockwall | Tier 3 | 20RPG023 | 2020-12-23 | 2021-01-19 |  |  | Y | N |  | 0 | 81830 | 57726
59525 | Cedar Crest Switch - Wall Street 69 kV Line Section Conversion To 138 kV | Convert existing 69 kV Line to 138 kV operation |  | Cedar Crest | Wall Street | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4071 | 2024-05-16 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 | [5 empty] | Y |  |  | 0 | 68717 | 59525
68266 | Dry Frio: Build new 138 kV station | Interconnect Sunray Solar to the Dry Frio 138 kV station | Contact Update | Dry Frio |  | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2024-05-19 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 4 |  |  |  |  | 8707, 8234, 8241 | Y |  |  | 0 | 68267 | 68266
79683 | Add Branch between Padua and Sommers |  |  | 5395 | 170722 | Planned | S-0969, T-0327 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2024-05-24 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5395, 170722 | Y |  |  | 0 | 79684 | 79683
73166 | Whitepoint: Rebuild Station | Rehab Whitepoint 138/69 kV Station | Schedule Update | Whitepoint |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TA2018035 | 2024-05-30 |  | 138 | 0 | 0 | 130 |  | San Patricio |  | Tier 4 |  |  |  |  | 8960, 8961 | Y | N |  | 0 | 73167 | 73166
68960 | North Edinburg: Expand 345 kV station | Construct new terminals at North Edinburg for the ETT 2nd circuits project | Transmission Status, Planning Tier, RPG Number, and RPG Dates Update | North Edinburg |  | Under Construction |  | AEP TCC | James Weaver mlforcum@aep.com 918-599-2674 | TP2021705 | 2024-05-30 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8383, 8455, 8901, 8905 | Y |  |  | 0 | 71132 | 68960
65987 | Gibbs: Build new 138 kV terminal | Interconnect Jackalope Solar to the Gibbs 138 kV station | In-Service Date Update | Gibbs |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2021288 | 2024-05-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 88173, 8173 | Y |  |  | 0 | 65988 | 65987
50874 | Smith - Mathis: Line Rebuild | Smith - Mathis: Line Rebuild |  | Smith | Mathis | Planned | 1053 - 1226 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3781 | 2024-05-30 |  | 69 | 0 | 22.47 | 0 |  | San Patricio | San Patricio | Tier 3 | 20RPG001 | 2020-02-15 | 2020-03-24 |  | 8407, 8408, 8424, 8866 | Y | N |  | 0 | 65547 | 50874
64505B | Flewellen to Peters Ckt.25E Upgrades | Upgrade Ckt.25E Foster to Twinwood Mobile to Peters to increase thermal limits |  | Foster | Peters | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-30 00:02 |  | 138 | 0 | 27.4 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 21RPG011 | 2021-06-04 | 2021-07-02 |  | 44256, 44860, 46220 | Y | N |  | Cost included in main entry | 64507 | 64505
66046 | Ckt09 Zenith-VillageCreek Reconfigurations | Expand Zenith 138kV substation and install radial section Ckt.45 Zenith to Village Creek. Reconfigure Ckt.09K at Village Creek to create Ckt.09K Zenith to Village Creek tap to Franz. |  | Zenith | Village Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 3.6 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44270, 44271, 44272, 48272, 44260, 44910 | Y | N |  | 0 | 80706 | 66046
75835B | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. | Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. |  | Hockley |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 | 0,40 | Harris | Harris | Tier 3 |  |  |  |  | 45886 | Y | N |  | 0 | 75837 | 75835
77148 | Coryell Rebuild |  |  |  |  | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-05-31 |  | 69 | 0 | 0 | 0 |  | Coryell | Coryell | Tier 4 |  |  |  |  | 37520, 37530, 37570, 37580 | Y |  |  | 0 | 77149 | 77148
48415B | TransPecos Capbank in TNMP West Texas System | Expands TransPecos Capacitor bank by 1 block of 20 Mvar. |  | TransPecos (Bus #38377) | TransPecos (Bus #38377) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | NTE07919 | 2024-05-31 |  | 138 | 0 | 0 | 0 | 0,20 | Reeves | Reeves | Tier 4 |  |  |  |  | 38377 | Y |  |  | 0 | 48417 | 48415
75932 | Village Creek Distribution Transformer Addition | Expand Village Creek substation with addition of 3rd distribution transformer. Transformer expected at Ckt.09K Zenith to Village Creek to Franz. |  | Village Creek | Zenith/ Franz | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44272 | Y | N |  | 0 | 80705 | 75932
82210 | PMCR for LEAGUE CITY STATION REBUILD | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38920 | Y |  |  | 0 | 82211 | 82210
69900B | Eastgate (EAS) 138kV CNP Substation for XE Murat Solar (22INR0354) | Install generator lead from Eastgate (EAS) substation to ADLONG/XE Murat Solar |  | Eastgate | ADLONG | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 75843 | 69900
76212 | Model Coachwhip Sub |  |  | From Mivida PSSE bus# 38152 | To Fishhook PSSE Bus# 38180 | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38170, 38152, 38180 | Y |  |  | 0 | 76213 | 76212
75936 | Galena Park Distribution Transformer Addition | Expand Galena Park substation with addition of 3rd distribution transformer. Transformer expected at Ckt.94M Normandy tap to Galena Park tap to TANKER. |  | Galena Park |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40613, 40614 | Y | N |  | 0 | 75937 | 75936
67422B | Greens Bayou to Clinton 138kV Conversion | Reduce existing Greens Bayou cap bank CB1 from 120 MVAR to 100 MVAR |  | Greens Bayou | 0 | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 | -20,0 | Harris | Harris | Tier 4 |  |  |  |  | 40717 | Y | N |  | 0 | 72773 | 67422
68970 | Lobo: Build (2) 345 kV terminals | Construct new terminals at Cenizo, Del Sol, Lobo, and Pomelo for the ETT 2nd circuits project | Transmission Status, In-Service Date, Planning Tier, RPG Number, and RPG Dates Update | Lobo |  | Under Construction |  | ETT TCC | James Weaver mlforcum@aep.com 918-599-2674 | TP2021704 | 2024-05-31 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80219 | Y | Y |  | 0 | 68971 | 68970
66386 | Albany to Throckmorton: Rebuild 69 kV line | Rehab 69 kV line from Albany to Throckmorton | In-Service Date Update | Albany | Throckmorton | Planned |  | AEP TNC | Raza Ansari twang1@aep.com 918-599-2635 |  | 2024-05-31 |  | 69 | 0 | 32.36 | 0 |  | Shackelford | Throckmorton | Tier 4 | 21RPG015 | 2022-08-21 | 2022-09-21 |  | 6205, 6206, 6207 | Y | N |  | 0 | 66387 | 66386
69900A | Eastgate (EAS) 138kV CNP Substation for XE Murat Solar (22INR0354) | New 138kV Eastgate (EAS) substation for generator interconnection to XE Murat Solar. Loop Ckt.66E into substation to create new Ckt.66 Crosby to Eastgate to Atascocita. |  | Eastgate | Atascocita/Crosby | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40690, 40130, 40390 | Y | N |  | Loop Ckt.66E into new substation to create new Ckt.66 Crosby to Eastgate to Atascocita. | 75842 | 69900
73371A | BP24 Sub Upgrades | Upgrade Bellaire Auto A2 spans and CTs to increase thermal limits |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47000, 47010, 49084 | Y | N |  | 0 | 73372 | 73371
72061 | HO Clarke to Kirby Ckt.90A Upgrade to Limiting Section | Upgrade Ckt.90A HO Clarke to Kirby to increase thermal limits. |  | HO Clarke | Kirby | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 6.78 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47151, 48363 | Y | N |  | 0 | 72062 | 72061
43212B | Caymus Capbanks in TNMP West Texas System | Expands Caymus Capacitor bank by 1 block of 20 Mvar. |  | Caymus (Bus #38410) | Caymus (Bus #38410) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | NTE07819 | 2024-05-31 |  | 138 | 0 | 0 | 0 | 0,20 | Reeves | Reeves | Tier 4 |  |  |  |  | 38410 | Y |  |  | 0 | 48414 | 43212
68972 | Tiempo to Fowlerton: Add Second 345 kV Circuit | Hang conductor to complete a double circuit between Tiempo and Fowlerton for the ETT 2nd circuits project | Project Title, Transmission Status, Owner, In-Service Date, RPG Number, and RPG Dates Update | Tiempo | Fowlerton | Under Construction |  | ETT TCC/STEC | Teresa Trotman mlforcum@aep.com 918-599-2674 | TP2021703 | 2024-05-31 |  | 345 | 63.38 | 0 | 0 |  | Webb | Zapata | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80219, 80220, 80221, 5709, 80224, 80230 | Y | Y |  | 0 | 68973 | 68972
67422C | Greens Bayou to Clinton 138kV Conversion | Convert Wallisville substation from double-tap service to loop service on Ckt.10A. Remove TEXWAL substation from Ckt.10 service. Resulting in Ckt.10A Clinton to CASTEN tap to Wallisville loop to Greens Bayou |  | Clinton | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 |  | 69 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 41570, 41680, 41681, 41682, 48372, 48412, 48413, 40720, 48299 | Y | N |  | 0 | 72772 | 67422
63834A | Alvin Area 138kV Conversions | Reconfigure existing Ckt.26H Archer to Karsten to create new Ckt.26H Archer to Manvel. |  | Karsten | Manvel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 44430, 44440, 42570, 44390, 44410 | Y | N |  | 0 | 79862 | 63834
66009B | SNUG (SNU) 138kV CEHE Station for Cottonwood Bayou Solar (21INR0228 | Install one generator lead for new interconnection to COTTON/Cottonwood Bayou Solar |  | SNUG | COTTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 44890, 113435 | Y | N |  | 0 | 75723 | 66009
73371B | BP24 Sub Upgrades | Upgrade Bellaire Auto A5 CTs to increase thermal limits |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47000, 47015, 49003 | Y | N |  | 0 | 73373 | 73371
67422D | Greens Bayou to Clinton 138kV Conversion | Rebuild TEXWAL substation as 138kV breakered station. Rebuild Wallisville substation as 138kV loop-tap station. Expand Greens Bayou 138kV 'West' bus and Clinton 138kV station with new line positions. Reconfigure and connect new 138kV stations to create new 138kV Ckt.xx Greens Bayou to TEXWAL to Wallisville to Clinton. |  | Greens Bayou | Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:02 |  | 138 | 2.17 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41575, 40350, 40715 | Y | N |  | Cost included in Phase C | 72774 | 67422
63834B | Alvin Area 138kV Conversions | Reconfigure existing Ckt.26B Rosharon to Karsten to create new Ckt.26B Manvel to Alvin tap to Karsten. |  | Manvel | Rosharon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42073, 44410, 48173, 44390, 44430 | Y | N |  | Cost in main project | 79863 | 63834
73371D | BP24 Sub Upgrades | Wharton Loop Upgrade Ckt.60B (BP24 Sub Upgrades) |  | Wharton | Caney | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:03 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 43570, 44131, 44132 | Y | N |  | 0 | 73375 | 73371
63834C | Alvin Area 138kV Conversions | Reconfigure existing Ckt.05B LIMBERG to Friendswood tap to Webster to create new Ckt.05B LIMBERG to Alvin tap to Friendswood tap. Rebuild Alvin substation for double-tap service. |  | LIMBERG | Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Harris | Tier 4 |  |  |  |  | 42072, 42651, 48172, 43280, 48111 | Y | N |  | Cost in main project | 79864 | 63834
63834D | Alvin Area 138kV Conversions | Rebuild portions of Ckt.53 Webster to Karsten to HO Clarke for 138kV Line Conversion. Retire the remaining portions of Ckt.53. Retire KR-A1 and WEB-A1 |  | Karsten | Webster/HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:04 |  | 69 | 0 | 0 | -300 |  | Brazoria | Harris | Tier 4 |  |  |  |  | 44400, 49022, 44440, 47160, 44390 | Y | N |  | Cost in main project | 79861 | 63834
73371F | BP24 Sub Upgrades | Upgrade Jeanetta to WA Parish Ckt.64A to increase thermal limits |  | Jeanetta | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:05 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47300 | Y | N |  | 0 | 73377 | 73371
73371G | BP24 Sub Upgrades | Upgrade Ckt.27A DOW to Jones Creek to increase thermal limits for Continuous ratings |  | DOW | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:06 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 42530 | Y | N |  | 0 | 73378 | 73371
73371H | BP24 Sub Upgrades | Upgrade White Oak to Jeanetta Ckt.72B to increase thermal limits |  | White Oak | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:07 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46600, 47300 | Y | N |  | 0 | 73379 | 73371
73371I | BP24 Sub Upgrades | Upgrade Jefferson to South Channel Ckt.06E to increase thermal limits |  | Jefferson | South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:08 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41240, 41370 | Y | N |  | 0 | 73380 | 73371
70660 | Plaza to Grant Ckt.08I Upgrade | Install parallel underground portion of Ckt.08I Plaza to Grant to increase thermal limits. |  | Plaza | Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:10 |  | 138 | 0 | 0.44 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47110, 47350 | Y | N |  | 0 | 70661 | 70660
50870 | Coleto Creek - Rosata: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild | In-Service Date Update | Coleto Creek | Rosata | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3778 | 2024-05-31 01:00 |  | 138 | 0 | 15.3 | 0 |  | Goliad | Goliad | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8162, 8153 | Y | N |  | 0 | 50871 | 50870
65719 | Rebuild and reconductor portion of Missouri City to Sienna Ckt.05A as a Hardening upgrade | Rebuild and reconductor portion of Missouri City to Sienna Ckt.05A as a Hardening upgrade |  | Missouri City | Sienna | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 12:00 |  | 138 | 0 | 3.7 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44482, 44652 | Y | N |  | 0 | 65720 | 65719
66009A | SNUG (SNU) 138kV CEHE Station for Cottonwood Bayou Solar (21INR0228 | Loop new CEHE 138kV substation SNUG (SNU) into Ckt.04 Liverpool to PETSON to create new Ckt.04 Liverpool to SNUG to PETSON. |  | SNUG | Liverpool/PETSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 12:00 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 44890, 42870, 43070 | Y | N |  | 0 | 66010 | 66009
70798 | Stewart Road: Station work | Kiskadee Storage |  | Stewart Road |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022166 | 2024-06-01 |  | 138 | 1 | 0 | 0 |  | Hidalgo |  | Tier 4 | [5 empty] | Y |  |  | 0 | 70799 | 70798
67093 | New 138 kV station cut-in between Garfield and Hi-Cross | New 138 kV Easton Park Substation cut-in on CKT963 from Garfield to Hi-Cross substation to serve BBEC Load |  | 9143 |  | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9143, 9071, 9147 | Y |  |  | 0 | 67094 | 67093
66113 | Add WalnutSpr Auto & 138kV Switchyard |  |  | Oncor Walnut Springs (Bus # 1646, 1647) | TNMP Walnut Springs (Bus # 37680, 37681) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-06-01 |  | 138 | 0 | 0 | 208.8 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 1647, 37681, 1646, 37680 | Y |  |  | 0 | 66115 | 66113
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures. Kramer Lane (KA) substation will be cut-into this line in 2023 |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | P396 | 2024-06-01 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238, 9276 | Y | N |  | Will add the ptoject to the base case. | 8207 | 1031

## CancelledTPIT060124NoCost
JUNE BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 6/1/2024
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
44416 | Add a 2nd circuit at Brinker - Denton Steam |  |  | Brinker | Denton Steam | Planned |  | DENTON | Chuck Sears |  | 2024-07-01 | 2022-07-01 | 138 | 0.631 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 982 | N | N |  | 0 | 44417 | 44416
64021 | Texana Solar Interconnection | Connect the Texana Solar to the El Campo to Victoria 138 kV line | CANCELLED | El Campo | Victoria | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2020888 | 2024-09-30 |  | 138 | 0 | 0 | 0 |  | Wharton | Victoria | Tier 4 |  |  |  |  | 8192, 8675, 8099, 8102, 8117 | N |  |  | 0 | 64022 | 64021
69485 | Wahpekute: Build new 69 kV station | Build new 69 kV station with a capacitor bank along the Jayton to Rotan 69 kV line | CANCELLED | Wahpekute |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2024-10-31 |  | 69 | 0 | 0 | 0 | 0,3.8 | Fisher |  | Tier 4 |  |  |  |  | 60057, 60066, 6162, 6196 | N |  |  | 0 | 69486 | 69485
76174 | Origin 138 kV Interconnection | Interconnect Callon Petroleum on the Saragosa to Solstice 138 kV line | CANCELLED | Origin |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-06-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60208, 60209, 60211, 60206, 60207, 60716 | N | N |  | 0 | 76175 | 76174
5461 | Load serving |  |  | Puckrus | Mayhill | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2025-07-01 | 2023-07-01 | 138 | 1.9 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 929, 917 | N | N |  |  | 13164 | 5461
76288 | Hecker to McCampbell: Rebuild 138 kV Line | Rebuild the Hecker to McCampbell 138 kV Line | CANCELLED | Hecker | McCampbell | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2023507 | 2025-11-30 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8565, 80470 | N | N |  | 0 | 76289 | 76288
61446 | Wilson-SS Felps Tap to Wilson South | Build 0.99 miles of new double circuit 138kV t-line loop, 795 ACSR Drake, along FM 775 to Wilson South Substation, about 4.35 miles south of La Vernia | [5 empty] | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-12-19 |  |  | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7627, 7628, 5418, 7615, 7629 | N |  |  | 0 | 61447 | 61446
61446 | Wilson-SS Felps Tap to Wilson South | Build 0.99 miles of new double circuit 138kV t-line loop, 795 ACSR Drake, along FM 775 to Wilson South Substation, about 4.35 miles south of La Vernia |  | Wilson South | Wilson | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-12-20 |  | 138 | 0.99 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 7627, 7628, 5418, 7615, 7629 | N | N |  | 0 | 61448 | 61446
76280 | Reforzar: Build new 345 kV station - stage 2 | Build new 345 kV station on the Lon Hill to North Edinburg 345 kV line | CANCELLED | Reforzar |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022035 | 2026-01-30 |  | 345 | 0 | 0 | 0 |  | Brooks |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80078 | N |  |  | 0 | 76281 | 76280
5496 | Forney Switch 345 kV Terminal Equipment | Upgrade the terminal equipment at Forney 345 kV Switch |  | Royse |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3022 | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 4 |  |  |  |  | 2437, 2478 | N |  |  | 0 | 62442 | 5496
65648 | Interconnects Faulkner Data Center | Project has been cancelled. |  | TNMP Faulkner (bus # 38124) | Customer substation (bus # 38125) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-10-01 |  | 138 | 0.15 | 0 | 0 | 0,160 | Reeves | Reeves | Tier 4 |  |  |  |  | 38125, 38124 | N |  |  | 0 | 65649 | 65648
5524 | Royse South 345/138 kV Switching Station | Establish new 345/138 kV switching station |  | Royse | Forney | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4234 | 2030-05-15 12:00 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 3 |  |  |  |  | 2469, 2470, 12471, 2437, 2467, 2471, 2478, 2702, 2472, 2474, 2485, 2710 | N | N |  | 0 | 49918 | 5524
5220 | Move Orange Grove load to 138 kV bus | Move load from the 69 KV to the 138 KV instead of replacing auto. 2015 RTP |  | Orange Grove |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 138 | 0 | 0 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 5660 | N | N |  |  | 12887 | 5220
3822 | San Miguel to Sigmor 138 kV line upgrade | Upgrade San Miguel to Sigmor 138 kV line as recommended in 2013 RTP. Will investigate re-conductoring on existing structures with ACCC and other high temperature conductors. |  | San Miguel | Sigmor | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 138 | 0 | 26.3 | 0 |  | Atascosa | Live Oak | Tier 3 |  |  |  |  | 5689, 5902, 8404 | N | N |  | Studies after the 2013 RTP have shown that AEP's approved project to rebuild the 69 kV Beeville to Three Rivers to 138 kV, TPIT 5166, reduces the loading on this line. STEC believes that rebuilding San Miguel to Sigmor is likely to be justified in the future by load growth and or generation additions. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 11279 | 3822
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  | Airport |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 5601, 5600, 5602 | N | N |  |  | 8729 | 1538

## RTPProjects
Project Number | Project Name | Transmission Owner | ERCOT Proposed in-service year | TSP MOD in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2023-C1 | North Rosenberg (944070) 345-kV Substation Addition and 345-kV Double-Circuit Line Additions from Whaley (44070) to North Rosenberg (944070) to Obrien (44500) | CNP | 2025
2023-C2 | Formosa (8126) to Lolita (8125) to Blessing (8121) 138-kV Line Upgrade | AEP | 2025
2023-C3 | Cangrejo (8720) to Pcomfort (8132) 69-kV Line Upgrade | AEP | 2025
2023-C4 | South Texas Project (5915) to WA Parish (44000) 345-kV Line Upgrade | AEP, CNP | 2025
2023-E1 | Big Brown Ses (3381) to Jewett (3391) 345-kV Double-Circuit Line Upgrade | ONCOR | 2025
2023-E2 | Canton Switch (3174) to Edgewood (3181) 138-kV Line Upgrade | ONCOR | 2025
2016-N1 | Kiamichi Energy Facility (140077) 345-kV Reactor Addition | KIOWA POWER PARTNERS LLC (RE) | 2026 min
2023-N1 | Gainesville 138/69-kV Transformer Upgrade | BEPC | 2026
2023-N2 | Beaver (1524) to Old Lake Switch (11541) 69-kV Line Upgrade | ONCOR | 2026
2023-N3 | LPL Line Upgrades | LPL | 2025
2023-N4 | Sand Road (6063) to Southwest Vernon (6064) 69-kV Line Upgrade | AEP | 2026
2023-N5 | Parkway (1499) to Bowman (1423) to Lake Wichita (1446) 138-kV Line Upgrades | ONCOR | 2025
2023-N6 | Fisher Road (1427) to Wichita Falls (1448) 138-kV Line Upgrade | ONCOR | 2025
2023-N7 | Hawk Hollow Switch (11768) to Deport (1768) to Rivercrest SES (1780) 138-kV Line Upgrades | ONCOR | 2025
2023-N8 | Yellow House Canyon Substation 345/115-kV Transformer Upgrade | LPL | 2028
2023-N9 | Spur 138/69-kV Transformer Upgrade | AEP | 2029
2023-N10 | Pleasant Valley Switch (1450) to Ceramic (1485) to Wichita Falls PPG (1484) to Wichita Falls PPG Oxygen (17005) to City View (1483) 138-kV Line Upgrades | ONCOR | 2025
2023-N11 | Wichita Falls South Switch (1464) to Arrowhead (1478) to Rathgeber (1480) 138-kV Line Upgrades | ONCOR | 2026
2023-N12 | Bonham Switch (1760) - Bonham (1808) - Copperhead Switch (11809) 138-kV Line Upgrade | ONCOR | 2025
2023-N13 | Whitesboro Southwest (718) 138-kV Capacitor Bank Addition | BEPC | 2028
2022-NC2 | Brand (827) to Ben Davis (968) 138-kV Line Upgrade | GPL | 2025 | 2024-06-01 | Operational | 67170
2022-NC5 | New International Airport Switch 345/138-kV Station | ONCOR | 2025
2022-NC7 | Liggett Switch- DFW Area 138-kV Line Upgrades | ONCOR | 2025
2023-NC1 | Miller to Palopnto 138-kV Line Upgrades | BEPC, ONCOR | 2025
2023-NC2 | Carmichael Bend Switch to Benbrook Switch 345-kV Line Upgrade | ONCOR | 2025
2023-NC3 | Randol Mill Tap East (2104) to Randol Mill (2106) 138-kV Line Upgrade | ONCOR | 2025
2023-NC4 | Watermill Switch (2428) to Loop Nine Switch (22427) 345-kV Line Addition | ONCOR | 2025
2023-NC5 | Temple Switch (3415) to Temple Southeast (3612) 138-kV Line Upgrade | ONCOR | 2025
2023-NC6 | Telico Area Upgrades | ONCOR | 2025
2023-NC7 | Four Brothers Switch -Tradinghouse - Outlaw - Lake Hall Switch - Sam Switch Area Improvements | ONCOR | 2026
2023-NC8 | Gunter 345/138-kV Substation Addition | ONCOR | 2025
2023-NC9 | Seagoville to Watermill 138-kV Line Upgrade | ONCOR | 2025 | 2025-12-15 | Planned | 71178
2023-NC10 | Prairie Creek to Mesquite North 138-kV Line Upgrade | ONCOR | 2025
2023-NC11 | Centerville Area Line Upgrades | GPL | 2025 | 2024-10-01 | Planned | 73348
2023-NC12 | Mexia Transformer Upgrade | ONCOR | 2025
2023-NC13 | Hillboro 138-kV Area Upgrades | BEPC | 2025
2023-NC14 | Killeen to Salado 345-kV Line Upgrade | ONCOR | 2029
2023-NC15 | Renner Switch 345/138-kV Transformer Upgrade | ONCOR | 2025
2023-NC16 | Sardis Area 138-kV Line Upgrades | ONCOR | 2025
2023-NC17 | Temple Southeast (3612) to Scott and White (3602) to Temple South (3611) 138-kV Line Upgrades | ONCOR | 2025
2023-NC18 | Tri Corner (2432) to Seagoville Switch (2433) to Forney Switch (2437) 345-kV Line Upgrade | ONCOR | 2025
2023-NC19 | Venus - Fort Smith - Sam Switch Double Circuit 345-kV Line Upgrades and Venus Kemp Ranch 345/138-kV Transformer Addition | ONCOR | 2025
2023-NC20 | Kemp South (2726) to Seven Points (3264) to Will White POI (3287) 138-kV Line Upgrade | ONCOR | 2026
2023-NC21 | Cedar Creek Pump (3263) to Mankin SW (3265) 138-kV Line Upgrade | ONCOR | 2025
2023-NC22 | Nolanville (3617) to Harker Heights (3618) 138-kV Line Upgrade | ONCOR | 2025
2023-NC23 | Venus - Navarro - Jewett Area 345-kV Line Upgrades | ONCOR | 2026
2023-NC24 | Southside POI (230) to MCCree (832) 69-kV Line Upgrade | BEPC | 2028
2023-NC25 | Concord (394) to Wildcat Switching Station (388) 138-kV Line Upgrade | BEPC | 2028
2023-NC26 | West Loop (480) - Brock (487) 138-kV Line Upgrade | BEPC | 2026
2023-NC27 | Olney 138/69-kV Transformer Upgrade | BEPC | 2028
2023-NC28 | Commerce Switch (1816) - Crossroads Switch (1844) 138-kV Line Upgrade | ONCOR | 2026
2023-NC29 | Mitchell Bend Switch (1895) - Carmichel (2285) 345-kV Circuit Addition | ONCOR | 2026
2023-NC30 | PNTHRISL (1966) - Randoll Mill (2106) 138-kV Line Upgrade | ONCOR | 2026
2023-NC31 | Parkdale Switch (2445) - Pleasant Grove Tap 1 (2960) 138-kV Line Upgrade | ONCOR | 2026
2023-NC32 | Cedar Crest Switch (2486) - Buntin Drive (2985) 138-kV Line Upgrade | ONCOR | 2026
2023-NC33 | Sargent Road (2941) - Saint Augustine Tap 2 (2951) 138-kV Line Upgrade | ONCOR | 2025
2023-NC34 | Temple Pecan Creek (3412) - Temple Switch (3414) 345-kV Line Upgrade | ONCOR | 2026
2023-NC35 | Navarro (3478) - Haney (213) - Hubbard (3515) 138-kV Line Upgrade | ONCOR | 2026
2023-NC36 | Temple Belton 138-kV Line Upgrades | ONCOR | 2025
2023-NC37 | Hillboro 138/69-kV Transformer Upgrade | ONCOR | 2025
2023-NC38 | Watermill 345/138-kV Transformer Upgrade | ONCOR | 2025
2023-NC39 | Navarro (3479) to Richland (3486) 69-kV Line Upgrade | ONCOR | 2028
2023-NC40 | Mclennan County East (3442) to Tradinghouse Tap (3555) to Hallsburg (95) to Lake Creek (3410) 138-kV Line Upgrades | BEPC | 2028
2023-NC41 | Watermill 138-kV Area Upgrades | ONCOR | 2026
2023-NC42 | Waxahachie Area 69-kV and 138-kV Line Upgrades | ONCOR | 2026 min
2023-NC43 | Wilmer 138/69-kV Transformer Upgrade | ONCOR | 2026
2023-NC44 | Corinth (1985) to Argyle (1984) to Highlands TNP (1974) 138-kV Line Upgrades | ONCOR | 2025
2023-NC45 | Cleburne Switch (2279) to Keene (2294) to Alvarado (2297) to Griffith (1905) to Railport (442) to Venus (1908) 138-kV Line Upgrades | BEPC, ONCOR | 2025
2023-NC46 | Desoto Switch (2424) to Parkerville Road (12425, 2425) 138-kV Line Upgrade | ONCOR | 2025
2023-NC47 | Carrollton Tarpley Road (2559) to Carrollton East (2578) 138-kV Line Upgrade | ONCOR | 2028
2023-NC48 | Plano Arco (2671) to Plano West (2673) 138-kV Line Upgrade | ONCOR | 2029
2023-NC49 | Greenville Avenue Switch (2882) to Greenville Avenue (12882) 138-kV Line Upgrade | ONCOR | 2028
2023-NC50 | Harker Heights (3618) to Killeen Taft Street (3616) to Killeen Elm (13427) 138-kV Line Upgrades | ONCOR | 2025
2023-NC51 | Temple Area 138-kV Upgrades | ONCOR | 2025
2023-NC52 | Cedar Hill Switch (2422) to Fish Creek Switch (2491) 138-kV Line Upgrade | ONCOR | 2026
2023-NC53 | Centerville Road Switch Area 138-kV Line Upgrades | ONCOR | 2026
2023-NC54 | Corsicana (3468) to Barry (Oncor) (3471) 69-kV Line Upgrades | ONCOR | 2028
2023-NC55 | Everman 345/138-kV Transformer Addition | ONCOR | 2028
2023-NC56 | Everman (1883,1884) to Marrs (1969) 138-kV Upgrade | ONCOR | 2028
2023-NC57 | Killeen Area 138-kV Capacitor Bank Additions | ONCOR | 2025
2023-NC58 | Lake Creek 345/138-kV Transformer Upgrade | ONCOR | 2028
2023-NC59 | Plano Highway 190 Area 138-kV Line Upgrades | ONCOR | 2029
2023-NC60 | Temple Switch and Temple Pecan 345/138-kV Transformer Additions | ONCOR | 2025
2023-NC61 | Temple Pecan Area 138-kV Upgrades | ONCOR | 2025
2023-NC62 | Whitney 345/138-kV Transformer Upgrade | BEPC | 2025
2023-NC63 | DFW and Euless Area 138-kV Upgrades | ONCOR | 2025
2021-W5 | Sacroc - Deep Creek Sub 138-kV Line Upgrade | ONCOR | 2026
2023-W1 | Hamlin to Roby 69-kV Line Rebuild | AEP | 2026 | 2026-11-30 | Planned | 73055
2023-W2 | San Angelo Mathis Field - Tankersley - Mertzon - Cassava 69-kV Line Upgrade | AEP | 2025
2023-W3 | Colorado City to Plowboy 69-kV Line Upgrade | ONCOR | 2026
2023-W4 | Bluff Creek Switch - China Grove Switch - Oncor 900067 Tap - Getty Vealmoor Tap 138-kV Line Upgrade | ONCOR | 2025
2023-W5 | Sterling City to Camp Elizabeth 69-kV Line Upgrade | AEP | 2025
2023-W6 | Cedar Hills to Silver Tap 69-kV Line Upgrade | AEP | 2025
2023-W7 | Carlsbad Tap to Burma 69-kV Line Upgrade | AEP | 2026
2023-W8 | San Angelo North 138/69-kV Transformer Upgrade | AEP | 2028
2023-W9 | New Load Bus 900110 138-kV Cap Bank Addition | AEP | 2028
2023-W10 | Dermott - Scurry Chevron - Kndrsacrc - Oncor900041 Tap - Knapp - Bluff Creek 138-kV Line Upgrade | ONCOR | 2025
2023-W11 | Red Creek Area 138-kV Lines Upgrade | AEP | 2026
2023-W12 | Morgan Creek SES - Tonkawa 345-kV Line Rebuild | ONCOR | 2025
2023-W13 | Bondroad to Friess Ranch 69-kV Line Upgrade | AEP | 2028
2023-W14 | Campwood - Barcksdale - Rocksprings 69-kV Line Upgrade | AEP | 2025 | 2028-08-31 | Planned | 55617, 55605
2023-W15 | San Angelo Redcreek Third 345/138-kV Transformer Addition | AEP | 2026
2023-W16 | Abilene Northwest-Abi Mulberry Creek-Abi Industrial Park-Abi Elmcreek 138-kV Upgrade | AEP | 2025
2023-W17 | Dermott to Ennis Creek Switch 138-kV Line Upgrade | ONCOR | 2028
2023-W18 | Golden Switch to Sun Switch 138-kV Line Upgrade | ONCOR | 2029
2023-W19 | Bluff Creek Switch - Exxon Sharon Ridge 138-kV Line Upgrade | ONCOR | 2026 min
2021-FW4 | Rio Pecos - Rankin - Texon Tap - Atlantic Best Tap - Kemper Tap - Big Lake 69-kV to 138-kV Line Conversion | AEP | 2025
2021-FW5 | Caymus TNP - Gas Pad 138-kV Line and Caymus TNP - Caymus Compressor TNP Line Terminal Equipment Upgrade | AEP | 2025
2021-FW6 | TNMP Monument Draw to Monument Draw Gray Oak 138-kV Line Terminal Equipment Upgrade | TNMP | 2028
2021-FW7 | TNMP Flat Top 138/25-kV Transformer Upgrade | TNMP | 2025
2021-FW8 | TNMP Wink - TNMP California 69-kV to 138-kV Line Conversion | TNMP | 2028
2021-FW16 | 16th Street TNP - Fort Stockton TNP 69-kV Line Upgrade | TNMP | 2025
2021-FW19 | Morgan Creek SES - Longshore Switch 345-kV Line Upgrade | ONCOR | 2026
2021-FW20 | Lamesa - Key Sub - Gail Sub - Willow Valley Switch 138-kV Line Upgrade | ONCOR | 2026 min
2022-FW2 | Cedarvale 345-kV Subtation Expansion | ONCOR, TNMP | 2025
2022-FW10 | Dollarhide - Dollarhide Unocal 138-kV Line Upgrade | ONCOR | 2025
2022-FW15 | Holt Switch - Turnbaugh Corner Switch - Scharbauer POI - Oncor 900053 Tap - Notrees Southeast POI - Blockline POD - Amburguey - Yucca Drive Switch 138-kV Line Upgrade | ONCOR | 2025
2022-FW23 | Consavy South 345/138 S-kV Susbstation Addition and 345-kV Line Addition | ONCOR | 2025
2022-FW24 | Faraday - Lamesa - Clearfork - Riverton 345-kV Double Circuit Line Addition | ONCOR, WETT | 2026 min
2022-FW25 | Cedarvale Third 345/138-kV Transformer Addition | TNMP | 2026
2023-FW1 | Glasscock County North - Forsan Tap - Mcdonald - Polecat Creek Switch 138-kV Line Upgrade | ONCOR | 2028
2023-FW2 | Illinois - Pandale - Ozona Rea - Ozona - Friend Ranch - Atlantic Sonora 69-kV Upgrade | AEP | 2025
2023-FW3 | Collie Field Tap TNP - IH 20 TNP 138-kV Line Upgrade | TNMP | 2028
2023-FW4 | Buzzard Draw Switch - Koch Tap - Vealmoor 138-kV Line Upgrade | ONCOR | 2025
2023-FW5 | Gemsbok TNP 138-kV Cap Bank Addition | TNMP | 2028
2023-FW6 | Foxtail TNP to Pig Creek 138-kV Line Upgrade | TNMP | 2026
2023-FW7 | Wolfcamp - Courtney Creek 69-kV to 138-kV Line Conversion | ONCOR | 2025
2023-FW8 | Midkiff Switch 138-kV Cap Bank Addition | ONCOR | 2028
2023-FW9 | East Stiles 138-kV Cap Banks Addition | ONCOR | 2025
2023-FW10 | Far West Reactive Power Support Device Addition | AEP, ONCOR, TNMP | 2028
2023-FW11 | New Load Bus 900062 138-kV Cap Bank Addition | AEP | 2025
2023-FW12 | Foxtail TNP to Flat Top TNP 138-kV Line Upgrade | AEP, TNMP | 2025
2023-FW13 | Bulldog - Elbow - Eiland - Einstein - Carterville 138-kV Line Upgrade | ONCOR | 2025
2023-FW14 | Spraberry Switch to Skywest 138-kV Line Upgrade | LCRA, ONCOR | 2025
2023-FW15 | Odessa to Onc900016 138-kV Line Upgrade | ONCOR | 2025
2023-FW16 | Fort Stockton Plant - Leon Creek TNP 138-kV Line Upgrade | AEP, TNMP | 2026
2021-WFW1 | Big Lake - Barnhart - Cassava 69-kV to 138-kV Line Conversion | AEP | 2028
2022-WFW1 | Twin Buttes - Hargrove - Pumpjack - Jerry - Russek Street - Big Lake 138-kV line Upgrade | AEP, LCRA | 2025
2022-WFW2 | Midessa South SW - Consavvy - Longshore Switch - Morgan Creek SES 345-kV Line Upgrades | ONCOR | 2026 min
2023-WFW1 | Exxon Sharon Ridge to Willow Valley Switch 138-kV Line Upgrade | ONCOR | 2026 min
2023-WFW2 | Morgan Creek SES - Falcon Seaboard - Midland East 345-kV Line Upgrade | ONCOR | 2026 min
2022-SC7 | Decker 138-kV Bus Tie Breaker Upgrade | AEN | 2025
2022-SC8 | Lytton Substation 345/138-kV Transformer Addition | AEN | 2025
2023-SC1 | Austrop Substation 345/138-kV Transformer Addition | LCRA | 2025
2023-SC2 | Austrop (9328) to Dunlap (9045) Second 138-kV Line Addition | AEN | 2025
2023-SC3 | Dessau (9193) to McNeil AEN (9076) 138-kV Circuit 2 Upgrade | AEN | 2025
2023-SC4 | Hutto Switch (3666) 138-kV Cap Bank Addition | ONCOR | 2025
2023-SC5 | Beck Road 345/138-kV Substation Expansion | CPS | 2028
2023-SC6 | Lytton Springs (9074) to Garfield (7048) to Austrop (7040) 345-kV Line Upgrades | AEN, LCRA | 2025
2023-SC7 | Cachena (5068) 345-kV Reactor Addition | CPS | 2025
2023-SC8 | Dunlap 345/138-kV Transformer Addition | AEN | 2025
2023-SC9 | Scooter 345/138-kV Substation Addition | ONCOR | 2025 | 2026-05-15 | Planned | 76654
2023-SC10 | Wiseman 138-kV Substation Addition and CPS Multiple Cap Bank Additions | CPS | 2025 | 5/8/2026 and 6/1/2028 | Planned | 73366 and 75493
2023-SC11 | Lockhart to San Marcos 69-kV to 138-kV Line Conversion | LCRA | 2025 | 2026-05-12 | Planned | 73106
2023-SC12 | Lytton Springs to Pilot Knob 138-kV Line Upgrade | AEN | 2025 | 2026-06-01 | Planned | 71408
2023-SC13 | AEN Dunlap to Decker Power Plant 138-KV Second Circuit Addition | AEN | 2025 | 2027-06-01 | Planned | 67091
2023-SC14 | Trading Post and Cedar Valley Substation 138-kV Cap Bank Additions | LCRA | 2025
2023-SC15 | Sim Gideon Area 138-kV Line Upgrades | LCRA, ONCOR | 2025
2023-SC16 | Hondo to Hondo Creek Switching Station 138-kV Line Upgrade | CPS, STEC | 2025
2023-SC17 | Round Rock, Hutto, and Georgetown Area 138-kV Line Upgrades | LCRA, ONCOR | 2025
2023-SC18 | El Campo Sub to Nada 69-kV Line Upgrade | STEC | 2025
2023-SC19 | South to Central Texas 345-kV Double-Circuit Line Additions | AEN, AEP, LCRA, ONCOR | 2029
2023-SC20 | Pearson - Natalia - Devine - Moore - Pearsall 69-kV Line Rebuild | STEC | 2026 | 2025-12-01 | Planned | 76768
2023-SC21 | Big Foot to Lytle 69-kV to 138-kV Line Conversion | AEP | 2025 | 2025-09-20 | Planned | 73063
2022-S2 | Fannisub - Goliad 69-kV Line Upgrade | AEP, STEC | 2025
2022-S3 | Pearsall 138/69-kV Transformer Upgrade | STEC | 2026 | 2027-05-01 | Planned | 76790
2023-S1 | LGE to Dupont Switch - Ingleside 138-kV Line Upgrade | AEP | 2025
2023-S2 | Lon Hill to Calallen Sub 69-kV Line Limiting Element Upgrade | AEP, STEC | 2025
2023-S3 | Oaks Sub 138/69-kV Transformer Upgrade | STEC | 2025
2023-S4 | Poteet Sub to Oaks Sub 69-kV Line Upgrade | STEC | 2025
2023-S5 | Poteet Sub to Pearsall Switching Station 69-kV Line Upgrade | STEC | 2025
2023-S6 | Rossville Substation Cap Bank Addition | STEC | 2025
2023-S7 | Static (8676) 345-kV Reactor Addition | AEP | 2026 min

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Cindy Miller | Camiller2@aep.com | Cindy Miller: 918 599 2891 | Glen Reed; Brandon Cogan; Mike Forcum; Jeff Ellis; Mina Turner; Lisa Kelso; | gareed@aep.com; bcogan@aep.com; mlforcum@aep.com; dnlyons@aep.com; jlellis@aep.com; myturner@aep.com; lokelso@aep.com; | Michael Forcum: 918 599 2674 Glen Reed: 918 599 2664 Brandon Cogan: 918 599 2857 Jeff Ellis: 918 599 3458
AUSTIN ENERGY | Primary & Secondary | Reza Ebrahimian | Reza.Ebrahimian@austinenergy.com; | Reza: (512) 322-6740 | Hunt, Dandy; Brion Ryan | dandy.hunt@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | Reza:512 322 6740 Dandy:512 322 6748 Brion: 512-322-6879
BPUB | Primary | Luis Martinez | lugmartinez@brownsville-pub.com; | Luis: 956 983 6212 | Javier Martinez Jr. | jamartinez@brownsville-pub.com; | Javier: 956 983 6530
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Brian Hithersay | bhithersay@brazoselectric.com | Brian: 254-750-6795 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | Edward Lopez | elopez@btutilities.com | Edward: 979 821 5697 | David Hering | dhering@btutilities.com | David: 979 821 5652
CNP | Primary & Secondary | Wesley Woitt | wesley.woitt@centerpointenergy.com | Wesley Woitt: 713-207-2760 | Samuel Whisler; Raja Sekhar Kakarla; Cody Mann | samuel.whisler@centerpointenergy.com; rajasekhar.kakarla@centerpointenergy.com; cody.mann@centerpointenergy.com | Samuel Whisler: 713-207-2767 Raja Sekhar Kakarla: 713-207-3614 Cody Mann: 713-207-3149
COCS | Primary | Glenn Gavit | ggavit@cstx.gov | Glenn: 979 764 3682 | Timothy Crabb, Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | William Robertson | wrobertson@cpsenergy.com | William: 210 353 4147 | Kenneth Bowen Marcos Terrazas Zuber Vohra Eduardo Olivarez | kbowen@cpsenergy.com; mterrazas1@cpsenergy.com; ZMVohra@cpsenergy.com; EJOlivarez@cpsenergy.com | Kenneth: 210 353 4142 Marcos: 210 353 2451 Zuber: 210 353 4262 Eduardo: 210 353 2357
CTT (Cross Texas Transmission) | Primary & Secondary | Christina Minchew | cminchew@lspower.com | Christina: 636:698:8443 | Ramya Nagarajan | RNagarajan@lspower.com | Ramya: 737-881-5008
DENTON | Primary & Secondary | Mark Zimmerer | Mark.Zimmerer@cityofdenton.com | Mark: 940 349 7169 | Cody Tenorio | Cody.Tenorio@cityofdenton.com | Cody: 940 349 7532
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | David Grubbs Kevin Sills | Dgrubbs@gpltexas.org; ksills@gpltexas.org | David: 972-205-2664 Kevin: 972-205-2603
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; BEC (Bandera); BBEC; CTEC; GVEC; NBU; SBEC; RGEC | Primary & Secondary | Dylan Preas | dylan.preas@lcra.org | Dylan: 512-578-4514 | Naved Khan | naved.khan@lcra.org | Naved: 512-578-4176
Lone Star | Primary & Secondary | Chenyan Guo | chenyan.guo@fpl.com | Chenyan: 561-304-5692 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Charles Saker | charles.saker@oncor.com | Charles: 214-743-6896 | Paul Bell | paul.bell@oncor.com | Paul: 214-743-6676
PEC | Primary & Secondary | Charles DeWitt | charles.dewitt@peci.com | Charles: 830-225-0673 | Joshua Rivers | joshua.rivers@peci.com | Joshua: 830-330-4192
Rayburn | Primary | Stephen Geiger | sgeiger@rayburnelectric.com | Stephen: 469-402-2112 | Scott Donham | Sdonham@rayburnelectric.com | Scott: 469-402-2024
Sharyland Utilities | Primary & Secondary | Brad Schwarz | bschwarz@huntpower.com | Brad: 512-289-7425 | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243
STEC | Primary & Secondary | Teddi Flessner Long Tran | tflessner@stec.org long.tran@stec.org | Teddi: 361 485 6119 Long: 361 485 6318 | Paul Person Loretta Gonzalez | pperson@stec.org; lgonzalez@stec.org; | Paul: 361 485 6151 Loretta: 956 377 7120
TMPA | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | Kevin Sills | Ksills@gpltexas.org | Kevin: 972-205-2603
TNMP | Primary & Secondary | Ross Cloninger | ross.cloninger@tnmp.com | Ross: 281-581-4733 | Xia, Tao Roberts, Vincent Gerety, Chris | Tao.Xia@tnmp.com; Vincent.Roberts@tnmp.com; Christopher.Gerety@tnmp.com; | Tao: 281-581-4764 Vincent:409-949-5608 Chris:409-949-5605
Wind Energy Texas Transmission (WETT) | Primary | Chris Ramirez | cramirez@wettllc.com | Chris: 737-218-4525 | Yang Zhang | yzhang@wettllc.com | Yang: 737-218-4542