## TX SET V5.0 Implementation
Tuesday, November 5, 2024
Time | Task | Entity
14:00 | 1st Market Conference Call - Confirm all MPs are ready to proceed with TX SET V5.0 implementation | All MPs
Wednesday, November 6, 2024
Time | Task | Entity
12:00 | CRs suspend sending 650_01 DNP Transactions - Pending DNPs will continue to be worked according to the DNP procedures | All CRs
17:00 | TDSPs will flush systems to cancel all pending 650 DNPs and send complete unexecutables to CRs | All TDSPs
Thursday, November 7, 2024
Time | Task | Entity
16:00 | 2nd Market Conference Call - Confirm DNPs are suspended; Roll call for TDSPs only | All MPs
Friday, November 8, 2024
Time | Task | Entity
NOTE: Friday November 8th will be treated as a TDSP Non-Business Day. Requested date for Move Ins, Move Outs and Switches must be for Monday, November 11, 2024 and beyond.
12:00 | CRs suspend sending 814 transactions to ERCOT (both EDI and through Retail portion of MIS). Requested date for Move Ins, Move Outs and Switches must be for Monday, November 11, 2024 and beyond. | All CRs
| CRs begin using Safety Net process as needed for submitting MVIs with a requested date of November 8 - November 9. Safety Net requests are for emergency lights out only. | All CRs
| CRs begin using Emergency Reconnect for non-payment spreadsheet process as needed for submitting Reconnects for Non-Payment | All CRs
| CRs suspend 814_PC transactions | All CRs
| CRs suspend 650_01 transactions | All CRs
| TDSPs suspend 650_04 transactions | All TDSPs
13:00 | TDSPs suspend 814 responses | All TDSPs
| CRs suspend 824 transactions | All CRs
| TDSPs suspend 814_PD transactions | All TDSPs
| TDSPs suspend 650_02 transactions | All TDSPs
| TDSPs to log MarkeTrak Issue with ERCOT for Initial County load file | All TDSPs
18:00 | 3rd Market Conference Call - MP Migration Status; Confirm Market Readiness | All MPs
Saturday, November 9, 2024
Time | Task | Entity
NOTE: Saturday November 9th will be treated as a TDSP Non-Business Day. Requested date for Move Ins, Move Outs and Switches must be for Monday, November 11, 2024 and beyond.
5:00 | TDSPs suspend 867s | All TDSPs
| TDSPs suspend 810_02 (810_03MC) transactions | All TDSPs
| CRs suspend 820_02 (820_03MC) transactions | All CRs
6:00 | 997s suspended for all transactions | All MPs
| TDSPs suspend LSE Files to ERCOT | All TDSPs
| TDSPs suspend 814_20 transactions | All TDSPs
| CRs use Safety Net process as needed for submitting MVIs with a requested date of November 8 - November 9. Safety Net requests are for emergency lights out only. | All CRs
| CRs use Emergency Reconnect for non-payment spreadsheet process as needed for submitting Reconnects for Non-Payment | All CRs
8:00 | ERCOT shuts down inbound and outbound processing and MarkeTrak | ERCOT
| ERCOT sends out System Shutdown email to market | ERCOT
9:00 | 4th Market Conference Call - ERCOT confirmation of transaction suspension. Update on transaction processing. | All MPs
18:00 | 5th Market Conference Call - MP Migration Status | All MPs
Sunday, November 10, 2024
Time | Task | Entity
10:00 | 6th Market Conference Call - MP Migration Status; Confirm Market Readiness | All MPs
17:00 | 7th Market Conference Call - MP Migration Status; Confirm Market Readiness | All MPs
Monday, November 11, 2024
Time | Task | Entity
10:00 | 8th Market Conference Call - MP Migration Status; | All MPs