## Wind Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 18INR0073 | Sweetwater 1 repower | Nolan | 2024-07-31 | 2002-10-23 | Wind | WT | 3 | 2024 | No
[6 empty] | 20INR0040 | Montgomery Ranch Wind | Foard | 2024-07-31 | 2022-03-22 | Wind | WT | 200.2 | 2024 | Yes
[6 empty] | 20INR0155 | Peyton Creek Wind II | Matagorda | 2024-12-03 | 2023-02-27 | Wind | WT | 241.2 | 2024 | Yes
[6 empty] | 24INR0627 | Champion Wind Repower | Nolan | 2024-12-20 | 2007-01-19 | Wind | WT | 0.31 | 2024 | Yes
[6 empty] | 24INR0632 | Cedro Hill Wind Repower | Webb | 2024-12-28 | 2009-09-09 | Wind | WT | 9.93 | 2024 | Yes
[6 empty] | 21INR0240 | La Casa Wind | Stephens | 2025-03-22 | 2023-09-07 | Wind | WT | 148.4 | 2025 | Yes
[6 empty] | 16INR0112 | Loma Pinta Wind | La Salle | 2025-03-31 | 2017-12-13 | Wind | WT | 197.01 | 2025 | No
[6 empty] | 20INR0217 | CAROL wind | Potter | 2025-04-17 | 2020-09-11 | Wind | WT | 165.42 | 2025 | Yes
[6 empty] | 22INR0517 | Ray Gulf Wind | Wharton | 2025-06-30 | 2022-05-13 | Wind | WT | 207 | 2025 | No
[6 empty] | 19INR0054 | Monte Cristo 1 Wind | Hidalgo | 2025-08-20 | 2023-05-09 | Wind | WT | 234.5 | 2025 | Yes
[6 empty] | 24INR0116 | Hart Wind 2 | Castro | 2025-09-01 | 2023-10-06 | Wind | WT | 166.38 | 2025 | No
[6 empty] | 19INR0022 | Monte Alto I | Willacy | 2025-09-30 | 2020-02-13 | Wind | WT | 141.5 | 2025 | Yes
[6 empty] | 19INR0023 | Monte Alto 2 Wind | Willacy | 2025-09-30 | 2022-03-22 | Wind | WT | 307.9 | 2025 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator
2024-04-20 | 39251.33 | 39251.33 | 0 | 0 | 0
2024-05-20 | 39251.33 | 39251.33 | 0 | 0 | 0
2024-06-20 | 39251.33 | 39251.33 | 0 | 0 | 0
2024-07-20 | 39454.53 | 39251.33 | 200.2 | 3 | 0
2024-08-20 | 39454.53 | 39251.33 | 200.2 | 3 | 0
2024-09-20 | 39454.53 | 39251.33 | 200.2 | 3 | 0
2024-10-20 | 39454.53 | 39251.33 | 200.2 | 3 | 0
2024-11-20 | 39454.53 | 39251.33 | 200.2 | 3 | 0
2024-12-20 | 39705.97 | 39251.33 | 451.64 | 3 | 0
2025-01-20 | 39705.97 | 39251.33 | 451.64 | 3 | 0
2025-02-20 | 39705.97 | 39251.33 | 451.64 | 3 | 0
2025-03-20 | 40051.38 | 39251.33 | 600.04 | 200.01 | 0
2025-04-20 | 40216.8 | 39251.33 | 765.46 | 200.01 | 0
2025-05-20 | 40216.8 | 39251.33 | 765.46 | 200.01 | 0
2025-06-20 | 40423.8 | 39251.33 | 765.46 | 407.01 | 0
2025-07-20 | 40423.8 | 39251.33 | 765.46 | 407.01 | 0
2025-08-20 | 40658.3 | 39251.33 | 999.96 | 407.01 | 0
2025-09-20 | 41274.08 | 39251.33 | 1449.36 | 573.39 | 0

## Solar Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 23INR0144 | Galactic Solar | Grayson | 2024-03-01 | 2022-08-12 | Solar | PV | 205.2 | 2024 | No
[6 empty] | 21INR0303 | Mandorla Solar | Milam | 2024-06-29 | 2022-09-19 | Solar | PV | 254 | 2024 | Yes
[6 empty] | 22INR0283 | Peregrine Solar | Goliad | 2024-07-01 | 2021-06-19 | Solar | PV | 301.3 | 2024 | Yes
[6 empty] | 22INR0354 | XE Murat [Adlong] Solar | Harris | 2024-07-26 | 2022-03-04 | Solar | PV | 60.36 | 2024 | Yes
[6 empty] | 21INR0353 | Big Elm Solar | Bell | 2024-08-09 | 2022-09-01 | Solar | PV | 201.02 | 2024 | Yes
[6 empty] | 23INR0385 | Camp Creek Solar SLF | Robertson | 2024-08-31 | 2023-07-15 | Solar | PV | 165.6 | 2024 | No
[6 empty] | 19INR0134 | Cottonwood Bayou Solar | Brazoria | 2024-09-07 | 2019-11-13 | Solar | PV | 351.4 | 2024 | Yes
[6 empty] | 19INR0155 | Morrow Lake Solar | Frio | 2024-09-16 | 2019-08-29 | Solar | PV | 201.1 | 2024 | Yes
[6 empty] | 20INR0248 | DAMAZO (Second Division) SOLAR | Brazoria | 2024-09-17 | 2020-10-14 | Solar | PV | 100.2 | 2024 | Yes
[6 empty] | 21INR0424 | Tierra Bonita Solar | Pecos | 2024-09-26 | 2022-09-08 | Solar | PV | 306.9 | 2024 | Yes
[6 empty] | 23INR0114 | True North Solar | Falls | 2024-09-30 | 2023-04-20 | Solar | PV | 238.8 | 2024 | Yes
[6 empty] | 23INR0180 | Jackalope Solar | San Patricio | 2024-10-31 | 2021-09-30 | Solar | PV | 155.68 | 2024 | Yes
[6 empty] | 21INR0368 | Eliza Solar | Kaufman | 2024-11-01 | 2022-08-04 | Solar | PV | 151.7 | 2024 | Yes
[6 empty] | 21INR0490 | Samson Solar 2 | Lamar | 2024-11-16 | 2020-08-27 | Solar | PV | 203 | 2024 | Yes
[6 empty] | 22INR0203 | Delilah Solar 2 | Lamar | 2024-11-16 | 2020-12-22 | Solar | PV | 317.58 | 2024 | Yes
[6 empty] | 23INR0089 | Donegal Solar | Dickens | 2024-11-30 | 2022-07-25 | Solar | PV | 204.2 | 2024 | No
[6 empty] | 20INR0216 | Starr Solar Ranch | Starr | 2024-12-01 | 2020-10-01 | Solar | PV | 136.73 | 2024 | Yes
[6 empty] | 23INR0084 | Lavaca Bay Solar | Matagorda | 2024-12-04 | 2022-06-15 | Solar | PV | 243.46 | 2024 | Yes
[6 empty] | 20INR0230 | Markum Solar | McLennan | 2024-12-18 | 2021-06-28 | Solar | PV | 161.54 | 2024 | Yes
[6 empty] | 24INR0208 | Eastbell Milam Solar II | Milam | 2024-12-20 | 2023-10-25 | Solar | PV | 150.6 | 2024 | Yes
[6 empty] | 24INR0023 | Compadre Solar | Hill | 2024-12-25 | 2022-11-12 | Solar | PV | 406.14 | 2024 | Yes
[6 empty] | 21INR0223 | Tulsita Solar | Goliad | 2024-12-31 | 2022-09-19 | Solar | PV | 256.2 | 2024 | Yes
[6 empty] | 22INR0356 | Jungmann Solar | Milam | 2024-12-31 | 2022-02-15 | Solar | PV | 40.21 | 2024 | No
[6 empty] | 22INR0511 | Gransolar Texas One | Milam | 2024-12-31 | 2022-06-13 | Solar | PV | 50 | 2024 | Yes
[6 empty] | 23INR0021 | Hornet Solar | Swisher | 2024-12-31 | 2021-12-06 | Solar | PV | 602.37 | 2024 | Yes
[6 empty] | 23INR0044 | Parliament Solar | Waller | 2024-12-31 | 2022-05-26 | Solar | PV | 484.56 | 2024 | Yes
[6 empty] | 23INR0070 | Chillingham Solar | Bell | 2024-12-31 | 2022-02-04 | Solar | PV | 352.39 | 2024 | Yes
[6 empty] | 24INR0477 | Barrett Solar | Rains | 2024-12-31 | 2023-10-05 | Solar | PV | 127.5 | 2024 | No
[6 empty] | 23INR0111 | GULF STAR SOLAR | Wharton | 2025-01-02 | 2021-10-01 | Solar | PV | 451.63 | 2025 | Yes
[6 empty] | 23INR0150 | Cradle Solar | Brazoria | 2025-01-02 | 2023-03-15 | Solar | PV | 225 | 2025 | Yes
[6 empty] | 23INR0007 | Outpost Solar | Webb | 2025-01-07 | 2022-01-11 | Solar | PV | 517.3 | 2025 | Yes
[6 empty] | 23INR0054 | Tanglewood Solar | Brazoria | 2025-01-16 | 2022-11-01 | Solar | PV | 250.96 | 2025 | Yes
[6 empty] | 21INR0379 | Ash Creek Solar | Hill | 2025-01-31 | 2022-11-11 | Solar | PV | 417.74 | 2025 | Yes
[6 empty] | 24INR0421 | Swift Air Solar | Ector | 2025-02-12 | 2024-04-30 | Solar | PV | 148.84 | 2025 | No
[6 empty] | 22INR0455 | Blue Sky Sol | Crockett | 2025-02-15 | 2022-02-01 | Solar | PV | 101.2 | 2025 | Yes
[6 empty] | 21INR0220 | Maleza Solar | Wharton | 2025-03-01 | 2021-01-27 | Solar | PV | 254.94 | 2025 | Yes
[6 empty] | 21INR0256 | Amsterdam Solar | Brazoria | 2025-03-01 | 2022-02-17 | Solar | PV | 509.88 | 2025 | No
[6 empty] | 21INR0391 | Grandslam Solar | Atascosa | 2025-03-01 | 2021-01-29 | Solar | PV | 121.89 | 2025 | No
[6 empty] | 20INR0086 | Arroyo Solar | Cameron | 2025-03-02 | 2021-09-28 | Solar | PV | 180 | 2025 | Yes
[6 empty] | 20INR0208 | Signal Solar | Hunt | 2025-03-15 | 2020-10-23 | Solar | PV | 51.79 | 2025 | Yes
[6 empty] | 16INR0049 | Nazareth Solar | Castro | 2025-03-24 | 2023-06-07 | Solar | PV | 204 | 2025 | Yes
[6 empty] | 24INR0093 | Oriana Solar | Victoria | 2025-04-06 | 2023-02-27 | Solar | PV | 181 | 2025 | Yes
[6 empty] | 21INR0393 | Orange Grove Solar | Jim Wells | 2025-04-30 | 2022-06-08 | Solar | PV | 130.6 | 2025 | Yes
[6 empty] | 24INR0031 | Stoneridge Solar | Milam | 2025-04-30 | 2023-05-15 | Solar | PV | 201.6 | 2025 | Yes
[6 empty] | 23INR0035 | Starling Solar | Gonzales | 2025-05-09 | 2021-12-03 | Solar | PV | 123 | 2025 | Yes
[6 empty] | 20INR0091 | Fagus Solar Park SLF | Childress | 2025-05-15 | 2019-02-21 | Solar | PV | 519.46 | 2025 | Yes
[6 empty] | 23INR0045 | GP Solar | Van Zandt | 2025-05-15 | 2021-12-29 | Solar | PV | 121.97 | 2025 | Yes
[6 empty] | 19INR0110 | Azalea Springs Solar | Angelina | 2025-05-31 | 2023-09-14 | Solar | PV | 181 | 2025 | Yes
[6 empty] | 23INR0047 | Charger Solar | Refugio | 2025-05-31 | 2021-06-05 | Solar | PV | 406.77 | 2025 | Yes
[6 empty] | 23INR0058 | Erin Solar | Wharton | 2025-05-31 | 2023-03-22 | Solar | PV | 202.5 | 2025 | No
[6 empty] | 23INR0091 | Cascade Solar | Brazoria | 2025-06-01 | 2023-04-17 | Solar | PV | 254.2 | 2025 | Yes
[6 empty] | 24INR0070 | Sypert Branch Solar Project | Milam | 2025-06-01 | 2023-10-12 | Solar | PV | 261.15 | 2025 | Yes
[6 empty] | 24INR0075 | Blue Bird Solar | Johnson | 2025-06-01 | 2024-01-18 | Solar | PV | 1004 | 2025 | No
[6 empty] | 24INR0166 | Stillhouse Solar | Bell | 2025-06-01 | 2023-06-07 | Solar | PV | 212.51 | 2025 | Yes
[6 empty] | 23INR0160 | Grimes County Solar | Grimes | 2025-06-15 | 2022-06-23 | Solar | PV | 210 | 2025 | Yes
[6 empty] | 20INR0203 | Pine Forest Solar | Hopkins | 2025-06-29 | 2020-07-29 | Solar | PV | 305 | 2025 | No
[6 empty] | 24INR0038 | SP Jaguar Solar | McLennan | 2025-06-30 | 2022-09-12 | Solar | PV | 300 | 2025 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator | 21INR0341 | Space City Solar | Wharton | 2025-07-01 | 2021-01-06 | Solar | PV | 609.74 | 2025 | Yes
2024-04-20 | 24495.14 | 24289.94 | 0 | 205.2 | 0 | 21INR0344 | Lunis Creek Solar SLF | Jackson | 2025-07-01 | 2021-10-29 | Solar | PV | 617.12 | 2025 | Yes
2024-05-20 | 24495.14 | 24289.94 | 0 | 205.2 | 0 | 23INR0118 | Blevins Solar | Falls | 2025-07-01 | 2023-06-17 | Solar | PV | 271.6 | 2025 | Yes
2024-06-20 | 24749.14 | 24289.94 | 254 | 205.2 | 0 | 25INR0052 | SanPat Solar 1 | San Patricio | 2025-07-01 | 2023-10-18 | Solar | PV | 256.23 | 2025 | Yes
2024-07-20 | 25110.8 | 24289.94 | 615.66 | 205.2 | 0 | 25INR0081 | SanPat Solar 2 | San Patricio | 2025-07-01 | 2023-10-18 | Solar | PV | 308.88 | 2025 | Yes
2024-08-20 | 25477.42 | 24289.94 | 816.68 | 370.8 | 0 | 23INR0040 | Dori BQ Solar | Harris | 2025-07-04 | 2022-12-01 | Solar | PV | 50.42 | 2025 | No
2024-09-20 | 26675.82 | 24289.94 | 2015.08 | 370.8 | 0 | 23INR0225 | MRG GOODY SOLAR | Lamar | 2025-07-07 | 2023-11-07 | Solar | PV | 171.72 | 2025 | No
2024-10-20 | 26831.5 | 24289.94 | 2170.76 | 370.8 | 0 | 20INR0255 | Renegade Project | Deaf Smith | 2025-07-31 | 2021-01-04 | Solar | PV | 515.66 | 2025 | Yes
2024-11-20 | 27707.98 | 24289.94 | 2843.04 | 575 | 0 | 24INR0141 | Gaia Solar | Navarro | 2025-07-31 | 2023-11-08 | Solar | PV | 152.65 | 2025 | Yes
2024-12-20 | 30719.68 | 24289.94 | 5687.03 | 742.71 | 0 | 20INR0222 | Tyson Nick Solar | Lamar | 2025-08-01 | 2020-08-28 | Solar | PV | 90.5 | 2025 | Yes
2025-01-20 | 32582.31 | 24289.94 | 7549.66 | 742.71 | 0 | 21INR0268 | Greyhound Solar | Ector | 2025-08-08 | 2022-01-15 | Solar | PV | 608.7 | 2025 | No
2025-02-20 | 32832.35 | 24289.94 | 7650.86 | 891.55 | 0 | 23INR0344 | XE Hermes Solar | Bell | 2025-08-25 | 2023-11-08 | Solar | PV | 100.36 | 2025 | Yes
2025-03-20 | 34154.85 | 24289.94 | 8341.59 | 1523.32 | 0 | 23INR0349 | Tokio Solar | McLennan | 2025-08-25 | 2023-11-06 | Solar | PV | 175.72 | 2025 | Yes
2025-04-20 | 34668.05 | 24289.94 | 8854.79 | 1523.32 | 0 | 23INR0056 | Caliche Mound Solar | Deaf Smith | 2025-08-28 | 2023-10-12 | Solar | PV | 408.21 | 2025 | Yes
2025-05-20 | 36222.75 | 24289.94 | 10206.99 | 1725.82 | 0 | 24INR0139 | Midpoint Solar | Hill | 2025-08-30 | 2023-10-31 | Solar | PV | 103.8 | 2025 | Yes
2025-06-20 | 38769.61 | 24289.94 | 11444.85 | 3034.82 | 0 | 24INR0303 | Erika Solar | Kaufman | 2025-08-31 | 2023-10-12 | Solar | PV | 203.5 | 2025 | No
2025-07-20 | 41723.63 | 24289.94 | 14176.73 | 3256.96 | 0 | 23INR0061 | Noria Solar DCC | Nueces | 2025-09-01 | 2022-10-12 | Solar | PV | 145 | 2025 | Yes
2025-08-20 | 43414.42 | 24289.94 | 15055.32 | 4069.16 | 0 | 23INR0367 | Fewell Solar | Limestone | 2025-09-09 | 2023-08-18 | Solar | PV | 203.5 | 2025 | Yes
2025-09-20 | 44576.08 | 24289.94 | 16066.14 | 4220 | 0 | 22INR0454 | DR Solar | Culberson | 2025-09-15 | 2022-02-07 | Solar | PV | 46.02 | 2025 | Yes
[6 empty] | 24INR0042 | Yaupon Solar SLF | Milam | 2025-09-17 | 2023-09-28 | Solar | PV | 204.08 | 2025 | Yes
[6 empty] | 22INR0211 | Schoolhouse Solar | Lee | 2025-09-22 | 2021-07-11 | Solar | PV | 150.84 | 2025 | No
[6 empty] | 20INR0236 | New Hickory Solar | Jackson | 2025-09-30 | 2020-06-30 | Solar | PV | 206 | 2025 | Yes
[6 empty] | 23INR0235 | Hoyte Solar | Milam | 2025-09-30 | 2022-10-14 | Solar | PV | 206.22 | 2025 | Yes

## Battery Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 22INR0325 | Dickens BESS | Dickens | 2024-05-30 | 2020-11-02 | Battery | BA | 200.8 | 2024 | Yes
[6 empty] | 24INR0609 | Rodeo Ranch Energy Storage Repowering | Reeves | 2024-05-30 | 2022-02-01 | Battery | BA | 10 | 2024 | Yes
[6 empty] | 22INR0490 | Callisto I Energy Center | Harris | 2024-06-01 | 2022-04-07 | Battery | BA | 206.4 | 2024 | Yes
[6 empty] | 23INR0470 | BoCo BESS | Borden | 2024-06-10 | 2022-12-09 | Battery | BA | 155.48 | 2024 | Yes
[6 empty] | 23INR0460 | GULF STAR STORAGE | Wharton | 2024-06-25 | 2023-03-23 | Battery | BA | 305.48 | 2024 | Yes
[6 empty] | 22INR0372 | Hydra BESS | Pecos | 2024-07-01 | 2021-05-08 | Battery | BA | 200.8 | 2024 | Yes
[6 empty] | 23INR0072 | Tortolas BESS | Brazoria | 2024-07-01 | 2021-07-15 | Battery | BA | 50.3 | 2024 | Yes
[6 empty] | 24INR0100 | Sheep Creek Storage | Callahan | 2024-07-01 | 2023-12-21 | Battery | BA | 142.1 | 2024 | Yes
[6 empty] | 22INR0327 | Hummingbird Storage | Denton | 2024-07-10 | 2022-02-23 | Battery | BA | 103.8 | 2024 | Yes
[6 empty] | 22INR0338 | Limousin Oak Storage | Grimes | 2024-07-10 | 2022-04-01 | Battery | BA | 104.62 | 2024 | Yes
[6 empty] | 22INR0322 | Paleo BESS | Hale | 2024-07-30 | 2021-02-05 | Battery | BA | 200.8 | 2024 | Yes
[6 empty] | 23INR0403 | Connolly Storage | Wise | 2024-08-15 | 2023-02-27 | Battery | BA | 125.36 | 2024 | Yes
[6 empty] | 24INR0273 | Al Pastor BESS | Dawson | 2024-08-16 | 2023-01-24 | Battery | BA | 103.1 | 2024 | Yes
[6 empty] | 23INR0423 | Camp Creek Storage SLF | Robertson | 2024-08-31 | 2023-07-15 | Battery | BA | 0 | 2024 | No
[6 empty] | 24INR0312 | Wigeon Whistle BESS | Collin | 2024-09-01 | 2022-12-08 | Battery | BA | 122.9 | 2024 | Yes
[6 empty] | 23INR0166 | Great Kiskadee Storage | Hidalgo | 2024-09-06 | 2022-06-30 | Battery | BA | 103.05 | 2024 | Yes
[6 empty] | 24INR0147 | Holy ESS | Harris | 2024-09-21 | 2022-07-29 | Battery | BA | 209.32 | 2024 | Yes
[6 empty] | 22INR0260 | Eliza Storage | Kaufman | 2024-09-27 | 2022-08-04 | Battery | BA | 100.4 | 2024 | Yes
[6 empty] | 24INR0629 | Jade Storage SLF | Scurry | 2024-09-30 | 2024-03-28 | Battery | BA | 0 | 2024 | Yes
[6 empty] | 24INR0630 | Andromeda Storage SLF | Scurry | 2024-09-30 | 2024-04-18 | Battery | BA | 0 | 2024 | Yes
[6 empty] | 20INR0246 | Ryan Energy Storage | Coryell | 2024-10-21 | 2021-02-18 | Battery | BA | 50 | 2024 | Yes
[6 empty] | 22INR0328 | Inertia BESS | Haskell | 2024-10-31 | 2021-05-04 | Battery | BA | 13 | 2024 | Yes
[6 empty] | 25INR0328 | Longbow BESS | Brazoria | 2024-11-13 | 2023-07-18 | Battery | BA | 180.8 | 2024 | Yes
[6 empty] | 22INR0349 | Antlia BESS | Val Verde | 2024-12-01 | 2021-06-05 | Battery | BA | 72.38 | 2024 | Yes
[6 empty] | 22INR0353 | Carina BESS | Nueces | 2024-12-01 | 2021-08-03 | Battery | BA | 154.11 | 2024 | Yes
[6 empty] | 22INR0368 | Padua Grid BESS | Bexar | 2024-12-01 | 2021-11-16 | Battery | BA | 51.1 | 2024 | Yes
[6 empty] | 22INR0388 | Cachi BESS | Guadalupe | 2024-12-01 | 2021-06-11 | Battery | BA | 205.46 | 2024 | No
[6 empty] | 23INR0290 | Zeya BESS | Galveston | 2024-12-01 | 2023-01-20 | Battery | BA | 255.33 | 2024 | Yes
[6 empty] | 24INR0329 | XE Murat Storage | Harris | 2024-12-14 | 2023-11-01 | Battery | BA | 60.14 | 2024 | No
[6 empty] | 24INR0405 | Crowned Heron BESS | Fort Bend | 2024-12-15 | 2023-06-26 | Battery | BA | 150 | 2024 | Yes
[6 empty] | 22INR0549 | Tanzanite Storage | Henderson | 2024-12-31 | 2022-07-15 | Battery | BA | 265.8 | 2024 | Yes
[6 empty] | 23INR0419 | SOHO BESS | Brazoria | 2025-01-01 | 2022-12-01 | Battery | BA | 206.32 | 2025 | Yes
[6 empty] | 25INR0162 | SOHO II BESS | Brazoria | 2025-01-01 | 2023-04-15 | Battery | BA | 206.32 | 2025 | Yes
[6 empty] | 24INR0265 | Ironman BESS | Brazoria | 2025-01-13 | 2022-12-15 | Battery | BA | 308.4 | 2025 | Yes
[6 empty] | 22INR0468 | Lower Rio BESS | Hidalgo | 2025-01-15 | 2023-07-10 | Battery | BA | 60.45 | 2025 | Yes
[6 empty] | 23INR0103 | Burksol BESS | Dickens | 2025-01-24 | 2022-11-17 | Battery | BA | 103.27 | 2025 | Yes
[6 empty] | 23INR0195 | Desert Willow BESS | Ellis | 2025-02-02 | 2023-05-15 | Battery | BA | 154.4 | 2025 | Yes
[6 empty] | 23INR0299 | Anole BESS | Dallas | 2025-02-10 | 2023-04-26 | Battery | BA | 247.1 | 2025 | Yes
[6 empty] | 22INR0417 | Amsterdam Storage | Brazoria | 2025-03-01 | 2022-04-14 | Battery | BA | 201.13 | 2025 | No
[6 empty] | 24INR0306 | Arroyo Storage | Cameron | 2025-03-02 | 2022-08-10 | Battery | BA | 183.76 | 2025 | No
[6 empty] | 22INR0554 | Platinum Storage | Fannin | 2025-03-03 | 2022-11-17 | Battery | BA | 309.53 | 2025 | No
[6 empty] | 23INR0381 | Bexar ESS | Bexar | 2025-03-15 | 2023-07-31 | Battery | BA | 102.6 | 2025 | Yes
[6 empty] | 23INR0219 | Dogfish BESS | Pecos | 2025-04-16 | 2023-06-01 | Battery | BA | 75 | 2025 | Yes
[6 empty] | 25INR0300 | Wizard BESS | Galveston | 2025-04-29 | 2023-08-21 | Battery | BA | 150.82 | 2025 | No
[6 empty] | 23INR0331 | Orange Grove BESS | Jim Wells | 2025-04-30 | 2022-11-30 | Battery | BA | 61.39 | 2025 | Yes
[6 empty] | 23INR0079 | Chillingham Storage | Bell | 2025-05-02 | 2022-02-04 | Battery | BA | 153.93 | 2025 | Yes
[6 empty] | 22INR0540 | Walstrom BESS | Austin | 2025-05-05 | 2023-06-30 | Battery | BA | 200 | 2025 | Yes
[6 empty] | 23INR0354 | Bordertown BESS | Starr | 2025-05-10 | 2022-10-12 | Battery | BA | 106.15 | 2025 | Yes
[6 empty] | 24INR0295 | Lucky Bluff BESS | Erath | 2025-05-31 | 2023-11-08 | Battery | BA | 100.8 | 2025 | Yes
[6 empty] | 24INR0315 | Black Springs BESS | Palo Pinto | 2025-05-31 | 2023-10-18 | Battery | BA | 120.96 | 2025 | Yes
[6 empty] | 23INR0350 | Fort Duncan BESS | Maverick | 2025-06-01 | 2022-12-12 | Battery | BA | 106.15 | 2025 | Yes
[6 empty] | 23INR0358 | Castor BESS | Brazoria | 2025-06-01 | 2023-09-15 | Battery | BA | 205.39 | 2025 | Yes
[6 empty] | 23INR0425 | Coneflower Storage Project | Chambers | 2025-06-01 | 2024-03-25 | Battery | BA | 170 | 2025 | Yes
[6 empty] | 24INR0128 | Desna BESS | Brazoria | 2025-06-01 | 2023-09-15 | Battery | BA | 205.46 | 2025 | Yes
[6 empty] | 24INR0281 | Red Egret BESS | Galveston | 2025-06-01 | 2023-06-07 | Battery | BA | 310.58 | 2025 | Yes
[6 empty] | 25INR0467 | Bocanova BESS | Brazoria | 2025-06-01 | 2023-11-14 | Battery | BA | 300.92 | 2025 | Yes
[6 empty] | 24INR0460 | Evelyn Battery Energy Storage System | Galveston | 2025-06-10 | 2023-09-14 | Battery | BA | 221.3 | 2025 | No
[6 empty] | 23INR0401 | Headcamp | Pecos | 2025-06-16 | 2024-02-16 | Battery | BA | 150 | 2025 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator | 22INR0526 | Pine Forest BESS | Hopkins | 2025-06-29 | 2024-04-10 | Battery | BA | 421 | 2025 | No
2024-04-20 | 6534.73 | 6524.78 | 0 | 0 | 9.95 | 21INR0492 | Stockyard Grid Batt | Tarrant | 2025-06-30 | 2022-10-26 | Battery | BA | 150.6 | 2025 | Yes
2024-05-20 | 6775.19 | 6524.78 | 210.8 | 0 | 39.61 | 24INR0039 | SP Jaguar BESS | McLennan | 2025-06-30 | 2022-09-12 | Battery | BA | 300 | 2025 | Yes
2024-06-20 | 7462.35 | 6524.78 | 878.16 | 0 | 59.41 | 23INR0119 | Blevins Storage | Falls | 2025-07-01 | 2023-06-17 | Battery | BA | 181.3 | 2025 | Yes
2024-07-20 | 8284.57 | 6524.78 | 1680.58 | 0 | 79.21 | 24INR0196 | Dori BQ BESS | Harris | 2025-07-04 | 2023-05-31 | Battery | BA | 154 | 2025 | No
2024-08-20 | 8552.43 | 6524.78 | 1909.04 | 0 | 118.61 | 21INR0443 | Cottonwood Bayou Storage | Brazoria | 2025-07-07 | 2022-03-18 | Battery | BA | 153.03 | 2025 | Yes
2024-09-20 | 9112.76 | 6524.78 | 2444.71 | 0 | 143.27 | 25INR0262 | Shepard Energy Storage | Galveston | 2025-07-09 | 2024-01-17 | Battery | BA | 263.2 | 2025 | Yes
2024-10-20 | 9185.75 | 6524.78 | 2507.71 | 0 | 153.26 | 21INR0517 | Tidwell Prairie Storage 1 | Robertson | 2025-07-15 | 2022-11-03 | Battery | BA | 200 | 2025 | Yes
2024-11-20 | 9366.55 | 6524.78 | 2688.51 | 0 | 153.26 | 22INR0555 | TE Smith Storage | Rockwall | 2025-07-15 | 2023-11-08 | Battery | BA | 125.36 | 2025 | Yes
2024-12-20 | 10620.7 | 6524.78 | 3637.23 | 265.6 | 193.09 | 24INR0294 | Citrus Flatts BESS | Cameron | 2025-07-15 | 2023-09-08 | Battery | BA | 100.8 | 2025 | Yes
2025-01-20 | 11515.36 | 6524.78 | 4521.99 | 265.6 | 202.99 | 25INR0421 | Aldrin 138 BESS | Brazoria | 2025-07-15 | 2024-02-26 | Battery | BA | 207 | 2025 | No
2025-02-20 | 11916.86 | 6524.78 | 4923.49 | 265.6 | 202.99 | 23INR0343 | Guajillo Energy Storage | Webb | 2025-07-30 | 2021-12-21 | Battery | BA | 204.8 | 2025 | Yes
2025-03-20 | 12713.88 | 6524.78 | 5026.09 | 960.02 | 202.99 | 23INR0494 | Cartwheel BESS 1 | Hopkins | 2025-07-31 | 2023-11-10 | Battery | BA | 156.91 | 2025 | Yes
2025-04-20 | 13001.09 | 6524.78 | 5162.48 | 1110.84 | 202.99 | 24INR0140 | Gaia Storage | Navarro | 2025-07-31 | 2023-11-08 | Battery | BA | 76.83 | 2025 | Yes
2025-05-20 | 13682.93 | 6524.78 | 5844.32 | 1110.84 | 202.99 | 24INR0365 | XE Hermes Storage | Bell | 2025-08-25 | 2023-11-08 | Battery | BA | 100.42 | 2025 | Yes
2025-06-20 | 16224.33 | 6524.78 | 7743.42 | 1753.14 | 202.99 | 24INR0302 | Pintail Pass BESS | San Patricio | 2025-08-27 | 2023-05-16 | Battery | BA | 207.18 | 2025 | No
2025-07-20 | 18047.56 | 6524.78 | 9205.65 | 2114.14 | 202.99 | 24INR0138 | Midpoint Storage | Hill | 2025-08-30 | 2023-10-31 | Battery | BA | 52.24 | 2025 | Yes
2025-08-20 | 18407.4 | 6524.78 | 9358.31 | 2321.32 | 202.99 | 23INR0062 | Noria Storage | Nueces | 2025-09-01 | 2022-10-12 | Battery | BA | 75 | 2025 | Yes
2025-09-20 | 19190.03 | 6524.78 | 10039.73 | 2422.53 | 202.99 | 25INR0208 | Iron Belt Energy Storage | Borden | 2025-09-01 | 2023-01-16 | Battery | BA | 401.9 | 2025 | Yes
[6 empty] | 25INR0389 | Stoneridge BESS | Milam | 2025-09-01 | 2024-04-19 | Battery | BA | 101.9 | 2025 | Yes
[6 empty] | 24INR0169 | Yaupon Storage SLF | Milam | 2025-09-17 | 2023-09-28 | Battery | BA | 0 | 2025 | No
[6 empty] | 23INR0351 | Seven Flags BESS | Webb | 2025-09-30 | 2023-05-19 | Battery | BA | 102.62 | 2025 | Yes
[6 empty] | 23INR0364 | Tierra Seca BESS | Val Verde | 2025-09-30 | 2023-05-18 | Battery | BA | 101.21 | 2025 | No
[6 empty] | Small Generators | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 22INR0590 | Muenster BESS | Cooke | 2024-12-31 | 2023-07-12 | Battery | BA | 9.9 | 2024 | No
[6 empty] | 22INR0596 | Grizzly Ridge BESS | Hamilton | 2023-05-31 | 2021-10-18 | Battery | BA | 9.95 | 2023 | Yes
[6 empty] | 22INR0602 | Regis Palacios BESS | Matagorda | 2024-07-16 | 2022-10-07 | Battery | BA | 9.9 | 2024 | Yes
[6 empty] | 23INR0498 | Moore Field BESS 2 | Hidalgo | 2024-05-24 | 2022-10-07 | Battery | BA | 9.8 | 2024 | Yes
[6 empty] | 23INR0499 | Laureles BESS | Cameron | 2024-08-15 | 2023-02-16 | Battery | BA | 9.8 | 2024 | Yes
[6 empty] | 23INR0500 | Fort Mason BESS | Mason | 2024-09-30 | 2023-01-10 | Battery | BA | 9.8 | 2024 | Yes
[6 empty] | 23INR0523 | Damon BESS | Brazoria | 2024-09-03 | 2022-10-18 | Battery | BA | 4.98 | 2024 | Yes
[6 empty] | 23INR0539 | Gregory BESS | San Patricio | 2024-06-28 | 2022-10-07 | Battery | BA | 9.9 | 2024 | Yes
[6 empty] | 23INR0541 | Telview BESS | Fort Bend | 2024-05-31 | 2023-07-10 | Battery | BA | 9.96 | 2024 | Yes
[6 empty] | 23INR0556 | IEP Orchard BESS | Fort Bend | 2024-10-02 | 2023-08-09 | Battery | BA | 9.99 | 2024 | Yes
[6 empty] | 23INR0569 | Weil Tract BESS | Nueces | 2024-05-15 | 2022-12-21 | Battery | BA | 9.9 | 2024 | Yes
[6 empty] | 23INR0603 | Damon BESS 2 | Brazoria | 2024-12-02 | 2023-10-06 | Battery | BA | 9.99 | 2024 | Yes
[6 empty] | 23INR0617 | Hidden Lakes BESS | Galveston | 2025-01-22 | 2024-02-07 | Battery | BA | 9.9 | 2025 | Yes
[6 empty] | 23INR0620 | Falfurrias BESS | Brooks | 2024-07-10 | 2023-04-10 | Battery | BA | 9.9 | 2024 | Yes
[6 empty] | 23INR0807 | Mayberry II BESS | Hidalgo | 2024-12-07 | 2023-05-17 | Battery | BA | 9.95 | 2024 | Yes
[6 empty] | 24INR0499 | Medina Lake BESS | Bandera | 2024-08-31 | 2023-01-18 | Battery | BA | 9.8 | 2024 | No
[6 empty] | 24INR0588 | Cisco BESS | Eastland | 2024-06-14 | 2023-07-19 | Battery | BA | 9.9 | 2024 | No
[6 empty] | 24INR0610 | Century BESS | Tarrant | 2024-09-27 | 2023-04-14 | Battery | BA | 9.88 | 2024 | Yes
[6 empty] | 24INR0614 | Russek Street BESS | Reagan | 2024-08-02 | 2023-08-03 | Battery | BA | 9.9 | 2024 | Yes
[6 empty] | 24INR0615 | Pavlov BESS | Matagorda | 2024-08-02 | 2023-08-21 | Battery | BA | 9.9 | 2024 | No
[6 empty] | 24INR0688 | SANDLAKE BESS | Reeves | 2024-12-06 | 2024-03-26 | Battery | BA | 9.99 | 2024 | Yes

## Gas-Combined Cycle Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 22INR0533 | Temple Generation I Repower | Bell | 2022-06-09 | 2012-06-21 | Gas | CC | 67 | 2022 | Yes
[6 empty] | 23INR0524 | Temple II Repower | Bell | 2023-10-15 | 2012-06-21 | Gas | CC | 0 | 2023 | Yes
[6 empty] | 20INR0286 | Wise County Power Repower (CT1, CT2) | Wise | 2024-06-30 | 2001-03-19 | Gas | CC | 21 | 2024 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator
2024-04-20 | 43776.709 | 43709.709 | 67 | 0 | 0
2024-05-20 | 43776.709 | 43709.709 | 67 | 0 | 0
2024-06-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-07-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-08-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-09-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-10-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-11-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2024-12-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-01-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-02-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-03-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-04-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-05-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-06-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-07-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-08-20 | 43797.709 | 43709.709 | 88 | 0 | 0
2025-09-20 | 43797.709 | 43709.709 | 88 | 0 | 0

## Gas-Other Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 24INR0605 | TEXAS GULF SULPHUR REPOWER | Wharton | 2024-06-25 | 2022-03-01 | Gas | GT | 16.1 | 2024 | Yes
[7 empty] | 23INR0339 | Remy Jade Power Station | Harris | 2024-06-30 | 2022-08-01 | Gas | GT | 408 | 2024 | Yes
[7 empty] | 23INR0506 | Beachwood II Power Station | Brazoria | 2024-08-01 | 2022-08-01 | Gas | GT | 102 | 2024 | Yes
[7 empty] | 24INR0382 | Remy Jade II Power Station | Harris | 2025-07-30 | 2022-08-01 | Gas | GT | 102 | 2025 | No
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator
2024-04-20 | 24407.94 | 24407.94 | 0 | 0 | 0 | 0
2024-05-20 | 24411.54 | 24407.94 | 0 | 0 | 3.6 | 0
2024-06-20 | 24848.19 | 24407.94 | 424.1 | 0 | 16.15 | 0
2024-07-20 | 24848.19 | 24407.94 | 424.1 | 0 | 16.15 | 0
2024-08-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2024-09-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2024-10-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2024-11-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2024-12-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2025-01-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2025-02-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2025-03-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2025-04-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2025-05-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2025-06-20 | 24950.19 | 24407.94 | 526.1 | 0 | 16.15 | 0
2025-07-20 | 25052.19 | 24407.94 | 526.1 | 102 | 16.15 | 0
2025-08-20 | 25052.19 | 24407.94 | 526.1 | 102 | 16.15 | 0
2025-09-20 | 25052.19 | 24407.94 | 526.1 | 102 | 16.15 | 0