|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MarkeTrak Transition Plan November 2024 | | | |  | | | |
|  | | | |  | | | |
| Sunday | Monday | Tuesday | Wednesday | | Thursday | Friday | Saturday | |
|  |  |  |  | |  | 1 | 2 | |
|  |  |  |  | |  | **Last Day for TDSP “Ready to Receive”** |  | |
| 3 | 4 | 5 | 6 | | 7 | 8 | 9 | |
|  | **REPs to submit BDMVIs** |  |  | |  | **TDSP Operational Holiday**  12:00PM PM | **TDSP Operational Holiday** | |
| 10 | 11 | 12 | 13 | | 14 | 15 | 16 | |
| **TX SET 5.0 Go LIVE** | **MTs “sent to TDSP” without BDMVI will be returned to REPs to follow new workflow** |  |  | |  |  |  | |
| 21 | 22 | 23 | 24 | | 25 | 26 | 27 | |
|  |  |  |  | |  |  |  | |
| 28 | 29 | 30 | 31 | |  |  |  | |
|  |  |  |  | |  |  |  | |
|  |  |  |  | |  |  |  | |
|  |  |  |  | |  |  |  | |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| FINAL Transition Plan TX SET V5.0  November 2024 | | | | | | |
| Tuesday  **November 5th** | Wednesday  **November 6th** | Thursday  **November 7th** | Friday  **November 8th** | Saturday  **November 9th** | Sunday  **November 10th** | Monday  **November 11th** |
| **2:00 PM:** **Market Conference Call**  *Confirm all MPs are ready to proceed with TX SET V5.0 implementation*  **Required MP participation** | **12:00 PM**: CRs suspend sending 650\_01 DNPs – *any pending DNPs will be worked per DNP procedures*  **5:00 PM:** TDSPs to cancel all pending 650\_01 DNPs – *TDSPs will complete unexecutable* | **4:00 PM: Market Conference Call**  *Confirm all DNPs are suspended*  **Required TDSP participation** | **12:00 PM:** CRs suspend sending all 814 transactions to ERCOT (EDI and MIS)  CRs begin using Safety Net process for MVIs with requested dates of 11/8 and 11/9 and Reconnects for non-pay  CRs suspend 814PCs  CRs suspend all 650\_01s  TDSPs suspend 650\_04s  TDSPs suspend 814\_20s  **1:00 PM:** TDSPs suspend 867s and 814 responses  CRs suspend 824s  TDSPs suspend 814PDs  TDSPs suspend 650\_02s  TDSPs submit MarkeTrak to ERCOT with initial County load file  **2:00 PM**: **Market Conference Call**  *ERCOT confirms all transaction suspension & processing*  **4:00 PM:** TDSPs suspend 810\_02s (810\_03MCs)  CRs suspend 820\_02 (820\_03MCs)  All 997s suspended  MarkeTrak processing suspended  ERCOT email to market of system shut down | **12:00 PM**: **Market Conference Call**  *MP migration status*  **Required MP participation**  **6:00 PM: Market Conference Call**  *MP migration status*  **Required MP participation** | **10:00 AM**: **Market Conference Call**  *MP migration status*  *Confirm market readiness*  **Required MP participation**  **5:00 PM: Market Conference Call**  *MP migration status*  *Confirm market readiness*  **Required MP participation** | **10:00 AM**: **Market Conference Call**  *MP migration status*  **Required MP participation** |