## Sheet1
Market Coordination Meeting (MCT) and Texas SET Meeting Notes / Action Items
2024-02-13
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes January, 2023--MCT / TX SET
| No changes were made to the notes. | The Vice Chair will have these posted to the February meeting page.
ERCOT Updates
Market Test Flight 0224 | ERCOT presented the flight update.
MCT Business Requirements Review – Mobile Generation | ERCOT reviewed the edits made to the Texas SET 5.0 Business Requirements document to accoromdate the Mobile Generation requirements. The document now provides references to the applicable RMGRR's and Texas SET change controls.
County Name Market Update Discussion | Centerpoint Energy brought up the topic of needing to clarify how the county update will take place. The group determined verbiage was needed to specify ALL ESIIDs will be updated, Active or De-Energized/Rep of Record or Not. The TDSPs will follow up with ERCOT offline to discuss testing a sample file ahead of the full market update.
The vice chair asked if 814_20 Update sample files could be provided to REPs in preparation of SET 5.0. The TDSPs advised the same information will be updated through the 814_05 REPS will receive during the Texas SET 5.0 flight test.
Texas SET 5.0 Change Control Call
TXSETCC847 | Update TXSETCC827 to require at least one form of communication (Telephone, Cellular, Email) when using the PER~PO (Power Outage Contact Information)
TXSETCC848 | This change control provides clarification by adding gray box language that State or Province Code(s) will only contain uppercase letters (A to Z) and if applicable digits (0-9).
TXSETCC849 | This change control provides clarification by adding gray box language that State or Province Code(s) will only contain uppercase letters (A to Z) and if applicable digits (0-9) to additional transactions not included in TXSETCC848.
Texas SET 5.0 Market Notice Discussion
Brief discussion around the ERCOT outage that delayed transaction processing on 02/12/24. The group agreed the topic would be taken up at TDTMS.
RMS Request: Texas SET 5.0 Production Go-Live Discussion
Texas SET Flight Test Certification Duration Discussion | Centerpoint Energy brought up the topic around EDI Certificate durations. There is a concern around REPs completing Texas SET Certification testing then choose not to activate that DUNS to serve any customers, sometimes REPs may need to have a unique DUNS available to serve specific large customers that require their own DUNS. Centerpoint asks should it expire in order to keep certification current?
ERCOT Legal points to PUCT Rules 25.107 (h) that advises of a 2 year provision and if the REP is not certified in that time they could lose their license.
ERCOT also pointed to the Texas Market Test Plan and Protocol 21 currently covers the market for this issue
Centerpoint asks, could we reference the PUCT rule in flight testing documents ?
Centerpoint proposed updating ERCOT Protocol 19.2 with the PUCT rule language to clarify
RMS Request: Texas SET 5.0 Production Go-Live Discussion
The group discussed what topics and documents need to be further discussed to prepare for SET 5.0 Go-Live.
• Transition Plan • Open IGL Transitions • WSDL API Update/Timing • Transaction Example Documents Updates • Updated MT Requirements Documents
ERCOT advised the group could begin discussing these topics at the March meeting, but most document updates will be available in the April/May timeframe.
Next Meeting-- In Person & WebEx | 2024-03-04
Attendees F-T-F
Attendees Webex
William Lewis Payless Power | Jordan Troublefield ERCOT | Angela - Good Charlie
Linda Summer - AEP Texas | Kathryn Thurman ERCOT | Carolyn Reed Centerpoint Energy
Bill Snyder AEP | Kathy Scott Centerpoint Energy | Cassandra Jenkins Centerpoint Energy
Jeff Chen Centerpoint Energy | Sarah Heselmeyer ERCOT | Cindy Juarez
Dee Lowerre Reliant | Mark Pepdjonovic ESG
Deb Belin Earth Etch | Melinda Earnest AEP
Diana Rehfeldt TNMP | Monica Jones-Centerpoint Energy
David Michelsen ERCOT | Chris Dominguez
Eric Lotter - Grid Monitor | Paul Yockey ERCOT
Amy Sue Stiriland LP&L | Sam Pak ONCOR
Jesse Macias AEP | Sheri Wiegand Vistra
Joe Lindsay Systrends | Stephen Wilson TXU