## Slide 1: Lubbock Retail Integration Task Force – LRITF July 9th, 2024
Chris Rowley Michael Winegeart Sheri Wiegand

## Slide 2: LRITF meeting 6/4/24
The Task Force reviewed the following:
LSE files– LP&L is currently working to successfully update LSE files once actual data is received replacing earlier estimated data.
zero estimates will be reflected during outages
sending single ESI files is a challenge and are currently testing
TSDP AMS Data Practices will be updated at a later date
867/810 Issues – LP&L reports backlog of 867/810 cancel/rebills has been completed. Out-of-sync conditions with ERCOT and LP&L are being reviewed. ERCOT has provided a list of ESIs to LP&L for approval. Such issues may have downstream impacts on receipt of LSE files via the AMS Settlement extract.
Meter Multipliers– all meter multiplier cancel/rebills have been completed and LP&L is billing current billing cycles.

## Slide 3: LRITF meeting 6/4/24 - continued
The Task Force also reviewed the following:
Decimals – LP&L confirmed announcement on market notice indicating they will begin sending decimal values on the 867/810s for the start and end register reads commencing with the August billing period (8/2/24).
SMT Readiness – LP&L plans to integrate with SMT after TXSET v5.0 is in place and likely in Q1 2025.
TXSET 5.0 Readiness – LP&L confirms teams are working toward TXSET v5.0 preparedness.
LRITF Sunsetting – Task Force will remain intact until all major issues have been resolved.

## Slide 4: Daily Market Calls
The weekly market calls will be held on Thursdays @ 10:00 AM to discuss any on-going issues:
https://us06web.zoom.us/j/89361889543?pwd=olviNzrBXvZJHnEHKgOUZprYTpSDDV.1
Meeting ID: 893 6188 9543
Passcode: 112233
DNP Discretionary Service Charges – were received on separate 810 invoices. REPs expecting charges to be included in monthly 810_02 charges.
DNP 650_01 RCNs processing – REPs receiving ‘date in past’ rejections when transaction was submitted prior. ROL requests were being pushed two days out thus causing RCN to be received prior to DNP being completed.
867 IDR– LP&L has created 867IDR however were being held up with validations at ESG
650_04s with R8 terminate & FA001 – LP&L was sending email requests to REPs for MVOs vs 650_04 notifications
BDMVIs submitted from transition until mid to late May – LP&L is unable to cancel an 810 for a BDMVI. Fix is in place and seeking REP assistance to “ignore” 810s for a period where they were not ROR. LP&L to send list of impacted ESIs/transactions.
Siebel Changes for Out of Sync conditions– ERCOT working with LP&L to ensure RORs are aligned in systems.
Priority Codes – per tariffs, LP&L will push any MVI requests for non-standard meters two days out whether priority code of 02 is used.

## Slide 5: Lessons learned
Customers with Multiple ESIs and DREP Process
TXSET Guides need updating
Need Regulatory/Legal decisions at beginning of project
Impact of Cycle Dates locked down and true MVI situations
Find a way to compare before defaulting – possibly provide customers with ESIs on their bundle bill prior to competition; create ESIs earlier in the process
We need to take some time and ensure we’ve captured the areas that need to be changed – ‘combo’ 814_05 kH vs KMON; Decimals; generalized practices - perhaps a ‘utility orientation’
Full awareness of any impacting legislation
Early conversations
LP&L has paved the way for additional MOU/ECs
Impacts stacking logic at go-live
Clear determination so REPs may design systems accordingly

## Slide 6: Lessons learned - continued
Phone Number formats & Country Code issue
Clean data for ESI creation
Addresses without descriptions
Decimals in meter reads
Update TXSET Guide
Avoid creation of ‘bad’ ESIs only to have to retire
Eliminates downstream confusion – customers, REPs
Understanding for Munis, other utilities may be associated
Systems should be able to use secondary address fields to help avoid inadvertent gain situations
With AMI being the standard meter type, this is an opportunity to allow decimals in meter reads. We are already using them in IDR situations

## Slide 7: Lessons learned - continued
Priority Codes for MVIs &Reconnects
TDSP Matrices in one location
Online enrollments – what options for multiple ESIs?
Cancel/rebill timing and LSE files
Should be included in the RMG along with other priority codes (service orders)
One place for: AMS Data Practices, Emergency Operating Plans, Solar Practices, Transaction Timelines
Including list in ERCOT opt-in checklist
Better customer experience if more than one ESI is to be enrolled
Providing a postcard to each customer with ESI information prior to sales window
This information is not captured in any protocols or guides at ERCOT… it is more of an ERCOT business process that impacts utilities processes. How can we capture for the next entrant? Opportunity to include in operating guide for settlements

## Slide 8: Lessons learned - continued
Full testing
Awareness of all files and extracts on ERCOT MIS
Shopping Fairs
Market Participants
Robust end to end testing with ‘real’ data including billing
Understanding of extracts available and purpose of data
WIN! Having a media market in a condensed geographical area resulted in effective communications to the residents
Providing questions for consideration – shopping guide and partnership with PUCT
Knowing the audience and conducting business/enrollments how the community wants to conduct business
Market participants were disengaged until the last minute
Requiring participation in the task force meeting if REP wants to become active in the territory

## Slide 9: Lessons learned - continued
EPS Meters
Understanding market processes
Understanding if territory has EPS meters, Muni will need to accept 867s from ERCOT
DCN/RCN processes and billing
ESI Maintenance and updating attributes

## Slide 10: TIMELINE of Actions
Q1 2023
Q2 2023
Q3 2023
Q4 2023
LP&L Rates
Customer Enrollment Process – Detailed Timeline
PUCT Complaint Process / Application of PUCT Rules
Transaction Timelines / TXSET Timelines
CSA Process
Mass Customer Lists
Power to Choose website
Customer Forums/Town Halls
Flight Testing / Bank Testing
CBCI files
Default REP Selection Process
DNP Blackout Period
Market Operations Group Established
GO LIVE – Transition to Competition
Q4 2022
Pro Forma Tariff
Access Agreement
POLR Process
Safety Net Process
Tampering Information Process
Smart Meter Texas
ESI IDs in TDSP Extract
RMG Chapter 8 Revisions
Historical Usage Requests
TDSP AMS Data Practices
ERCOT Activities: SAC04s, Load Profiles
TSDP Activities: Critical Care, DLFs, Solar/DG, Switch Hold Files, BUSIDDRQ, Call Center, OGFLT, Weather Moratoriums, Proration
March 2024
Completed
Q3 2023
Q4 2023
Q1 2024
Q4 2024 Q1 2025

## Slide 11: Lritf meeting 7/9/2024 @ 1:00PM following RMS – Webex only
AGENDA ITEMS:
Decimals
AMS Data Practices
SMT Readiness
Texas SET 5.0 Readiness
Stabilization
  650_01 RCN Processing
  DNP Discretionary Service Charges on 810s
  867_03 IDRs
  Seibel Changes with ERCOT
  BDMVIs and 810s
  810s received, missing 867s
  Duplicate 810s
Priority Codes – MVIs on Non-Standard Meters
Premise Reclassifications
POLR Process
LP&L Weekly Market Calls
Lessons Learned
Open Discussion