## Slide 1
RTC+B Update
Matt Mereness
TWG
July 25, 2024

## Slide 2: RTC+B Program Update (excerpt from June Board T&S RTC Update)
ERCOT to publish go-live date before or during September

## Slide 3
Sequence and Potential Dates for Market Trials (dates subject to change while in Planning phase)
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
3-4 months
2 months
1 month
1-2 months
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Attestation
9 months before Trials
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
Each activity will have a public-facing Scorecard and exit Criteria
Updated 2024-05-22
DRAFT
Current draft of the earliest possible dates for Market Trials and Go-Live that have been shared through TWG and the RTC+B Workshops, in support of Market Participants readiness at RTCBTF.
Actual Market Trials and Go-Live milestones are to be determined and will be communicated no later than 9/30/24.

## Slide 4: Reminder of Draft Market Trials Planning Document format

## Slide 5: ERCOT interested in feedback
ERCOT is interested in feedback on Market Trials Plan:
Open to feedback on all 7 activities, especially any reliability risks not addressed by the trial activities, durations or frequencies.
Specific questions ERCOT asks:
  What windows and frequency of requiring QSE production-like offers for the Open Loop SCED is best cost/beneficial (ie for dual entry by QSEs)?
    Example, 8 hours/day twice per week for 2 months?
  Any argument to make DAM participation a required activity or more iterations?
  Metrics for required testing will focus on QSEs with Resources, unless DAM becomes required.
  Understanding that while ERCOT will not be able to provide settlement invoices and extracts, that sample/generic versions will be provided from ERCOT test environment during iTest.
Higher level question- Market ideas on the priority of education/deep-dives to help QSEs in their development and readiness?

## Slide 6: Next Steps
Comments due on Market Trials Plan by August 9 and to be discussed at the August 14 RTCBTF Meeting.
  https://www.ercot.com/files/docs/2024/07/16/Issue%209_RTCB%20Market%20Trials%20Plan_ERCOT_Redlines_071624.docx
  Comments to be sent to Matt.Mereness@ercot.com
QSE Attestations were released this week to QSEs with Resources:
  Sent to Authorized Representatives (and Backup AR)
  QSEs with Resources will identify Accountable Executive
  RTCB Accountable Executive will attest the QSE is aware of interface changes being posted and acknowledge the need to develop the necessary systems changes to be ready to engage the RTC+B Market Trials activities (potentially as early as May 2025).
Clarifying NPRRs being released next week
  No system changes in clarifying NPRRs.
  All clarifications in alignment with specifications posted.
Questions?