## Slide 1: Lubbock Retail Integration Task Force – LRITF August 6th, 2024
Chris Rowley Michael Winegeart Sheri Wiegand

## Slide 2: LRITF meeting 7/9/24
The Task Force reviewed the following:
Decimals – Market notice sent 7/30/24 informing REPs decimals on 867/810s will commence with September billing period (9/2/24). Test files to some market participants were received on 7/26 and 7/29. ESG is working with LP&L to confirm mapping of up to six decimal places. Typically, the register reads and volumes (MEA and QTY segments) will have 3 to 4 except in proration cases, up to 6 decimal places.
LSE files– LP&L is currently working to successfully update LSE files once actual data is received replacing earlier estimated data.
zero estimates will be reflected during outages
sending single ESI files is a challenge and are currently testing
TSDP AMS Data Practices will be updated at a later date
SMT Readiness – LP&L plans to integrate with SMT after TXSET v5.0 is in place and likely in Q1 2025.
TXSET 5.0 Readiness – LP&L confirms teams are working toward TXSET v5.0 preparedness.

## Slide 3: LRITF meeting 7/9/24 - continued
The Task Force also reviewed the following:
Priority Codes – MVIs on non-standard meters (AMSM) will be executed same day if the ‘02’ priority code is noted and the MVI is received prior to 3PM. Previously, any MVI for an AMSM meter was being pushed two days despite the priority code.
Premise Reclassifications – Currently LP&L systems will not allow a premise/ESI to be reclassified from residential to non-residential (and vice versa) with an 814_20 transaction. Per LP&L, the premise classification is fundamental to the ESI, thus if a change is confirmed, LP&L will create a new ESI and the REP will need to submit an MVI on the new ESI and an MVO on the old ESI. LP&L will transfer the existing meter from the old to the new ESI. Negative downstream impacts to the process were discussed.
POLR Process – LP&L was noticeably absent from PUC worksheet. LP&L is considering extending their current contracts with their POLR REP and VREPs in order to later align with the ERCOT schedule. ERCOT will assist in administering distribution of ESIs in any POLR drop.
Stabilization Issues – also discussed during weekly market calls

## Slide 4: Daily Market Calls Stabilization issues
The weekly market calls will be held on Thursdays @ 10:00 AM to discuss any on-going issues:
https://us06web.zoom.us/j/89361889543?pwd=olviNzrBXvZJHnEHKgOUZprYTpSDDV.1
Meeting ID: 893 6188 9543
Passcode: 112233
DNP 650_01 RCNs processing – REPs receiving ‘date in past’ rejections when transaction was submitted prior. ROL requests were being pushed two days out thus causing RCN to be received prior to DNP being completed. Temporary fix in place so RCNs are not rejected. Permanent fix to not push DNPs two days with ROL notation is still undergoing testing.
DNP Discretionary Service Charges – were received on separate 810 invoices. REPs expecting charges to be included in monthly 810_02 charges. Fix went into place 7/19. Cancel/rebills for previous 810s are not expected.
867 IDR– LP&L has yet to determine root cause why some 867IDRs are hung at ESG due to validations
Siebel Changes for Out of Sync conditions– ERCOT working with LP&L to ensure RORs are aligned in systems. LP&L has requested a refreshed list.
BDMVIs submitted from transition until mid to late May – LP&L is unable to cancel an 810 for a BDMVI. Fix is in place and seeking REP assistance to “ignore” 810s for a period where they were not ROR. LP&L to send list of impacted ESIs/transactions. LP&L is determining how REPs will be credited accordingly.

## Slide 5: Daily Market Calls Stabilization issues- continued
The weekly market calls will be held on Thursdays @ 10:00 AM to discuss any on-going issues:
https://us06web.zoom.us/j/89361889543?pwd=olviNzrBXvZJHnEHKgOUZprYTpSDDV.1
Meeting ID: 893 6188 9543
Passcode: 112233
810s received, Missing 867s – start/end reads on 867s were missing for some unmetered and metered situations. LP&L is in final stages of testing metered examples. Unmetered cases should have received cancel/rebills.
Duplicate 810s – LP&L continues to work through clean up of duplicates, however, functionality should be corrected. If any REPs are seeing duplicates, send a MarkeTrak for correction.
810s with weekend due dates – LP&L’s technical team was working on a fix and should move to production soon. At this time, LP&L is not assessing late fees until stabilization is nearly complete.
60 day bills – any 60-day invoices should be submitted for correction via MarkeTrak.
650_04s with R8 terminate & FA001 – LP&L was sending email requests to REPs for MVOs vs 650_04 notifications. A fix is in place, yet LP&L is working with field personnel on application.
LOA Historical Usage Requests – LP&L is working to comply with standard format.

## Slide 6: Lessons learned
Customers with Multiple ESIs and DREP Process
TXSET Guides need updating
Need Regulatory/Legal decisions at beginning of project
Impact of Cycle Dates locked down and true MVI situations
Find a way to compare before defaulting – possibly provide customers with ESIs on their bundle bill prior to competition; create ESIs earlier in the process
We need to take some time and ensure we’ve captured the areas that need to be changed – ‘combo’ 814_05 kH vs KMON; Decimals; generalized practices - perhaps a ‘utility orientation’
Full awareness of any impacting legislation
Early conversations
LP&L has paved the way for additional MOU/ECs
Impacts stacking logic at go-live
Clear determination so REPs may design systems accordingly

## Slide 7: Lessons learned - continued
Phone Number formats & Country Code issue
Clean data for ESI creation
Addresses without descriptions
Decimals in meter reads
Update TXSET Guide
Avoid creation of ‘bad’ ESIs only to have to retire
Eliminates downstream confusion – customers, REPs
Understanding for Munis, other utilities may be associated
Systems should be able to use secondary address fields to help avoid inadvertent gain situations
With AMI being the standard meter type, this is an opportunity to allow decimals in meter reads. We are already using them in IDR situations

## Slide 8: Lessons learned - continued
Priority Codes for MVIs &Reconnects
TDSP Matrices in one location
Online enrollments – what options for multiple ESIs?
Cancel/rebill timing and LSE files
Should be included in the RMG along with other priority codes (service orders)
One place for: AMS Data Practices, Emergency Operating Plans, Solar Practices, Transaction Timelines
Including list in ERCOT opt-in checklist
Better customer experience if more than one ESI is to be enrolled
Providing a postcard to each customer with ESI information prior to sales window
This information is not captured in any protocols or guides at ERCOT… it is more of an ERCOT business process that impacts utilities processes. How can we capture for the next entrant? Opportunity to include in operating guide for settlements

## Slide 9: Lessons learned - continued
Full testing
Awareness of all files and extracts on ERCOT MIS
Shopping Fairs
Market Participants
Robust end to end testing with ‘real’ data including billing
Understanding of extracts available and purpose of data
WIN! Having a media market in a condensed geographical area resulted in effective communications to the residents
Providing questions for consideration – shopping guide and partnership with PUCT
Knowing the audience and conducting business/enrollments how the community wants to conduct business
Market participants were disengaged until the last minute
Requiring participation in the task force meeting if REP wants to become active in the territory

## Slide 10: Lessons learned - continued
EPS Meters
Understanding market processes
Understanding if territory has EPS meters, Muni will need to accept 867s from ERCOT
DCN/RCN processes and billing
ESI Maintenance and updating attributes
Understanding of the settlement differences of BUSIDRRQ, significance of LSE files and reversions, and impacts of cancel/rebills
ERCOT Settlement Process

## Slide 11: TIMELINE of Actions
Q1 2023
Q2 2023
Q3 2023
Q4 2023
LP&L Rates
Customer Enrollment Process – Detailed Timeline
PUCT Complaint Process / Application of PUCT Rules
Transaction Timelines / TXSET Timelines
CSA Process
Mass Customer Lists
Power to Choose website
Customer Forums/Town Halls
Flight Testing / Bank Testing
CBCI files
Default REP Selection Process
DNP Blackout Period
Market Operations Group Established
GO LIVE – Transition to Competition
Q4 2022
Pro Forma Tariff
Access Agreement
POLR Process
Safety Net Process
Tampering Information Process
Smart Meter Texas
ESI IDs in TDSP Extract
RMG Chapter 8 Revisions
Historical Usage Requests
TDSP AMS Data Practices
ERCOT Activities: SAC04s, Load Profiles
TSDP Activities: Critical Care, DLFs, Solar/DG, Switch Hold Files, BUSIDDRQ, Call Center, OGFLT, Weather Moratoriums, Proration
March 2024
Completed
Q3 2023
Q4 2023
Q1 2024
Q4 2024 Q1 2025

## Slide 12: Lritf meeting 8/6/2024 @ 1:00PM following RMS – ERCOT Met Center (and via Webex)
AGENDA ITEMS:
Decimals
AMS Data Practices – Gap Retrieval
SMT Readiness – daily sync file
Texas SET 5.0 Readiness
Stabilization
  650_01 RCN Processing
  DNP Discretionary Service Charges on 810s
  867_03 IDRs
  Seibel Changes with ERCOT
  BDMVIs and 810s
  810s received, missing 867s
    Missing start/end Reads
  Duplicate 810s
  60 day bills
  650_04s FA001 R8 codes
LOA Historical Usage Request - Format
Premise Reclassifications
POLR Process
LP&L Weekly Market Calls
Lessons Learned
Open Discussion