## Slide 1
RTC+B Task Force
Update
Matt Mereness
RTCBTF
August 14, 2024

## Slide 2: Outline
Brief Program update: RTC+B Program Update from Board T&S
Reminder of RTCBTF Review Cycle
Review of Issues List
Scope of RTC+B Program
Today’s Issues List for Discussion:
  Review RTC and ESR Clarifying Revision Requests for market questions
    RTC- NPRR1245
    ESR- NPRR1246, NOGRR268, PGRR118, OBDRR52
  Issue 3- RTC Simulator update (verbal update only) (Raymund Lee)
  Issue 9- Explanation of Market Submission interface changes (Nathan Smith)
  Issue 10- Market Readiness
    Final review of Market Trials Plan
    Attestation scorecard going to Board
  Issue 18 – Placeholder for MPs Discussion of AS Demand Curves
  Heads-up on topics for September RTCBTF meeting
  Issue 8- Mapping of bill determinants to extracts and reporting for developing shadow settlement
    Settlements and Billing Deep-Dive (1-2 hours) (Magie Shanks)

## Slide 3: RTC+B Program Update (excerpt from June Board T&S RTC Update)
ERCOT to publish go-live date before or during September

## Slide 4
Sequence and Potential Dates for Market Trials (dates subject to change while in Planning phase)
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
3-4 months
2 months
1 month
1-2 months
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Attestation
9 months before Trials
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
Each activity will have a public-facing Scorecard and exit Criteria
Updated 2024-05-22
DRAFT
Current draft of the earliest possible dates for Market Trials and Go-Live that have been shared through TWG and the RTC+B Workshops, in support of Market Participants readiness at RTCBTF.
Actual Market Trials and Go-Live milestones are to be determined and will be communicated no later than 9/30/24.

## Slide 5: Plans for Meetings and Review Cycles
Reminder of RTC+B Program Scope
  RTC Key Principles were approved to lay foundation of NPRR1007-1013
    Consolidated Key Principles: https://www.ercot.com/files/docs/2020/04/01/RTC_Key_Principle_Quick_Reference.docx
    Library of Key Principles: https://www.ercot.com/mktrules/puctDirectives/rtCoOptimization
  Battery Key Topic Concepts approved to lay foundation of NPRR1014
    https://www.ercot.com/mktrules/keypriorities/bes
  RTC State-of-Charge accounting in NPRR1204
Objective is to present concepts or issues that need to be resolved for an effective implementation.
  Coordinating timelines for interface requirements and testing,
  Providing the forum for any analysis or policy decisions (such as parameter values)
  Coordinating market readiness and cutover activities,
  Review draft Revision Requests or other artifacts necessary to successfully implement the program within the identified timeframes, and discussing other details as needed.
Lessons learned from RTCTF to avoid being delayed in decisions:
  Meeting #1: Initial concept presented by ERCOT staff
  Meeting #2: Comments and alternatives presented by MPs
  Meeting #3: RTCTF consensus achieved or escalated to TAC for a vote to decide the matter.

## Slide 6: Current RTCBTF Issues List
Prior to Sept meeting, ERCOT will streamline and align to key risks with program schedule.

## Slide 7: RTC+B Clarification NPRRs
ERCOT developed at clarifying Revision Requests:
  Clarification RTC NPRR after completing business requirements (eg, drift in baseline since 2019, discrepancies and/or small gaps found during business requirement development)
  Clarification Single Model NPRR, PGRR, NOGRR, OBD as an extension of NPRR1014 Single Model to clarify single model language in other areas of protocols.
  Note- All changes are intended to be “as designed” clarifications, aligned with Key Principles, and have no system impacts.
Shared initial drafts with RTCBTF at July RTCBTF meeting
ERCOT filed RRs at end of July to allow vetting of comments via existing PRS process and supported by RTCBTF to review (next 2-3 meetings).
  RTC- NPRR1245
  ESR- NPRR1246, NOGRR268, PGRR118, OBDRR52

## Slide 8: Scope of RTC+B Program (Excel version posted with meeting)

## Slide 9: Proceed with rest of meeting
Review RTC and ESR Clarifying Revision Requests if market questions
  RTC- NPRR1245
  ESR- NPRR1246, NOGRR268, PGRR118, OBDRR52
Issue 3- RTC Simulator update (verbal update only) (Raymund Lee)
Issue 9- Explanation of Market Submission interface changes (Nathan Smith)
Issue 10- Market Readiness
  Final review of Market Trials Plan
  Attestation scorecard going to Board
Issue 18 – Placeholder for MPs Discussion of AS Demand Curves
Heads-up on topics for September RTCBTF meeting
Issue 8- Mapping of bill determinants to extracts and reporting for developing shadow settlement
  Settlements and Billing Deep-Dive (1-2 hours) (Magie Shanks)
Next meeting in-person/WebEx on Wednesday September 13, 2024