## Sheet1
CATEGORY | ISSUE DESCRIPTION | RECOMMENDED SOLUTION | ERCOT Response | Joint Comments (8/15/24) | ERCOT Response (08/23/24) | 8/26/2024 1:00 PM Meeting Notes
Request Submission | All QSE certificates will need to be updated to include NDCRC. Currently only RE certificates have NDCRC authorized on them. | Need to confirm with ERCOT that QSE certificate will gain access to NDCRC without manually updating the certificate. | If the QSE does not have the proper Cert, They will need to coordinate with the RE to submitt the test request. | Suggest ERCOT to provide an update if any changes will be made for this issue. | QSE Certs having either QSE_W or QSE_R role will be able login into NDCRC and access QSE Test Request forms directly without depending on RE certs. This change was implemented in production on 08/23/2024 around 11:00 AM.
Request Submission | Submission of test request is on unit bases. Requires multiple tickets for testing Combine cycle generators. | Provide options for both unit-based and configuration-based. Provide check box selection which has all the units represented by the QSE. | NDCRC does provide combine cycle configurations, we will look into check box selection option as well for all units represented by QSE. | The CC configuration option is available now, but the unit-based selection option is taken away. | Test Request form dropdown now has both Combined Cycle Configurations and Combined Cycle Physcal Units. This change was implemented in production on 08/23/2024 around 11:00 AM.
Request Submission | The start date in the test range is limited to no more than 7 days in advance. | What's the benefit of this new rule? A QSE should be able to submit a request more than 7 days in advance considering ERCOT's cancellation rules. Also need flexibility to submit a request for a test lasting more than a week. (The current process allows this kind of flexibility) | 7 days is the maximum a QSE can update their cop (WRUC). There are too many changes that can happen outside of 7 days. The current process does not allow for test request to exceed 7 days. | The requirement of a less than 7-day advance notice makes it difficult to schedule a test which requires coordination of different groups and outside contractors. | This is the current process with the email and there is no change. The only timeline change is a two-hour minimum submission on the test request. ERCOT gets many requests, we need time to review and process each request. | Joint Commentors are good with submitting within 7 days window as this is the current process. ERCOT Control Room plans to continue the current approval process as it is now and should normally be processed in less than an hour although sometimes it maybe delayed based on grid conditions.
Request Submission | The “Submittal Information” section appears to limit the total number of characters in each field. However, we successfully submitted a test request using an incomplete email address in the QSE Email field due to that limitation. |  |  | New issue | We will address the character limit issue in the next NDCRC release targeted for 9/26 (we will also look at delivering early if possible)
Request Submission | ERCOT did not detect or send a notification about the incomplete email address in the testing request. |  |  | New issue. Q: Does ERCOT receive undelivered notice for incomplete email addresses included in the request? | This issue is related to the above issue, fixing the character limit issue should address the issue and this will be addressed in the next NDCRC release targeted for 9/26.
Request Submission | Special characters in the email address are not allowed in the email field. For example, we got the following error message when trying to enter “#pogendispatchkennett@constellation.com”. Note that the “#” sign was automatically removed by the system. |  |  | New issue | Email address field validation rules are working as expected, this maybe a User training issue. # special character is not allowed in the email address field.
Request Submission | The system requires that the test request submitter fill out the start and end time fields to the seconds. Outage Scheduler does not go down to Seconds field. |  |  | New issue. Is the "seconds" filed needed for testing request purpose? | Seconds fields will be removed with the next NDCRC release, which is targeted for 9/26 (we will also look at delivering early if possible).
Request Modification | ERCOT system locks down ticket once in Approved state. Process to modify test start will result in cancellation and recreation of test request as once approved. | Must allow test modification without cancellation and recreation of test request. | QSE's will be able to modify the test request (start and end time only) during the requested dates. If they need to adjust the date, they will need to submitt a new request as we do today. |  | This will be addressed in the next release as well, which is targeted for 9/26 | ERCOT Control room will be able to review/approve resubmitted requests which were approved before but later reschduled within 24 hours or even earlier based on the urgency. Resubmitted unit test requests do not go to the bottom of the queue because there is no queue. With this feedback from ERCOT, joint commentors are good with the process of ERCOT allowing start/end time change only of a given start/end date but start/end date changes are not allowed.
Request Modification | ERCOT requires scheduling a test request two hours in advance. We will lose the flexibility to conduct opporunity-based testing. | Must allow a QSE to adjust testing schedules near real time contigent upon ERCOT shift supervisor approval. Nodal Protocols or Nodal Operating Guides should allow QSEs to make phone calls or emails to ERCOT shift supervisor to modify a test request. | With the amount of calls and request for Real Time approvals created addition stress on the control room. With the amount of request ERCOT receives in realtime this is one of the concerns ERCOT is trying to minimize. | Cannot request an extension for an ongoing testing due to the two hour limit. | We request that the QSE work with the RE to plan accordingly so that the QSE can request the extension within the timeframes. | End time (within the original End day) can be updated if test goes longer than expected.
Request Modification | ERCOT system locks down ticket once in Approved state. Extending a test request will result in cancellation and recreation of test request as once approved. | Must allow a QSE to extend a test as needed without cancellation and recreation of test request. | QSE's will be able to modify the test request (start and end time only) during the requested dates. If they need to adjust the date, they will need to submitt a new request as we do today. | In contrast, QSE can extend an active outage in Outage Scheduler without sending a new request. | Effectively you may think you are extending the outage although you are creating a Forced Outages stating that the RE can't be returned withing the timeline originally approved.
ERCOT Communication of Status | No guidance provided on when the testing request will be reviewed by ERCOT. | Will ERCOT provide language in the Real Time Operating Procedure? | The test request procedure is planed to land in the Reliability Risk desk and the Shift Supervisor Desk procedures. | All notifications sent by ERCOT should confirm the details in the testing requests submitted. Suggest ERCOT to provide draft procedure language for review at the August TWG meeting. | Currently, the test request procedure resides in the Shift Supervisor Desk procedures. Once we implement the new process, it will also reside in the Reliability Risk desk procedure. We disseminate these procedure changes through the Power Operations Bulletin notifications. | Email Confirmation message should include Resource Name/test type/start-end times (summary details), along with attachment. Additionally Joint commentors requested to provide the capability to upload the word document as attachment. ERCOT will provide the fix to update the email confirmation message with summary details with attachment with 09/26 as target release date but supporting word document as attachment might require further review by ERCOT on implementation.
ERCOT Communication of Status | Communication of acceptance of testing request requires ERCOT operator to chose to send an email. QSE Operators need to check the NDCRC page to ensure no changes are made to previously submitted and approved test request. | Will ERCOT provide language in the Real Time Operating Procedure? (ERCOT to confirm that an automated standard email will be sent out once it's approved/rejected by ERCOT.) | Yes, Once the the test is approved,rejected and/or updated email will automatically be sent to the email address provided in the request for. |  | This has been take care of and will be inlcuded in the next release, which is targeted for 9/26.
API | There is no API to upload or pull down data from NDCRC. |  | API is not part of this project scope, current NDCRC application does not have API framework to add this change, it requires significant effort to develop NDCRC API.
API | There is no API/Listener to inform market participants if test request is approved. |  | API is not part of this project scope, current NDCRC application does not have API framework to add this change, it requires significant effort to develop NDCRC API.
General Feedback |  | ERCOT not deploy process change until it is further discussed and a better solution is created. A. ERCOT can opt to have testing request get submitted into Outage Scheduler B. ERCOT can opt to have testing request submitted into MMSUI C. ERCOT can develop an API in NDCRC | ERCOT is planning to have a parallel testing period of the old and new procedure for the month of August. As of now the go live is slated for October 1, If no critical show stoppers are identified then October 1 will be our transition. ERCOT did not consider MMS UI and Outage Scheduler applications for this purpose because these applications objectives are different, design, architecture and workflows of these applications by default do not support gatthering and tracking generating units test data. NDCRC application was designed for that purpose, so it was chosen to implement this effort requirements. | Suggest ERCOT to explain in detail the issues/obstacles relative to implementing this process in the Outage Scheduler. Need more testing time: * Need to do more testing to cover most of the important scenarios. August is a busy time for operators to be fully engaged in this testing * In addition, it is difficult to design training materials for operators to perform testing considering the cert issue and potential changes. As such, operators are not fully engaged in this testing. * Need time to adequately address the issues discovered before and during the testing * Need time to determine the best platform for this new process | Additional Testing Time - You can utilize month of September for testing instead of parallel operation. Parallel operation is optional, we incorporated parallel operation in the plan based on the feedback we recieved. Parallel Operation puts more burden on our control room to manage both current and new process, so we prefer to go live (October 1st) after testing is completed and Septermber month can be utilized for testing. | Additional Testing Time: Joint Commentors support the idea of cancelling the current plan of utilizing September month for parallel operation and use entire September month for further testing the tool and go live October 1st without parallel operation. ERCOT will send out of Market Notice to all QSEs to notify this change in the current plan. ERCOT will prepare a short presentation to explain why implementing this process in Outage Scheduler is complex and requires significant effort.