## Slide 1
RTC+B Task Force
Update
Matt Mereness
TAC
September 19, 2024

## Slide 2: Outline
Program Go-Live Announcement
Realignment of Current Issues for RTCBTF
Follow-up on A/S Demand Curve status

## Slide 3: RTC+B Program Go-Live Announcement
Links to:
Market Notice
Press Release
Trending Topic Paper

## Slide 4
Sequence and Potential Dates for Market Trials (dates subject to change while in Planning phase)
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
3-4 months
2 months
1 month
1-2 months
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Attestation
9 months before Trials
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
Each activity will have a public-facing Scorecard and exit Criteria
Updated 2024-05-22
DRAFT
Current draft of the earliest possible dates for Market Trials and Go-Live that have been shared through TWG and the RTC+B Workshops, in support of Market Participants readiness at RTCBTF.
Actual Market Trials and Go-Live milestones are to be determined and will be communicated no later than 9/30/24.
Graphic will be updated
with Program Dates
at next RTBTF and TAC

## Slide 5: Current RTCBTF Issues List
At last TAC, ERCOT committed to streamline and align to key risks with program schedule.
  Market Trials and Readiness (eg, new telemetry points and how to test in trials)
  Analysis of market outcomes (eg, price formation for certain historical days)
  Parameter values (eg, proxy offer for Ancillary Services)
  Open discussion of other risks and concerns (eg, shape of AS Demand Curves)
Old List

## Slide 6: Change to RTCBTF Issues List
How mapped/transitioned into streamlined list
TEMPORARY WORKING DOCUMENT

## Slide 7: New streamlined RTCBTF Issues List going forward
Parameter and Policy dates defined
Ramp-up of RTC Simulator Analysis and priorities of what to study
More details coming for Market Readiness progression

## Slide 8: Reviewed at September RTCBTF
Issue 1- Initial Review of Parameters for AS Proxy Offer Curves
  Likely to become a hot-topic (proxy offer at $0, the $OfferCap, or in between)
  Will discuss at Oct and Nov RTCBTF meetings and then November TAC
Review RTC and ESR Clarifying Revision Requests if market questions
  RTC- NPRR1245 (any updates from ERCOT)
  ESR- NPRR1246, NOGRR268, PGRR118, OBDRR52 (any updates from ERCOT)
Issue 3- RTC Simulator update
  ERCOT committed to studying 3 Operating Days and providing analysis at Oct RTCBTF
Issue 10- Market Trials Plan Review
  Final review planned at next RTCBTF meeting and coming to October TAC for endorsement.
Discuss Approach to Training/Readiness
  ERCOT authored initial outline of Market Readiness “training components”
Issue 18 – Placeholder for MPs Discussion of AS Demand Curves
  ERCOT posted explanation of ASDC discussion and posted with TAC materials
  Also note Shams has expressed concerns with AS Indifference requirement being needed (link)
Next meeting in-person/WebEx on Tuesday, October 22, 2024