## Sheet1
RTC+B Program Scope for delivery (as of 10/22/2024)
Revision Request | Status | RTC+B Program revisions | Description | Reason
NPRR1007 | PUC appv | ALL | RTC | Foundation
NPRR1008 | PUC appv | ALL | RTC | Foundation
NPRR1009 | PUC appv | ALL | RTC | Foundation
NPRR1010 | PUC appv | ALL | RTC | Foundation
NPRR1011 | PUC appv | ALL | RTC | Foundation
NPRR1012 | PUC appv | ALL | RTC | Foundation
NPRR1013 | PUC appv | ALL | RTC | Foundation
NOGRR211 | BOD appv | ALL | RTC- Op Guide 2 and 9 | Foundation
OBDRR020 | BOD appv | ALL | RTC- Setting Shadow Price | Foundation
NPRR1014 | PUC appv | ALL | Single Model | Foundation
NPRR1204 | PUC appv | ALL | RTC- State of Charge for SCED/RUC | Supplemental
NPRR1236 | PRS- in flight | ALL | RTC- RUC Capacity Short | Supplemental
NPRR1245 | PRS- in flight | ALL | RTC- Clarification | Clarifications
NPRR1246 | PRS- in flight | ALL | Single Model- Clarification | Clarifications
NOGRR268 | ROS- in flight | ALL | Single Model- Clarification | Clarifications
PGRR118 | PWG- in-flight | ALL | Single Model- Clarification | Clarifications
OBDR052 | TAC- in-flight | ALL | Single Model- Clarification | Clarifications
NPRR1000 | PUC appv | ALL | Remove Dynamically Scheduled Resources | Efficiency
NPRR1054 | PUC appv | (no gray box) | Remove Oklaunion Exemption settlement | Efficiency
NPRR1172 | PUC appv | 5.7.2(2)&(4)- RUC Clawback | S&B Portion of NPRR1172 RUC ClawBack | Efficiency
NPRR963 | PUC appv | 6.6.5.5 6.6.5.5.1 6.6.5.6 | NPRR1014 was written on top of the NPRR963 greyboxes for Set Point Deviation changes. In order to appropriately implement these changes for ESRs, need some of the language from NPRR963. | Dependency for NPRR1014
NPRR1058 | PUC appv | 4.4.9.3 6.6.9 | Adapting requirements for Market Submission required field and locking the Energy Offer Curve for Emergency Settlements | Implementing in current system August 2024
NPRR965 | PUC appv |  | GREDP Shutdown Exemption- Insignificant addition to overall reporting change. | Efficiency
NPRR1216 | PUC appv |  | PUCT Emergency Pricing Program- defer automation to RTC+B and report changes. | Efficiency