## Slide 1
RTC+B Task Force
Update
Matt Mereness
TAC
November 20, 2024

## Slide 2: Outline
Current Issues and Schedule for RTCBTF
Highlights of RTCBTF Issues
  Readiness/Training Update
  Parameters/Policy Needing NPRR
  IMM Proposal for ASDC
Upcoming RTCBTF Discussion for 12/11/24 meeting

## Slide 3
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.

## Slide 4: RTCBTF Issues List
Progress on parameter-values and RTC Simulator Analysis
More details for Market Readiness progression

## Slide 5: November RTCBTF meeting outline
3. Scaling Factors for Ramp sharing
    Second round review (general agreement and will go into NPRR)
4. Market Readiness Update
    Technical Update – Digital Certificate Plan
    Training Update – Review Initial Video Postings
5. Discussion of NPRR(s) for RTC+B Parameters
    Outline issues to be codified in protocols
6. Review of Parameters for AS Proxy Offer Curves
    Third round review (will go to fourth round with Dave’s proposal to leverage ASDCs)
7. Discussion of AS Demand Curves
    IMM Discussion
8. RTC Simulator update
    Historical Analysis for 9/6/23 (scarcity), 7/10/23 (congestion), 10/20/23 (reliability deployment adders)
    Historical Analysis for 6/19/23 (volatility) and 11/16/23 (mild day)
2025 RTCBTF meeting dates on calendar
RTCBTF meeting will start to include technical details RTC+B that were previously in “Technical Workshops”

## Slide 6: Readiness/Training Update
RTCBTF Home page has Training Link

## Slide 7: Parameters/Policy Needing NPRR
Current scope of NPRR for Parameter/Policy Changes
  AS Proxy Offer Floors
  Ramp Rate Sharing
  ASDCs for Reliability Unit Commitment
  Ancillary Services Duration Requirements (ie, State of Charge)
Timeline of NPRR for the RTC+B Parameter Changes
  ERCOT will file NPRR in December 2024 or January 2025
  In parallel, RTCBTF can be vetting the values and filling in the blanks/values
  MP can document positions in NPRR formal comments
  Target completing RTCBTF analysis by March to then move NPRR though stakeholder process.
  Best before trials start in early May 2025):
    RTCBTF discussions in meetings (Dec2024-Feb2024)
    Potentially add a RTCBTF meeting in early March
    PRS Approval March 12, 2025 (assumes Urgent status)
    TAC approval March 26, 2025
    Board approval April 8, 2025
    PUCT consideration May 15, 2025

## Slide 8: IMM AS Demand Curves
Protocol approved:
IMM 11/13/2024 blended proposal:

## Slide 9: Next Steps at December 11th RTCBTF Meeting
Further discussion
  AS Proxy Offer Floors (4th mtg)
  IMM AS Demand Curves
  RTC Simulation Cases
New topics added for discussion
  AS Deliverability (when RTC Awards AS behind constraints)
  IRR AS Qualifications
  Draft Market Trial Handbooks for May 2025 activities
Any questions?