## Slide 1
RTC+B Task Force
Update
Matt Mereness
TAC
January 22, 2025

## Slide 2: Outline
Current Issues and Schedule for RTCBTF
Highlights of RTCBTF Issues
  Parameters/Policy Needing NPRR
  IMM Study and Proposal for ASDC NPRR
  AS Qualification clarification NPRR
  Refreshed ERCOT study of annual RTC cost savings in 2023-2024
Upcoming RTCBTF Discussion for 1/23/25 meeting

## Slide 3: RTC+B Program Update (excerpt from December Board T&S RTC Update)

## Slide 4
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added to network model.
NEW

## Slide 5: RTCBTF Issues List
First red box will be a single ERCOT NPRR for 4 policy issues
Second red box is a single IMM NPRR for ASDC changes
Third red box is a clean-up NPRR and includes explicit AS Qualification issue

## Slide 6: Reminder of Details Scope of RTC+B Program
No change from
October 2024

## Slide 7: RTCBTF Key Discussions 12/11/2024 & 1/14/2025
Discussion of NPRR for RTC+B Parameters (ERCOT staff)
- Ramp Rate sharing (NPRR language)
- AS Proxy Offer Floor (NPRR language to consider leveraging modified ASDC)
- ASDC for RUC discussion (NPRR sections impacted and presentation)
- AS Duration Requirements (initial discussion)
Proposed changes for NPRR related to AS Qualification (ERCOT)
- Follow-up on discussion of IRR AS qualification (deferred to Jan 23 meeting)
Discussion of AS Demand Curves (IMM)
- ASDC sensitivity analysis study for different ASDC proposals
- Current protocol approved version ASDC
- IMM Blended ASDCs
- IMM Adjusted ASDCs (based on MP feedback)
- Draft NPRR for IMM Blended ASDCs
Refreshed RTC Efficiency Cost Savings (ERCOT)
- ERCOT study of annual RTC cost savings in 2023-2024 (now $2.5-6.4B)
Review any Market feedback on Market Trials Handbooks (ERCOT)
- QSE Market Submissions (Handbook #1) – No comments received
- QSE Telemetry Check-Out (Handbook #2) – No comments received
WMS question about WSL in Load Forecast (ERCOT)

## Slide 8: Summary and Timeline of NPRRs that will be in flight
NPRR for Parameter/Policy Changes (ERCOT sponsor)
  AS Proxy Offer Floors - ASDCs for Reliability Unit Commitment
  Ramp Rate Sharing - AS Duration Requirements (ie, State of Charge)
NPRR for AS Qualification details (ERCOT sponsor)
NPRR for ASDC Modifications (IMM sponsor)
Timeline and vetting of RTC+B NPRRs
Jan 2025
Feb 2025
Mar 2025
Apr 2025
May 2025
June 2025
File NPRRs
(No impacts) Jan 28
PRS Urgency & Table NPRRs
Feb 12
PRS Approval March 12
TAC approval
March 26
Board Approval
April 8
PUCT Approval
May 15
RTCBTF: Jan 23, Feb 19, add 1-2 meetings
Stakeholder comments in Feb and March
ERCOT window for “re-factoring” development
ERCOT market trials deployed and begin on May 5, 2025

## Slide 9: Readiness/Training Update
RTCBTF Home page has Training Link
RTC+B Basic Education was added in December (37 minute YouTube)

## Slide 10: Next steps at January 23rd RTCBTF Meeting
Half-day meeting focused on:
Review of the 3 NPRRs (concepts and draft language)
  Recognition NPRRs still subject to stakeholder input via formal comments and RTCBTF discussion after Jan 28 filing
  Discuss needs for extra RTCBTF meeting(s)
Support MP questions on ERCOT and IMM studies
  IMM and ERCOT released data set supporting Jan 14 analysis
Questions?