## Slide 1
Revision Request
Project Go-Live History
2013 – Current

## Slide 2: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/11 – 2/15 | Release 2 4/22 – 4/26 | Release 3 6/10 – 6/14 | Release 4 7/29 – 8/2 | Release 5 9/23 – 9/29 | Release 6 12/9-12/13 | 2013 TBD
On-Cycle | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456 | NPRR481 NPRR520(a) NOGRR093 | NPRR393 NPRR461 NPRR520(b) SCR760(d) | NPRR207 NPRR385 NPRR457 NPRR514 NOGRR101 SCR770 | NPRR407(b) NPRR425(a) NPRR476 NPRR492 | 
Off-Cycle |  | NPRR463 | SCR773 |  |  | NPRR479 NPRR484(1a) | 
Counts Total = 31 | 9 | 2 | 4 | 4 | 6 | 6 | 0
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
None
October
None
Late May
Moved to Future Years
NPRR407(a) – MMS portion
NPRR407(b) – CRR portion
NPRR425(a) – RARF, EMS portions
NPRR484(1a) – initial CMM/CRR components
NPRR520(a) – MMS, MIS, CDR portions
NPRR520(b) – EMS, NMMS, ICCP portions
SCR760(d) – final phase
ü
ü
ü
ü
ü
ü
ü
ü
ü

## Slide 3: 2014 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
None
January
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR425(b) – GREDP, EIS portions
NPRR589(a) – MMS portion
SCR756(b) – Remaining portions of SCR
SCR774(a) – All new fields except Comments
(a), (b), etc. indicates multiple phases
None
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
ü
ü
ü
Release Approach | Release 1 2/3 – 2/7 | Release 2 4/14 – 4/18 | Release 3 6/9 – 6/13 | Release 4 7/28 – 8/1 | Release 5 9/22–9/26 | Release 6 12/8–12/12 | 2014 TBD
On-Cycle | NPRR240 NPRR425(b) NOGRR105 NPRR509 | NPRR564 NPRR570 | NPRR532 NPRR555 | NPRR491 SCR769 SCR756(b) | NPRR485 NPRR571 NPRR586 SCR774(a) | NPRR467 NPRR580 NPRR619 | 
Off-Cycle | NPRR416 NPRR575 |  | NPRR568 NPRR589(a) |  | NPRR527 |  | 
Counts Total = 23 | 6 | 2 | 4 | 3 | 5 | 3 | 0
6/1
11/1
Retail: 2/22-2/23
Retail: 8/17
ü
ü
ü
2015
ü
ü
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
ü
ü

## Slide 4: 2015 Release Summary – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR589(b) – S&B portion
NPRR686(a) – Wind portion
SCR774(b) – Addition of Comments field
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
February 2/2 – 2/12 | March 3/23 – 3/27 | June |  | September 9/7 – 9/11 | October 10/19 – 10/23 | December 12/7 – 12/11
NPRR500 SCR772 | SCR778 SCR779 | NPRR559 NPRR597 NPRR601 NPRR639 | NPRR543 NPRR626 NPRR645 NPRR665 SCR774(b) SCR775 OBD (Shadow Price Caps) | SCR771 NPRR589(b) NPRR701 | NPRR556 NPRR595 NPRR698 NPRR706 NPRR710 | NPRR680 NPRR686(a) NPRR703 NPRR718 PGRR044
2 | 2 | 11 |  | 3 | 5 | 5
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
Late May
6/13 (CMM)
6/22 – 6/26
September
9/21 – 9/25

## Slide 5: 2016 Release Results – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR686(b) – Solar portion
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
February 2/2 – 2/4 | April 4/12 – 4/14 | June 6/21 – 6/23 | August 8/30 – 9/1 | September 9/26 – 9/30 | December 12/6 – 12/8
NPRR588 NPRR615 NPRR686(b) | NPRR419 NPRR728 COPMGRR040 | NPRR515 NPRR617 NPRR700 NPRR719 NPRR742 NPRR745 VMCRR008 EMS Upgrade | NPRR662 NPRR712(a) RMGRR126 RMGRR137 | NPRR219 SCR783 NOGRR050 NOGRR143(a) NPRR712(b) NOGRR143(b) NPRR495 NPRR736 NPRR770 | NPRR713 NPRR754 NOGRR147 SCR787 SCR788 RMGRR127 RMGRR140 SCR786
3 | 3 | 7 | 4 | 9 | 8
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
EMS Upgrade “Chill”
6/16
12/10 – 12/11 (Retail)
7/23 – 7/24
(Retail)
11/1 – 11/3
5/1

## Slide 6: 2017 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
March 3/7 – 3/9 | May 5/1 – 5/11 | June 6/27 – 6/29 | August 9/11 – 9/13 | October 10/31 – 11/2 | December 12/5 – 12/7
NPRR272 NPRR649 NPRR753 NPRR764 NPRR785 RMGRR134 NPRR790 | SCR790 NPRR746 NPRR786 NPRR792 NOGRR164 PGRR051 RRGRR003 RRGRR006 RRGRR007 RRGRR009 RRGRR010 PGRR046 | NPRR573 NPRR789 NPRR797 NPRR801 NPRR827 NPRR744 | NPRR758 NPRR775 NPRR809(a) PGRR052 PGRR054 | NPRR782 NPRR831(a) NPRR562(a) NPRR808 PGRR056 | NPRR812 NPRR778 RMGRR139
7 | 12 | 6 | 5 | 5 | 3
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
12/9 – 12/10 (Retail)
5/8 – NMMS Upgrade
6/1
9/1 & 9/14
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
8/1
2/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
NPRR562(a) – Procedural changes
NPRR809(a) – Procedural changes
NPRR831(a) – All impacted systems except CRR
ü

## Slide 7: 2018 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/6 – 2/8 | April 4/5 – 4/9 | May 5/29 – 5/31 | August 8/7 – 8/9 | October 10/23 – 10/25 | December 12/11 – 12/13
NPRR659 NPRR683 NPRR743 NPRR760 NPRR800 NPRR810 PGRR042 NPRR846 | NPRR562(b) SCR792 NPRR776 NOGRR167 | NPRR768 NPRR815 OBDRR002 PGRR057(a) | NPRR819 NPRR844 NPRR854 SCR791 NPRR702 (partial implementation) NPRR825(a) | NPRR843(a) NPRR864 NPRR875 SCR795 RRGRR015 | NPRR843(b) PGRR063 NPRR831(b) SCR777
7/2
9/1
CMM Release 1a
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
1/1 & 2/1
NPRR825(a) – NoticeBuilder changes
NPRR825(b) –
NPRR562(b) – Reporting/posting system changes
NPRR809(b) – Reporting/posting system changes
NPRR833(a/b) – DAM/SCED system changes
NPRR843(a) – CDR, 48 hour, & 7 day reports
NPRR843(b) – 60 day reports
PGRR057(a) – Preliminary posting
TBD Items (and point at which they became “TBD”)
2014 | 2015 | 2016 | 2017 | 2018
NPRR664 | None | SCR781 P | NPRR702 P, NPRR829 | RRGRR016, NOGRR154, NPRR825(b), NPRR867, NPRR884, NPRR895, PGRR066
1/1
2/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
11/1
ü
11/19
6/1
ü
ü
ü
ü
ü
ü
10/1
ü
ü
ü
ü
ü
ü

## Slide 8: 2019 Releases – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/5 – 2/7 | April 4/2 – 4/4 | May 5/28 – 5/30 | August 8/6 – 8/8 | October 10/15 – 10/17 | December 12/10 – 12/12
NPRR842 NPRR858 NPRR878 SCR794 PGRR057(b) OBDRR011 RMGRR156 PGRR062 NPRR916(a) | NPRR809(b) NPRR817 NPRR833(a/b) NPRR845 NPRR847 NPRR865 NPRR866 NPRR880 VCMRR021 RRGRR017 VCMRR022 NPRR877 Ph1 NPRR833(c) NPRR749 | NPRR901 NPRR910 NPRR912 NPRR916(b) NOGRR174 OBDRR010 NPRR909 NPRR519 NPRR620 NPRR741 NPRR755 NOGRR154 | NPRR925 SCR793 SCR796 SCR798 OBDRR003 OBDRR014 NPRR821 PGRR066 NPRR899 | NPRR895 NPRR914 NPRR923 OBDRR007 PGRR061 PGRR070(a) RR917(a) NPRR889 RMGRR155 RRGRR018 NPRR921 NOGRR185 PGRR069 | NPRR911 NPRR952 NPRR972 PGRR072 NPRR920
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
NPRR809(b) – Reporting/posting system changes
NPRR833(a/b) – DAM/SCED system changes
NPRR833(c) – CRR system changes
NPRR916(a) – Mitigated Offer Floor to $0/MWh
NPRR916(b) – Mitigated Offer Floor to -$20/MWh
PGRR057(b) – List of GMD event contingencies
PGRR070(a) – Sect. 3.1.8, paragraphs (1) and (2)
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
7/1
6/2
ü
ü
CMM Release 1b
5/1
1/22
3/26
ü
ü
ü
ü
ü
ü
ü
TBD Items | 2017 | 2018 | 2019
 | NPRR702, NPRR829 | NPRR825(b), NPRR867, NPRR841 | NPRR887,NPRR904,OBDRR009,NPRR905,NPRR936,NPRR939,NPRR951, PGRR066,SCR804
3/1
3/5
5/6 – 5/7
12/9
RARF (SCR781)
Testing/Training of View/Update
(Go-Live in April 2020)
ü
R1
R2
R3
R4
R5
R6
ü
4/10
ü
ü
6/15
ü
ü
ü
ü
ü
ü
ü
ü
ü
6/1
9/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
8/1
ü
10/18
11/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
12/16
ü
ü
ü
ü
ü

## Slide 9: 2020 Releases – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/29 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR873 SCR797 NPRR877 Ph2 NPRR968 NPRR943 EMIL Web Interface NPRR863 FFR NPRR960 NOGRR187 OBDRR011 | SCR802 NPRR928 NPRR929 NPRR978(a) NPRR988 NPRR953 | NPRR856 NPRR884 OBDRR006 SCR803 NPRR887 NPRR907 NPRR985 RMGRR163 NPRR837 NPRR930(a) NPRR933 RRGRR021 | NPRR935(a) NPRR951 NPRR977 NPRR955 NOGRR183 SCR781(a) RRGRR016 RRGRR019 | MIS Go-Live RIOO R2 MMS/OS Refresh | SCR806 NPRR978(b)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
3/1
NPRR930(a) – O&M portion
NPRR935(a) – Sections 4.2.2 (1) (6), 4.2.5
NPRR935(b) – Sections 2.1, 2.2, 4.2.3
NPRR978(a) – Initial report decommissions
NPRR978(b) – Non-Forecast Zone scope
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
ü
ü
ü
December
Off-Cycle
1/1
1/19
E
ü
ü
ü
CMM Release 2a
1/30
8/1
November
RIOO – 9/3
RARF Go-Live - View/Update
ü
ü
ü
ü
ü
ü
ü
ü
ü
5/1
ü
7/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
10/1
ü
ü
ü
ü
ü
ü

## Slide 10: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/2 – 2/4 | April 3/30 – 4/1 | May 5/25 – 5/27 | July 7/27 – 7/29 | October 10/5 – 10/7 | December 12/7 – 12/9
NPRR902(a) NOGRR195 NPRR1055 OBDRR023(a) NPRR1020 SCR804 | NPRR971 NPRR986 NPRR998 NPRR1024 NPRR1043 NOGRR213 VCMRR027 PGRR070 NPRR1060 | NPRR974 NPRR978(c) NPRR1048 NPRR1051 SCR811 ECMS ECMS NPRR1080 OBDRR030 NPRR1081(a) | NPRR902(b) NPRR905 SCR789 NPRR1062 RMGRR164 NPRR1031 RRGRR026 NPRR867 NPRR1081(b) | None NPRR984 OBDRR023(b) | None SCR781
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR902(a) – ECEII Market Participant MPIM role
NPRR902(b) – MIS links updated for ECEII reports
NPRR978(c) – Forecast Zone scope
NPRR1081(a) – Manual implementation
NPRR1081(b) – Automated solution
OBDRR023(a) – ERS Expenditure Limit
OBDRR023(b) – 4 Standard Contract Terms/Year
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 879, 885, 904, 918, 930, 935(b), 936, 941, 945, 962, 965, 1004, 1006, 1019, 1023, 1030, 1032, 1034, 1040, 1057 SCRs: 799, 805, 809, 812 Market Guides: PGRR066, PGRR076 Other Binding Docs: OBDRR009
E
Replace NoticeBuilder
ECMS
11/17 – 11/20
New navigation
1/1
ü
ü
ü
2/1
10/1
5/1
3/15
ü
ü
ü
ü
ü
ü
ü
ü
ü
4/22
ü
6/1
ü
RIOO – 12/20
Interconnection requests of less than 10MWs and DGRs
6/25
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
New public version of ERCOT.com homepage
ü
7/1
7/14
7/23
8/1
ü
ü
ü
ü
ü
ü
September
Various Dates
ü
ü
ü
ü
ü
ü

## Slide 11: 2022 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February Various Dates | April 4/5 – 4/7 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 NPRR1054(a) NPRR1005 NOGRR210 RRGRR025 NPRR917 NPRR1052 NPRR1065 NPRR1073 NPRR1016 PGRR082 NOGRR212 | None NPRR1092(a) | NPRR939 NPRR1093 NPRR1101 NPRR1113 NOGRR191 NOGRR198 NOGRR232 OBDRR032 OBDRR033 OBDRR035 SCR800 SCR809 SCR814 MarkeTrak User Interface Refresh | NPRR1108(a) NPRR935(b) NOGRR239 NPRR1129 NPRR1108(b) | None FFR Advancement (NPRR863 FFR) NPRR1120 OBDRR039 NPRR987(a) NPRR1002(a) NPRR1063 NPRR1142 | NPRR1084 NPRR1096(a) NPRR1097 SCR812 RIOO (“Create”, SODG, Load Resources)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
ü
ü
ü
ü
Securitization Subchapter N March Go-Live
1/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
DGR/DESR
NPRR935(b) – New solar forecasts and reports
NPRR987(a) – ESR Contribution to PRC
NPRR1002(a) – Charging Restrictions in Emergency Conditions
NPRR1054(a) – Portion of gray box
NPRR1092(a) – RUC offer floor change
NPRR1096(a) – Non-Spin portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,962,963,965,975,987,995,1004,1006,1007,1019,1023,1026,1030,1032,1034,1057, 1077,1090,1092(b),1105 SCRs: 799,805,807,810,813,816,818,819 PGRRs: 066,076,088,091,094,099 Other: OBDRR009,OBDRR017,RRGRR028
ü
ü
ü
ü
6/4 – 6/6
7/1
5/13
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
10/13
ü
ü
ü
7/15
ü
8/16
ü
12/1
ü
12/9
ü
ü
ü
ü
ü

## Slide 12: 2023 Releases – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 1/31 – 2/2 | March 3/28 – 3/30 | June 6/6 – 6/8 | July 7/25 – 7/27 | October 10/3 – 10/5 | December 12/5 – 12/7
NPRR1020(a) | None | ECRS (NPRR863) NPRR903 NPRR992 NPRR1015 NPRR1085 NPRR1096(b) NPRR1148 NOGRR186 NOGRR187 OBDRR043/44 NPRR1135 | Securitization Phase 2A – Maine Invoice and Credit Exposure SCR789 Ph2 NPRR1112 | NPRR1154 LPGRR070 NPRR1163 NPRR1136 NPRR1175 NPRR1189 OBDRR048 EMS Upgrade SCR824 | SCR807 SCR816 SCR822 NOGRR249(a) NPRR1026(a) NPRR1164 PGRR081 RRGRR033 NPRR1153
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1020(a) – EPS Metering portion
NPRR1026(a) – SLF – RIOO portion
NPRR1096(b) – ECRS portion
NOGRR249(a) – GridGeo portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,963,965,975,987,995,1004,1006,1007,1019,1030,1032,1034,1057, 1077,1105,1111, 1128,1131 SCRs: 799,805,810,818,819 PGRRs: 066,076,088,091,094,099,103 Other: OBDRR009,OBDRR017,RRGRR028
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
11/2
7/14
ü
ü
ü
10/1
ü
EMS Upgrade Freeze – July 2023 – Jan. 2024
11/1
6/28
ü
12/19
11/19 and 12/1
12/20

## Slide 13: 2024 Releases – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/25 | February 2/22 | March 3/28 | April 4/25 | May 5/30 | June 6/27
NPRR1092(b) PGRR098(a) ESR Telemetry Public API Enhancements | NPRR1132(a) RRGRR032 NOGRR249(b) NPRR1184(a) NPRR1026(b) NPRR1172(a) | NPRR1040 NOGRR247(a) NPRR1165 NPRR989(a) NPRR1038 NOGRR204(a) |  | SCR819 NPRR1111 Securitization Default Charge Supporting Data | NPRR1149 NPRR1186 NPRR1196 NPRR1121 NPRR1090 NPRR962 NPRR1139 NPRR1205(a)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R4
R5
R6
NPRR989(a) – ESR tech. req.
NPRR1026(b) – SLF – Reporting
NPRR1092(b) – Limit RUC Opt-Out
NPRR1132(a) – RIOO portion
NPRR1172(a) – RUC Process/Clawback
NPRR1184(a) – Interest calcs
NPRR1186(b) – 60 Day Reports
ü
ü
ü
ü
ü
ü
July 7/25 | August 8/22 | September 9/26 |  | TX SET 5.0 11/10 | December 12/11-12/12
 | NPRR1058 NPRR1131 NPRR1186(b) OBDRR040 SCR821 | Forecast Presentation Platform (CDR rpts) NPRR1002 RRGRR023 NOGRR208 | SCR799 SCR799 NPRR1205(b) NPRR1218 NPRR1231 | NPRR1095 NPRR1134 NPRR1168 SCR817 SCR823 RMGRRs: 168,169, 172,179 | NPRR1183 NPRR1184 PGRR082 PGRR094 PGRR108
R7
R8
R11
ü
ü
ü
ü
ü
ü
2/1
3/1
ü
ü
ü
ü
ü
1/1
2/16
4/1
Various effective dates
2/26
3/11
NPRR1205(a) – Credit Limit %
NPRR1205(b) – Credit Rating
NOGRR204(a) – ESR tech req
NOGRR247(a) – UFLS changes
NOGRR249(b) – MIS posting
PGRR098(a) – Section 4.1.1.8
R3
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
R9
6/1
ü
ü
ü
ü
ü
ü
ü
ü
7/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
NPRR1217
SCR799
ü
10/9
ü
ü
10/1
11/15
11/1
ü

## Slide 14: 2025 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/30 | February 2/27 | March 3/27 | April 4/24 | May 5/29 | June 6/26
NPRR945 NPRR1219 |  | NPRR1145 NPRR1253(a) | RTC+B Market Trials begin on 5/5/2025 | NPRR1253(b) | 
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R4
R5
R6
July 7/31 | August 8/28 | September 9/25 | October 10/23 |  | December 12/18
 |  |  |  |  | RTC+B Stabilization begins
R7
R8
R10
R11
E
NS
R3
R9
NPRR1007-1013
RTC+B Market Trials
Closed-loop SCED/LFC
Day-Ahead Market
Open-loop RTC SCED
QSE Telemetry Tests
RTC QSE Submission Testing
RTC QSE Telemetry Check-out
RTC+B Stabilization
RTC+B
12/5
NPRR963(a)
NPRR965
NPRR1000
NPRR1014
NPRR1054
NPRR1058
NPRR1172
NPRR1204
NPRR1216
NPRR1236
NPRR1245
NPRR1246
NOGRR211
NOGRR268
OBDRR020
OBDRR052
PGRR118
E
NPRR963(a) – Portion of NPRR
NPRR1253(a) – ICCP
NPRR1253(b) – Public API
ü
ü
1/1
NS
As of Feb 2025