## Production
Production | From | Solution
I know there was prior discussion on the CR IA on the MVIs - I think the guidelines are clear that those are optional but Im not sure CRs fully understood the rejects by the TDSPs which I think could be clarified | Big Data Energy | Referred to RMTTF for clarification in market training. Suggestion was for RMG section 7.3.4.1 on rejects to be incorporated to help reduce confusion.

## Cutover
Cutover

## Testing
TESTING
If a TDSP or a CR aren’t going to send a specified code that is required per the scripts, then we would suggest the TDSP or CR needs to state this prior to the testing starting and possibly a waiver given etc. o For example, if the script states that the REF*MSL is required then said TDSP needs to state that they don’t support this segment for whatever reason and therefore wont be sending it, and then the CR in those territories should be notified. Another suggestion would be that if a TDSP is never going to use that segment then to update the guidelines or permanently note or have a permanent waiver? o And likewise, the same should be for a CR. If the CR states that their business doesn’t support the BGN*07 CR or IA codes for example, then the CR needs to state that prior to testing starting and a wavier stated and also the TDSP notified.
If a script cannot be completed such as MCSA or ICSA or other due to a unexpected reject from the TDSP, then somehow a notification to the CR either via email and/or on the script tasks themselves etc.
Organize a call for Day 1 COB to discuss where flight is.
Review scripts ahead of 0225
Review users guide
Deliver test bed earlier