## Slide 1
RTC+B Task Force
Update
Matt Mereness
RTCBTF
Feb 19, 2025

## Slide 2: Outline
Focused discussion today:
  Work on 3 NPRRs (NPRR1268, 1269, 12970)
  Market Readiness
    2 Handbooks
    Training materials update

## Slide 3: RTCBTF Issues List
First red box is NPRR1269 for 3 policy issues (target April Board)
Second red box is IMM NPRR1268 for ASDC changes (target April Board)
Third red box is a clean-up NPRR1270 and remove automatic qualification (target April Board)
Still need evaluation of State of Charge and AS Duration (target June Board)
Market Trials

## Slide 4
Sequence and Dates for Market Trials to Go-Live
RTC QSE Submission Testing
(Submit COP, RT AS Offers,
DAM Virtual AS, Outages for ESRs)
Open-loop RTC SCED
(QSE offers, SCED non-binding award/dispatch)
Ongoing Open-Loop
& Periodic Closed-loop SCED/LFC
(QSE RTC offers and telemetry to support closed-loop frequency control test 2-3 tests of 2-4 hour durations)
RTC QSE Telemetry Check-out (QSEs add/verify new telemetry points for UDSP, New ramp rates, ESR telemetry)
Day-Ahead Market
(Non-binding DAM using QSE offers for at least 2 tests)
Transition to Go-Live
Upon completion of testing, confirmation of ERCOT and market readiness for Go-Live.
May 2025
June 2025
July 2025
Aug 2025
Sep 2025
Oct 2025
Nov 2025
Dec 2025
QSE Telemetry Tests
(Individual QSE to follow UDSP and support new ramp rate and ESR telemetry)
QSE Scorecards & Exit Criteria for each Trial Phase
Start
5/5/25
Start
7/7/25
30-day Market Notice
11/5/25
Start
9/2/25
Go-Live
12/5/25*
* Go-Live date reflects 12/5/2025 as first Operating Day
where 12/4/2025 is planned software migration.
March/April
2025
QSE/Vendor Submission Sandbox and Telemetry Points added Prod EMS model.

## Slide 5: Summary and Timeline of NPRRs that will be in flight
NPRR1268 for ASDC Modifications (IMM sponsor)
NPRR1269 for 3 Parameter/Policy Changes (ERCOT sponsor)
  AS Proxy Offer Floors
  ASDCs for Reliability Unit Commitment
  Ramp Rate Sharing
NPRR1270 for AS Qualification details (ERCOT sponsor)
State of Charge – TBD but targeting late-June Board
Timeline and vetting of RTC+B NPRRs
Jan 2025
Feb 2025
Mar 2025
Apr 2025
May 2025
June 2025
File NPRRs
(No impacts) Jan 28
PRS Table NPRRs
Feb 12
PRS Urgency & Apprv 3/12
TAC approval
March 26
Board Approval
April 8
PUCT Approval
May 15
RTCBTF: Jan 14, 23, Feb 7,19, March 5, 25
Stakeholder comments in Feb and March
ERCOT window for “re-factoring” development
ERCOT market trials deployed and begin on May 5, 2025

## Slide 6: Other Updates
TWG Meeting Feb 27
  ERCOT will continue to support detailed technical conversations such as adding telemetry points to network model, digital certificates, accessing ERCOT systems in March/April timeframe
Goal of strengthening communication and centralize content in March
  Developing new folders on RTCBTF home page
    Market Trials folder: Handbooks and supporting materials / FAQ
    Technical Support folder: Key TWG technical materials
  Leverage RTCB@ercot.com mailbox for support of stakeholder implementation questions
  Post ICCP/telemetry explanation video (recorded and posting later this week)
  Following guidance from RTCBTF to engage DSWG separately (ERCOT developing content)
Acknowledge need to get ahead of Closed-Loop LFC planning
Formal Market Trials begin in about 10 weeks

## Slide 7: RTCBTF Discussion today
Note that by the end of today’s meeting:
- Need to have discussed key positions/issues for each NPRR to provide to TAC next week
Discussion of NPRR 1268- IMM Modifications to ASDCs / IMM staff
a. Hunt Energy Presentation and prior comments
b. ERCOT presentation and draft comments
Discussion of NPRR 1269- ERCOT 3 Parameter Policy issues / ERCOT staff
a. AS Proxy Offer Floor
- IMM comments filed 2/6/25
b. RUC ASDC
- ERCOT to share analysis in presentation
c. Ramp sharing
Discussion of NPRR 1270 Clarification and AS Qualification / Nitika Mago
a. No comments filed
Market Readiness / ERCOT Staff
a. Initial Review of Handbook #3 – Open Loop SCED
b. Initial Review of Handbook #4 – QSE Telemetry Tests
c. Draft Operator Training Seminar slides (work-in-progress)
Extra meeting- Friday March 7 for NPRRs (before March 12 PRS meeting)