## Sheet1
April
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Script Day
Date |  |  | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05
Script Day
Date | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12
Script Day | 2025-04-09: Application Deadline
Date | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19
Script Day
Date | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26
Script Day
Date | 2025-04-20: 2025-04-27; 2025-04-21: 2025-04-28; 2025-04-22: 2025-04-29; 2025-04-23: 2025-04-30
May | bar: 2025-04-21 to 2025-04-25
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Script Day
Date | 2025-04-24: 2025-05-01; 2025-04-25: 2025-05-02; 2025-04-26: 2025-05-03
Script Day | 2025-04-23: Signup Deadline; 2025-04-25: Testing Matrix Available
Date | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10
Script Day | 2025-05-05: Test Specs Submit Deadline; 2025-05-06: Connectivity Testing Begins
Date | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17
Script Day | bar: 2025-05-12 to 2025-05-16
Date | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24
Script Day | bar: 2025-05-19 to 2025-05-23
Date | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31
June
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Script Day | 2025-05-27: Testbed Upload Due
Date | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07
Script Day |  | 1 | 2 | 3 | 4 | 5
Date | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14
Script Day |  | 6 | 7 | 8 | 9 | 10
Date | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21
Script Day |  | 11 | 12 | 13 | 14 | 15
Date | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28
Script Day | bar: 2025-06-22
Date | 2025-06-22: 2025-06-29; 2025-06-23: 2025-06-30
Notes: | 2025-06-22: The highlighted script days 11 through 15 represent Contingency Testing Dates. Flight is technically scheduled to conclude on test day 10. However, we will have until test day 15 only if necessary. This requires approval by the Flight Administrator and the TDSPs.
Formulas:
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1
Friday = [Thursday]+1
Saturday = [Friday]+1